## Cover
Test Plan
Generated: | November 28, 2025
Solution: | Safeid Authentication
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
FT-001 | Unit | SafeID Server Installation | Validate SafeID Enterprise server installation and startup | Server hardware provisioned | 1. Install SafeID software; 2. Configure database; 3. Start services; 4. Verify admin console access | SafeID admin console accessible with all services running | High | Not Started
FT-002 | Unit | Active Directory Integration | Validate SafeID syncs with Active Directory users and groups | AD connection configured | 1. Configure LDAP connection; 2. Test sync; 3. Verify user import; 4. Check group mapping | 500 users synced from AD with correct group assignments | High | Not Started
FT-003 | Unit | RADIUS Server Configuration | Validate RADIUS authentication service is operational | SafeID server running | 1. Configure RADIUS listener; 2. Add VPN as client; 3. Test authentication; 4. Verify logging | RADIUS responds to authentication requests with MFA | High | Not Started
FT-004 | Integration | YubiKey FIDO2 Enrollment | Validate user can self-enroll YubiKey via portal | Self-service portal deployed | 1. Access enrollment portal; 2. Insert YubiKey; 3. Follow enrollment wizard; 4. Confirm registration | YubiKey registered to user with FIDO2 credentials | High | Not Started
FT-005 | Integration | Cisco AnyConnect VPN MFA | Validate VPN authentication with YubiKey FIDO2 | VPN RADIUS integration complete | 1. Launch AnyConnect; 2. Enter credentials; 3. Tap YubiKey when prompted; 4. Verify connection | VPN connects after successful YubiKey tap | Critical | Not Started
FT-006 | Integration | Microsoft 365 SAML SSO | Validate M365 login with YubiKey authentication | SAML IdP configured for M365 | 1. Access M365 portal; 2. Redirect to SafeID; 3. Authenticate with YubiKey; 4. Return to M365 | User logged into M365 after YubiKey authentication | Critical | Not Started
FT-007 | Integration | AWS IAM Identity Center | Validate AWS console access with FIDO2 | AWS SAML federation configured | 1. Access AWS console; 2. Select SAML provider; 3. Authenticate with YubiKey; 4. Assume role | User accesses AWS with federated FIDO2 authentication | High | Not Started
FT-008 | System | Lost Token Recovery | Validate help desk can issue temporary token | User has lost YubiKey | 1. Help desk disables lost key; 2. Issues temp token; 3. User authenticates; 4. New key enrolled | User regains access with temporary then permanent token | High | Not Started

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
NFT-001 | Performance | Authentication Latency | Validate FIDO2 authentication completes within target time | Users enrolled with YubiKeys | 1. Measure tap-to-auth time; 2. Test 100 authentications; 3. Calculate average; 4. Check 99th percentile | Average authentication time under 2 seconds | Critical | Not Started
NFT-002 | Performance | Enrollment Time | Validate self-service enrollment completes quickly | Portal operational | 1. Time enrollment process; 2. Test 50 enrollments; 3. Calculate average; 4. Check user experience | Average enrollment time under 5 minutes per user | High | Not Started
NFT-003 | Performance | Concurrent Authentications | Validate system handles peak authentication load | 500 users enrolled | 1. Simulate 100 concurrent auths; 2. Monitor response times; 3. Check for failures; 4. Verify logging | 100 concurrent authentications succeed without degradation | High | Not Started
NFT-004 | Reliability | Server Failover | Validate HA failover for SafeID servers | HA pair configured | 1. Fail primary server; 2. Monitor failover; 3. Test authentication; 4. Measure recovery time | Failover completes within 30 seconds with no auth failures | High | Not Started
NFT-005 | Security | Phishing Resistance | Validate FIDO2 prevents credential phishing | FIDO2 enforcement enabled | 1. Attempt phishing simulation; 2. Verify origin binding; 3. Check cryptographic challenge; 4. Confirm rejection | FIDO2 rejects authentication to non-origin domains | Critical | Not Started
NFT-006 | Security | Token Theft Protection | Validate stolen YubiKey requires PIN | PIN policy enforced | 1. Attempt auth without PIN; 2. Verify PIN prompt; 3. Test incorrect PIN lockout; 4. Confirm security | Stolen YubiKey cannot authenticate without user PIN | Critical | Not Started
NFT-007 | Compliance | Audit Logging | Validate 3-year audit log retention configured | Logging enabled | 1. Verify log configuration; 2. Check retention settings; 3. Test log search; 4. Validate CMMC evidence | All authentication events logged with 3-year retention | High | Not Started
NFT-008 | Compliance | CMMC Level 2 Requirements | Validate MFA requirements for CMMC compliance | Full deployment complete | 1. Verify IA.2.078 network MFA; 2. Verify IA.2.079 privileged MFA; 3. Document evidence; 4. Prepare audit | All CMMC Level 2 MFA controls satisfied | Critical | Not Started

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
UAT-001 | Business Process | VPN Remote Access Workflow | Validate end-to-end remote access with YubiKey | User enrolled with YubiKey | 1. Connect from home network; 2. Launch VPN client; 3. Authenticate with YubiKey; 4. Access resources | Remote user connects via VPN with FIDO2 MFA | Critical | Not Started
UAT-002 | Business Process | M365 Daily Login | Validate daily M365 access experience | User enrolled with YubiKey | 1. Access Outlook web; 2. Authenticate with YubiKey; 3. Check SSO to Teams SharePoint; 4. Measure time | User accesses M365 apps with single FIDO2 authentication | High | Not Started
UAT-003 | Business Process | Mobile NFC Authentication | Validate YubiKey NFC works with mobile devices | YubiKey 5 NFC token | 1. Access M365 on mobile; 2. Tap YubiKey via NFC; 3. Verify authentication; 4. Check app access | Mobile authentication works with YubiKey NFC tap | High | Not Started
UAT-004 | User Interface | Self-Service Enrollment | Validate user can enroll without IT assistance | Portal access granted | 1. Access enrollment URL; 2. Login with password; 3. Register YubiKey; 4. Test authentication | User completes self-enrollment in under 5 minutes | High | Not Started
UAT-005 | User Interface | PIN Recovery | Validate user can reset YubiKey PIN | User has forgotten PIN | 1. Access PIN reset portal; 2. Verify identity; 3. Reset PIN; 4. Test authentication | User resets PIN and authenticates successfully | Medium | Not Started
UAT-006 | Business Process | Privileged Admin Access | Validate admin YubiKey for privileged operations | Admin enrolled with separate key | 1. Access admin console; 2. Authenticate with admin YubiKey; 3. Perform admin action; 4. Verify audit log | Admin actions require separate privileged YubiKey | Critical | Not Started