## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Poweredge Ci Infrastructure
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Planning | Project Kickoff | 1 day | Week 1 Day 1 | Week 1 Day 1 | None | Project Manager | Not Started
Planning | Current CI/CD Assessment | 2 days | Week 1 Day 1 | Week 1 Day 2 | Project Kickoff | DevOps Architect | Not Started
Planning | Pipeline Inventory and Analysis | 2 days | Week 1 Day 2 | Week 1 Day 3 | Assessment Start | DevOps Lead | Not Started
Planning | Artifact Storage Requirements | 2 days | Week 1 Day 3 | Week 1 Day 4 | Inventory Complete | DevOps Architect | Not Started
Planning | GitLab Configuration Design | 2 days | Week 1 Day 4 | Week 2 Day 1 | All Assessments | DevOps Architect | Not Started
Planning | Dell Hardware Order Submission | 1 day | Week 2 Day 1 | Week 2 Day 1 | Design Approved | Procurement | Not Started
Planning | Network and VLAN Preparation | 2 days | Week 2 Day 2 | Week 2 Day 3 | Order Submitted | Network Engineer | Not Started
Planning | GitLab License Procurement | 1 day | Week 2 Day 3 | Week 2 Day 3 | Design Approved | Procurement | Not Started
Deployment | Hardware Delivery and Rack | 1 day | Week 3 Day 1 | Week 3 Day 1 | Dell Delivery | Dell ProDeploy | Not Started
Deployment | Ubuntu Server Installation | 1 day | Week 3 Day 1 | Week 3 Day 1 | Hardware Racked | DevOps Engineer | Not Started
Deployment | Docker Enterprise Installation | 1 day | Week 3 Day 2 | Week 3 Day 2 | Ubuntu Installed | DevOps Engineer | Not Started
Deployment | GitLab Premium Deployment | 2 days | Week 3 Day 2 | Week 3 Day 3 | Docker Ready | DevOps Architect | Not Started
Deployment | GitLab Runner Configuration | 1 day | Week 3 Day 4 | Week 3 Day 4 | GitLab Deployed | DevOps Architect | Not Started
Deployment | JFrog Artifactory Installation | 2 days | Week 3 Day 4 | Week 3 Day 5 | Runner Config | DevOps Engineer | Not Started
Deployment | SAML SSO Integration | 1 day | Week 4 Day 1 | Week 4 Day 1 | GitLab Ready | Security Team | Not Started
Deployment | Docker Registry Configuration | 1 day | Week 4 Day 1 | Week 4 Day 1 | Artifactory Ready | DevOps Engineer | Not Started
Migration | Pipeline Template Creation | 2 days | Week 4 Day 2 | Week 4 Day 3 | Infrastructure Ready | DevOps Architect | Not Started
Migration | Platform Team Migration | 2 days | Week 4 Day 3 | Week 4 Day 4 | Templates Ready | DevOps Lead | Not Started
Migration | Backend Team Migration | 2 days | Week 4 Day 4 | Week 5 Day 1 | Platform Complete | DevOps Lead | Not Started
Migration | Frontend Team Migration | 2 days | Week 5 Day 1 | Week 5 Day 2 | Backend Complete | DevOps Lead | Not Started
Migration | Mobile Team Migration | 2 days | Week 5 Day 2 | Week 5 Day 3 | Frontend Complete | DevOps Lead | Not Started
Migration | QA Team Migration | 2 days | Week 5 Day 3 | Week 5 Day 4 | Mobile Complete | DevOps Lead | Not Started
Validation | Build Performance Testing | 1 day | Week 5 Day 5 | Week 5 Day 5 | All Teams Migrated | DevOps Architect | Not Started
Validation | Load Testing (24 concurrent) | 1 day | Week 6 Day 1 | Week 6 Day 1 | Performance Testing | DevOps Engineer | Not Started
Training | GitLab Admin Training | 1 day | Week 6 Day 1 | Week 6 Day 1 | Validation Complete | Training Lead | Not Started
Training | Pipeline Development Workshop | 0.5 day | Week 6 Day 2 | Week 6 Day 2 | Admin Training | Training Lead | Not Started
Training | Artifactory Management Training | 0.5 day | Week 6 Day 2 | Week 6 Day 2 | Admin Training | Training Lead | Not Started
Closure | Documentation Finalization | 1 day | Week 6 Day 3 | Week 6 Day 3 | All Training | Technical Writer | Not Started
Closure | Jenkins Deprecation Plan | 1 day | Week 6 Day 4 | Week 6 Day 4 | Documentation | DevOps Lead | Not Started
Closure | Project Acceptance Sign-off | 1 day | Week 6 Day 5 | Week 6 Day 5 | Deprecation Plan | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Hardware Ordered | Week 2 | 8 Dell PowerEdge R650 servers ordered with GitLab Premium license | Project Manager | Not Started
M2 | Infrastructure Ready | Week 3 | GitLab Artifactory and Docker registry operational | DevOps Architect | Not Started
M3 | Templates Complete | Week 4 | Pipeline templates for Java Node Docker builds ready | DevOps Architect | Not Started
M4 | Migration Complete | Week 5 | All 50 developers and 12 teams migrated from Jenkins | DevOps Lead | Not Started
M5 | Validation Complete | Week 6 | 5000 builds/day capacity and <5 min queue time verified | DevOps Architect | Not Started
M6 | Project Closure | Week 6 | Training complete Jenkins deprecated support transitioned | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Arch | DevOps | NetEng | SecOps | Dev | IT | Client
Project Charter and Kickoff | A | C | C | I | I | I | C | I
Current CI/CD Assessment | A | R | C | C | C | C | C | C
GitLab Configuration Design | A | R | C | C | C | I | I | I
Dell Hardware Procurement | A | C | I | I | I | I | R | C
GitLab Premium Deployment | A | R | C | I | I | I | C | I
GitLab Runner Configuration | A | R | C | I | I | I | C | I
Artifactory Installation | A | C | R | I | I | I | C | I
SAML SSO Integration | A | C | C | I | R | I | C | I
Pipeline Template Creation | A | R | C | I | I | C | I | I
Team Migration Execution | A | C | R | I | I | C | C | I
Build Performance Testing | A | R | C | I | I | I | I | I
GitLab Admin Training | A | I | R | I | I | C | C | C
Documentation Delivery | A | R | C | C | C | C | C | I
Production Go-Live Approval | A | C | C | C | C | C | C | R
Legend:
R | A A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders PM Architect CTO DevOps Lead | Launch project and align on scope and timeline | Project Manager | Week 1 Day 1
Steering Committee | Weekly | Executive sponsors PM CTO IT Director | Strategic updates budget review issue escalation | Project Manager | Fridays 10:00
Daily Standup | Daily | Core project team | Review progress blockers and daily priorities | Project Manager | Daily 09:00
Technical Review | Weekly | Architect DevOps Engineers Network Security | Technical decisions and implementation progress | DevOps Architect | Wednesdays 14:00
Migration Checkpoint | Daily | DevOps Lead Architect Team Leads | Team migration progress and pipeline issues | DevOps Lead | Week 4-5 Daily
Validation Review | Daily | Architect DevOps Engineers QA | Build performance and capacity testing results | DevOps Architect | Week 6 Daily
Training Coordination | Once | Training Lead DevOps IT Team | Training schedule and logistics confirmation | Training Lead | Week 5 Day 5
Go-Live Readiness | Daily | All stakeholders | Go-live checklist and final preparation | Project Manager | Week 6 Daily