## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Powerswitch Datacenter
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Planning | Project Kickoff | 1 day | Week 1 Day 1 | Week 1 Day 1 | None | Project Manager | Not Started
Planning | Current Network Assessment | 2 days | Week 1 Day 1 | Week 1 Day 2 | Project Kickoff | Network Architect | Not Started
Planning | Traffic Flow Analysis | 2 days | Week 1 Day 2 | Week 1 Day 3 | Assessment Start | Network Engineer | Not Started
Planning | VLAN and Subnet Planning | 2 days | Week 1 Day 3 | Week 1 Day 4 | Traffic Analysis | Network Architect | Not Started
Planning | BGP and EVPN Design | 2 days | Week 1 Day 4 | Week 2 Day 1 | VLAN Planning | Network Architect | Not Started
Planning | Dell Switch Order Submission | 1 day | Week 2 Day 1 | Week 2 Day 1 | Design Approved | Procurement | Not Started
Planning | Cabling and Rack Planning | 2 days | Week 2 Day 2 | Week 2 Day 3 | Order Submitted | Data Center Team | Not Started
Planning | Automation Playbook Development | 3 days | Week 2 Day 2 | Week 2 Day 4 | Design Approved | Network Architect | Not Started
Deployment | Switch Delivery and Rack Install | 1 day | Week 3 Day 1 | Week 3 Day 1 | Dell Delivery | Dell ProDeploy | Not Started
Deployment | Spine Switch Configuration | 2 days | Week 3 Day 1 | Week 3 Day 2 | Switches Racked | Network Architect | Not Started
Deployment | Rack 1-10 Leaf Deployment | 2 days | Week 3 Day 2 | Week 3 Day 3 | Spine Ready | Network Engineer | Not Started
Deployment | BGP Underlay Configuration | 1 day | Week 3 Day 3 | Week 3 Day 3 | Leaf Deployed | Network Architect | Not Started
Deployment | Rack 11-20 Leaf Deployment | 2 days | Week 3 Day 4 | Week 3 Day 5 | BGP Underlay | Network Engineer | Not Started
Deployment | EVPN-VXLAN Overlay Config | 2 days | Week 4 Day 1 | Week 4 Day 2 | Underlay Complete | Network Architect | Not Started
Deployment | Rack 21-30 Leaf Deployment | 2 days | Week 4 Day 2 | Week 4 Day 3 | Overlay Config | Network Engineer | Not Started
Deployment | TACACS+ AAA Integration | 1 day | Week 4 Day 3 | Week 4 Day 3 | Network Operational | Security Team | Not Started
Deployment | Rack 31-40 Leaf Deployment | 2 days | Week 4 Day 4 | Week 4 Day 5 | AAA Ready | Network Engineer | Not Started
Migration | Server Migration Rack 1-10 | 2 days | Week 5 Day 1 | Week 5 Day 2 | Rack Ready | Server Team | Not Started
Migration | Server Migration Rack 11-20 | 2 days | Week 5 Day 2 | Week 5 Day 3 | Rack 1-10 Complete | Server Team | Not Started
Migration | Server Migration Rack 21-30 | 2 days | Week 5 Day 3 | Week 5 Day 4 | Rack 11-20 Complete | Server Team | Not Started
Migration | Server Migration Rack 31-40 | 2 days | Week 5 Day 4 | Week 5 Day 5 | Rack 21-30 Complete | Server Team | Not Started
Validation | East-West Traffic Testing | 1 day | Week 6 Day 1 | Week 6 Day 1 | All Servers Migrated | Network Engineer | Not Started
Validation | Fabric Throughput Testing | 1 day | Week 6 Day 1 | Week 6 Day 1 | Traffic Testing | Network Architect | Not Started
Training | Network Admin Training | 1 day | Week 6 Day 2 | Week 6 Day 2 | Validation Complete | Training Lead | Not Started
Training | Ansible Automation Workshop | 0.5 day | Week 6 Day 3 | Week 6 Day 3 | Admin Training | Training Lead | Not Started
Training | OS10 CLI Operations | 0.5 day | Week 6 Day 3 | Week 6 Day 3 | Admin Training | Training Lead | Not Started
Closure | Documentation Finalization | 1 day | Week 6 Day 4 | Week 6 Day 4 | All Training | Technical Writer | Not Started
Closure | Legacy Switch Decommission Plan | 1 day | Week 6 Day 4 | Week 6 Day 4 | Documentation | Network Architect | Not Started
Closure | Project Acceptance Sign-off | 1 day | Week 6 Day 5 | Week 6 Day 5 | Decommission Plan | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Hardware Ordered | Week 2 | 4 spine Z9432F-ON and 40 leaf S5248F-ON switches ordered | Project Manager | Not Started
M2 | Spine Layer Ready | Week 3 | 100GbE spine fabric with BGP underlay operational | Network Architect | Not Started
M3 | Leaf Layer Complete | Week 4 | All 40 ToR switches deployed with EVPN-VXLAN overlay | Network Architect | Not Started
M4 | Migration Complete | Week 5 | All 1920 server ports migrated from Cisco to Dell fabric | Network Engineer | Not Started
M5 | Validation Complete | Week 6 | 1.6Tbps throughput and <2 microsecond latency verified | Network Architect | Not Started
M6 | Project Closure | Week 6 | Training complete Cisco deprecated support transitioned | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Arch | NetEng | DC | SecOps | Server | IT | Client
Project Charter and Kickoff | A | C | C | I | I | I | C | I
Current Network Assessment | A | R | C | C | C | C | C | C
BGP EVPN Design | A | R | C | I | C | I | I | I
Dell Switch Procurement | A | C | I | I | I | I | R | C
Spine Switch Configuration | A | R | C | I | I | I | C | I
Leaf Switch Deployment | A | C | R | C | I | I | C | I
EVPN-VXLAN Overlay Configuration | A | R | C | I | I | I | C | I
TACACS+ AAA Integration | A | C | C | I | R | I | C | I
Server Migration Execution | A | C | C | C | I | R | C | I
Fabric Performance Testing | A | R | C | I | I | I | I | I
Network Admin Training | A | I | R | I | I | I | C | C
Documentation Delivery | A | R | C | C | C | C | C | I
Production Go-Live Approval | A | C | C | C | C | C | C | R
Legend:
R | A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders PM Architect CTO Network Lead | Launch project and align on scope and timeline | Project Manager | Week 1 Day 1
Steering Committee | Weekly | Executive sponsors PM CTO IT Director | Strategic updates budget review issue escalation | Project Manager | Fridays 10:00
Daily Standup | Daily | Core project team | Review progress blockers and daily priorities | Project Manager | Daily 09:00
Technical Review | Weekly | Architect Network Engineers Data Center Security | Technical decisions and implementation progress | Network Architect | Wednesdays 14:00
Migration Checkpoint | Daily | Network Engineer Server Team Data Center | Rack migration progress and connectivity issues | Network Engineer | Week 5 Daily
Validation Review | Daily | Architect Network Engineers QA | Fabric performance and latency testing results | Network Architect | Week 6 Daily
Training Coordination | Once | Training Lead Network Ops IT Team | Training schedule and logistics confirmation | Training Lead | Week 5 Day 5
Go-Live Readiness | Daily | All stakeholders | Go-live checklist and final preparation | Project Manager | Week 6 Daily