## Cover
Level Of Effort Estimate
Presales Document
Generated: | November 15, 2025
Solution: | Disaster Recovery Web Application
Customer Name: | [Customer Name]
Version: | 1.0

## Scope Assumptions
Column 1 | Column 2 | Column 3 | Column 4 | Column 5

## Estimate Settings
INSTRUCTIONS: How to Use Estimate Settings
This sheet contains phase-based multiplier variables that control effort scaling for each project phase.
The EO Sales Engineer updates these multipliers based on customer scope compared to baseline assumptions.
How It Works:
1. Review customer requirements from Discovery Questionnaire
2. Compare customer scope to Baseline Assumptions (see 'Scope Assumptions' sheet)
3. Update YELLOW HIGHLIGHTED multiplier values below (Column C) for each phase
4. All tasks in that phase on the 'LOE' sheet automatically update their Actual Hours
5. Total cost recalculates automatically
Multiplier Guidelines:
• 1.0 = Matches baseline exactly (Small scope)
• 1.5-2.0 = Medium scope (moderately above baseline)
• 2.0-3.0 = Large scope (significantly above baseline)
• 3.0+ = Very large/complex (substantially above baseline, document rationale)
Example: Customer needs comprehensive testing due to compliance → Set TESTING_MX to 2.0
Example: Complex architecture requiring more technical oversight → Set LEADERSHIP_MX to 1.5
ESTIMATE SETTINGS - Update phase multipliers in Column C below: