## Cover
Test Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Onpremise To Cloud Migration
Customer Name: | Data table for test plan
Version: | 1.0

## Test Plan
Test ID | Test Category | Test Phase | Test Name | Test Description | Test Objectives | Prerequisites | Test Environment | Test Data Required | Owner | Estimated Duration | Priority | Status | Pass Criteria | Fail Criteria | Notes
TST-MIG-001 | Pre-Migration | Assessment | Application Dependency Testing | Test all application dependencies and external integrations | Validate application connectivity and dependency mapping | Application discovery complete | On-premise environment | Production-like test data | Migration Architect | 4 hours | High | Not Started | All dependencies identified and documented | Critical dependencies missing or inaccessible | Include database APIs and network dependencies
TST-MIG-002 | Pre-Migration | Assessment | Network Connectivity Testing | Test network connectivity and bandwidth requirements | Validate network performance and identify bottlenecks | Network topology documented | On-premise and cloud environments | Network performance baselines | Network Engineer | 6 hours | High | Not Started | Network meets migration bandwidth requirements | Network bandwidth insufficient for migration | Include latency and packet loss measurements
TST-MIG-003 | Pre-Migration | Assessment | Application Performance Baseline | Establish performance baselines for all applications | Document current performance metrics for comparison | Applications identified and accessible | On-premise environment | Production workload data | Performance Engineer | 8 hours | High | Not Started | Performance baselines documented for all applications | Unable to establish reliable performance metrics | Critical for post-migration comparison
TST-MIG-004 | Pre-Migration | Assessment | Data Integrity Validation | Validate data integrity and establish data quality baselines | Ensure data quality before migration | Database access and documentation | Source database systems | Production database snapshots | Data Migration Specialist | 12 hours | Critical | Not Started | Data integrity validated with checksums and counts | Data corruption or inconsistencies detected | Include referential integrity and business rule validation
TST-MIG-005 | Migration Tools | Setup | AWS MGN Replication Testing | Test AWS Application Migration Service replication | Validate replication process and data synchronization | AWS environment setup complete | AWS and on-premise environments | Sample application servers | Migration Engineer | 6 hours | High | Not Started | Successful replication with minimal lag | Replication failure or excessive lag | Include bandwidth throttling and encryption testing
TST-MIG-006 | Migration Tools | Setup | Database Migration Service Testing | Test AWS DMS for database migration | Validate database migration tools and processes | DMS setup and configuration complete | AWS DMS environment | Database migration test datasets | Database Administrator | 8 hours | Critical | Not Started | Successful database replication and synchronization | Data loss or replication failures | Include both homogeneous and heterogeneous migrations
TST-MIG-007 | Migration Tools | Setup | Data Validation Script Testing | Test automated data validation scripts and procedures | Ensure data migration accuracy and completeness | Data validation scripts developed | Test environment | Representative data samples | Data Migration Specialist | 4 hours | High | Not Started | 100% data validation accuracy | Data validation failures or false positives | Include checksum validation and record count verification
TST-MIG-008 | Security | Implementation | Cloud Security Controls Testing | Test AWS security controls and configurations | Validate security implementation and compliance | AWS security services configured | AWS test environment | Security test scenarios | Security Engineer | 12 hours | Critical | Not Started | All security controls functioning and compliant | Security control failures or compliance gaps | Include IAM policies security groups and encryption
TST-MIG-009 | Security | Implementation | Network Security Testing | Test network security controls and access restrictions | Validate network segmentation and security policies | Network security groups configured | AWS network environment | Network security test cases | Security Engineer | 8 hours | High | Not Started | Network security controls properly restricting access | Unauthorized access or security policy failures | Include penetration testing and vulnerability scanning
TST-MIG-010 | Security | Implementation | Data Encryption Testing | Test data encryption at rest and in transit | Validate encryption implementation and key management | Encryption services configured | AWS environment with KMS | Encrypted test data | Security Engineer | 6 hours | Critical | Not Started | All data properly encrypted with correct key management | Encryption failures or key management issues | Include S3 EBS and RDS encryption testing
TST-MIG-011 | Migration Execution | Wave 0 Pilot | Pilot Migration Testing | Execute pilot migration with selected applications | Validate migration process and identify issues | Pilot applications selected and assessed | Pilot migration environment | Pilot application data | Migration Team | 16 hours | Critical | Not Started | Successful pilot migration with documented lessons learned | Pilot migration failures or critical issues | Include comprehensive testing and rollback validation
TST-MIG-012 | Migration Execution | Wave 1 | Application Functionality Testing | Test migrated application functionality | Ensure all application features work correctly in AWS | Applications migrated to AWS | AWS production environment | Application test datasets | QA Engineer | 20 hours | Critical | Not Started | All application functionality working as expected | Critical application functionality failures | Include user workflows and business processes
TST-MIG-013 | Migration Execution | Wave 1 | Database Migration Validation | Validate database migration accuracy and performance | Ensure data integrity and database performance | Database migration completed | AWS RDS environment | Production database copy | Database Administrator | 12 hours | Critical | Not Started | Database migration 100% accurate with acceptable performance | Data loss corruption or performance degradation | Include transaction log validation and performance benchmarking
TST-MIG-014 | Migration Execution | Wave 1 | Integration Testing | Test application integrations and data flows | Validate all system integrations work correctly | All integrated systems available | AWS and hybrid environment | Integration test datasets | Integration Specialist | 16 hours | High | Not Started | All integrations functioning with proper data flow | Integration failures or data flow issues | Include API testing and data synchronization validation
TST-MIG-015 | Performance | Validation | Application Performance Testing | Test application performance in AWS environment | Validate performance meets or exceeds baselines | Applications deployed and configured | AWS performance test environment | Performance test workloads | Performance Engineer | 24 hours | High | Not Started | Performance meets or exceeds baseline metrics | Performance degradation beyond acceptable thresholds | Include load testing and stress testing scenarios
TST-MIG-016 | Performance | Validation | Database Performance Testing | Test database performance and optimization | Validate database performance in cloud environment | Database migrated and optimized | AWS RDS environment | Database performance test queries | Database Administrator | 12 hours | High | Not Started | Database performance meets SLA requirements | Database performance below acceptable levels | Include query optimization and connection pooling testing
TST-MIG-017 | Performance | Validation | Auto-Scaling Testing | Test auto-scaling policies and configurations | Validate automatic scaling under load | Auto-scaling configured | AWS production environment | Load testing tools and scenarios | Cloud Engineer | 8 hours | Medium | Not Started | Auto-scaling responds appropriately to load changes | Auto-scaling failures or improper scaling behavior | Include scale-out and scale-in testing scenarios
TST-MIG-018 | High Availability | Validation | Multi-AZ Failover Testing | Test multi-AZ failover and recovery | Validate high availability configurations | Multi-AZ deployment configured | AWS production environment | Failover test procedures | Infrastructure Engineer | 6 hours | High | Not Started | Successful failover with minimal downtime | Failover failure or excessive downtime | Include automated failover and manual failover testing
TST-MIG-019 | Disaster Recovery | Validation | Backup and Recovery Testing | Test backup and recovery procedures | Validate backup completeness and recovery time | Backup solutions implemented | AWS backup environment | Test backup datasets | Backup Administrator | 8 hours | High | Not Started | Successful backup and recovery within RTO/RPO | Backup failure or recovery time exceeding RTO | Include cross-region backup and point-in-time recovery
TST-MIG-020 | Disaster Recovery | Validation | Disaster Recovery Testing | Test complete disaster recovery procedures | Validate DR capabilities and documentation | DR environment established | AWS DR region | DR test scenarios | DR Specialist | 16 hours | High | Not Started | Successful DR with RTO/RPO compliance | DR failure or RTO/RPO not met | Include full application stack recovery and validation
TST-MIG-021 | User Acceptance | Validation | Business User Acceptance Testing | Business users validate migrated applications | Ensure applications meet business requirements | Applications migrated and functional | AWS production environment | Business test scenarios | Business Users | 40 hours | Critical | Not Started | Business users accept all migrated functionality | Business requirements not met or user acceptance failure | Include training and change management validation
TST-MIG-022 | User Acceptance | Validation | End-to-End Business Process Testing | Test complete business processes in cloud environment | Validate end-to-end business workflows | All applications and integrations complete | AWS production environment | Business process test cases | Business Process Owners | 24 hours | High | Not Started | All business processes function correctly end-to-end | Business process failures or workflow disruptions | Include cross-application workflows and reporting
TST-MIG-023 | Operations | Readiness | Monitoring and Alerting Testing | Test monitoring and alerting systems | Validate operational monitoring capabilities | Monitoring solutions deployed | AWS production environment | Monitoring test scenarios | Operations Team | 8 hours | High | Not Started | All monitoring and alerts functioning correctly | Monitoring gaps or alert failures | Include custom metrics and automated response testing
TST-MIG-024 | Operations | Readiness | Runbook and Procedure Testing | Test operational runbooks and procedures | Validate operational readiness and documentation | Runbooks and procedures documented | AWS production environment | Operational test scenarios | Operations Team | 12 hours | Medium | Not Started | All operational procedures function as documented | Procedure failures or documentation gaps | Include incident response and troubleshooting procedures
TST-MIG-025 | Rollback | Contingency | Migration Rollback Testing | Test migration rollback procedures | Validate ability to rollback migration if needed | Rollback procedures documented | AWS and on-premise environments | Rollback test scenarios | Migration Team | 8 hours | Critical | Not Started | Successful rollback to on-premise within defined timeframe | Rollback failure or excessive rollback time | Include data synchronization and application rollback testing
TST-MIG-026 | Security | Compliance | Compliance Validation Testing | Test compliance with regulatory requirements | Validate compliance framework implementation | Compliance controls implemented | AWS compliance environment | Compliance test scenarios | Compliance Officer | 16 hours | Critical | Not Started | Full compliance with all regulatory requirements | Compliance failures or gaps identified | Include SOC 2 PCI DSS and industry-specific compliance
TST-MIG-027 | Performance | Optimization | Cost Optimization Testing | Test cost optimization features and policies | Validate cost management and optimization | Cost optimization tools configured | AWS production environment | Cost optimization scenarios | FinOps Analyst | 6 hours | Medium | Not Started | Cost optimization achieving target savings | Cost optimization not meeting targets | Include Reserved Instance optimization and right-sizing validation