## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Enterprise Platform
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Foundation | Project Kickoff and Charter | 1 day | 2025-02-01 | 2025-02-01 | None | Project Manager | Not Started
Foundation | Stakeholder Engagement | 3 days | 2025-02-03 | 2025-02-05 | Project Kickoff | Project Manager | Not Started
Foundation | Current State Assessment | 5 days | 2025-02-06 | 2025-02-12 | Stakeholder Engagement | Platform Architect | Not Started
Foundation | Azure Subscription Setup | 2 days | 2025-02-13 | 2025-02-14 | Assessment Complete | Infrastructure Engineer | Not Started
Foundation | Azure AD Integration | 3 days | 2025-02-17 | 2025-02-19 | Subscription Ready | Security Engineer | Not Started
Foundation | Azure DevOps Organization Setup | 2 days | 2025-02-20 | 2025-02-21 | AD Integration | DevOps Lead | Not Started
Infrastructure | Network Infrastructure Configuration | 5 days | 2025-02-24 | 2025-02-28 | Organization Setup | Network Engineer | Not Started
Infrastructure | Azure Key Vault Setup | 2 days | 2025-03-03 | 2025-03-04 | Network Ready | Security Engineer | Not Started
Infrastructure | Azure Container Registry Deployment | 2 days | 2025-03-05 | 2025-03-06 | Key Vault Ready | DevOps Engineer | Not Started
Infrastructure | Azure Kubernetes Service Setup | 5 days | 2025-03-07 | 2025-03-13 | ACR Ready | Container Engineer | Not Started
Infrastructure | Monitoring Infrastructure Setup | 3 days | 2025-03-14 | 2025-03-18 | AKS Ready | Monitoring Specialist | Not Started
Pipelines | CI/CD Pipeline Templates Creation | 7 days | 2025-03-19 | 2025-03-27 | Infrastructure Complete | Senior DevOps Engineer | Not Started
Pipelines | Build Agent Configuration | 3 days | 2025-03-28 | 2025-04-01 | Templates Ready | DevOps Engineer | Not Started
Pipelines | Security Scanning Integration | 5 days | 2025-04-02 | 2025-04-08 | Agents Ready | Security Engineer | Not Started
Pipelines | Infrastructure as Code Development | 5 days | 2025-04-09 | 2025-04-15 | Scanning Ready | Infrastructure Engineer | Not Started
Pipelines | Test Automation Framework Setup | 5 days | 2025-04-16 | 2025-04-22 | IaC Complete | QA Engineer | Not Started
Migration | Repository Migration Planning | 3 days | 2025-04-23 | 2025-04-25 | Pipelines Complete | DevOps Lead | Not Started
Migration | Pilot Team Selection | 2 days | 2025-04-28 | 2025-04-29 | Planning Complete | Project Manager | Not Started
Migration | Pilot Migration Execution | 7 days | 2025-04-30 | 2025-05-08 | Pilot Selected | Migration Team | Not Started
Migration | Pilot Phase Review | 2 days | 2025-05-09 | 2025-05-12 | Pilot Complete | Project Manager | Not Started
Test | Functional Testing | 5 days | 2025-05-13 | 2025-05-19 | Pilot Review | QA Engineer | Not Started
Test | Security Testing | 3 days | 2025-05-20 | 2025-05-22 | Functional Complete | Security Engineer | Not Started
Test | Performance Testing | 3 days | 2025-05-23 | 2025-05-27 | Security Complete | Performance Engineer | Not Started
Test | User Acceptance Testing | 5 days | 2025-05-28 | 2025-06-03 | Performance Complete | Business Users | Not Started
Deploy | Production Deployment | 2 days | 2025-06-04 | 2025-06-05 | UAT Complete | Deployment Team | Not Started
Deploy | Go-Live Support | 5 days | 2025-06-06 | 2025-06-12 | Deployment Complete | Support Team | Not Started
Training | Training Material Development | 10 days | 2025-05-19 | 2025-05-30 | Pilot Complete | Training Team | Not Started
Training | Developer Training | 3 days | 2025-06-02 | 2025-06-04 | Materials Ready | Training Team | Not Started
Training | Admin Training | 2 days | 2025-06-05 | 2025-06-06 | Developer Training | Training Team | Not Started
Closure | Hypercare Support | 30 days | 2025-06-09 | 2025-07-18 | Go-Live | Support Team | Not Started
Closure | Project Documentation | 5 days | 2025-07-14 | 2025-07-18 | Hypercare | Project Manager | Not Started
Closure | Project Closure | 2 days | 2025-07-21 | 2025-07-22 | Documentation Complete | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | 2025-02-01 | Kickoff meeting held; project charter signed; team assigned and onboarded | Project Manager | Not Started
M2 | Foundation Complete | 2025-02-21 | Azure DevOps organization configured; AD integration complete; RBAC implemented | DevOps Lead | Not Started
M3 | Infrastructure Ready | 2025-03-18 | AKS cluster deployed; ACR configured; monitoring operational | Infrastructure Engineer | Not Started
M4 | Pipeline Framework Complete | 2025-04-22 | CI/CD templates ready; security scanning integrated; IaC deployed | Senior DevOps Engineer | Not Started
M5 | Pilot Complete | 2025-05-12 | Pilot teams migrated; pipelines operational; lessons learned documented | DevOps Lead | Not Started
M6 | Testing Complete | 2025-06-03 | All test cases passed; security validated; UAT signed off | QA Lead | Not Started
M7 | Go-Live | 2025-06-05 | Production deployment complete; platform operational; monitoring active | Project Manager | Not Started
M8 | Training Complete | 2025-06-06 | All developers trained; admin team certified; documentation delivered | Training Team | Not Started
M9 | Project Closure | 2025-07-22 | Hypercare complete; documentation delivered; lessons learned captured | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | DevOps Lead | Sec Eng | Infra Eng | QA | Dev Team | Client IT | Sponsor
Project Charter and Kickoff | A | C | I | I | I | I | C | C
Azure DevOps Organization Setup | A | R | C | C | I | I | C | I
Infrastructure Deployment | A | C | C | R | I | I | C | I
CI/CD Pipeline Framework | A | R | C | C | I | C | I | I
Security Scanning Integration | A | C | R | I | I | I | C | I
Repository Migration | A | R | C | I | I | C | C | I
Test Automation Setup | A | C | I | I | R | C | I | I
Developer Training | A | C | I | I | I | R | I | I
Production Deployment | A | R | C | C | C | I | C | I
Hypercare Support | A | R | C | C | C | I | C | I
Legend:
R | A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders and project team | Launch project and align on objectives | Project Manager | Day 1 10:00
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic direction and issue resolution | Project Manager | Alternate Tuesdays 14:00
Status Meeting | Weekly | Core project team | Review progress and address blockers | Project Manager | Mondays 10:00
Technical Review | Weekly | DevOps lead and engineers | Pipeline development and technical decisions | DevOps Lead | Wednesdays 14:00
Security Review | Bi-weekly | Security engineer and DevOps team | Security scanning and compliance review | Security Engineer | Alternate Thursdays 11:00
Migration Sync | Weekly | Migration team and pilot teams | Migration progress and issue resolution | DevOps Lead | Fridays 10:00
Go-Live Readiness | Daily (Week -1) | Go-live team and stakeholders | Cutover preparation and checklist review | Project Manager | Daily 09:00
Hypercare Standup | Daily (30 days) | Support team and operations | Post-go-live issues and optimization | Support Lead | Daily 09:30