## Cover
[DOCUMENT TITLE]
Level of Effort
JUNIPER - Cyber-Security - Srx Firewall Platform
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Datacenter Firewalls | 2 SRX4600 (HA pair) | 2 SRX4600 (HA pair) | 4 SRX5400 (2 HA pairs) | 8+ SRX5800 (4 HA pairs) | Enterprise datacenter firewall deployment
Solution Scope | Branch Firewalls | 10 SRX300 branch sites | 10 SRX300 branch sites | 25 SRX345 branch sites | 50+ SRX380 branch sites | Branch office firewall and SD-WAN deployment
Integration | Firewall Rules to Migrate | 500 firewall rules | 500 firewall rules | 1500 firewall rules | 3000+ firewall rules | Policy migration from legacy ASA or firewall platform
Integration | External System Integrations | 2 integrations (SIEM NAC) | 2 integrations (SIEM NAC) | 4-6 systems | 8+ systems or complex protocols | SIEM NAC authentication and management integration
Integration | VPN Tunnels | 30 site-to-site + 100 SSL VPN | 30 site-to-site + 100 SSL VPN | 100 site-to-site + 500 SSL VPN | 300+ site-to-site + 1500 SSL VPN | IPsec VPN tunnels and SSL VPN remote users
User Base | Network Administrators | 4 firewall administrators | 2-4 administrators | 6-10 administrators | 15+ administrators | Firewall administrators and security operators
User Base | Remote Users | 100 SSL VPN users | 100 SSL VPN users | 500 SSL VPN users | 1500+ SSL VPN users | Remote access SSL VPN concurrent users
Data Volume | Firewall Throughput | 80 Gbps datacenter firewall | 80 Gbps datacenter | 160 Gbps datacenter | 400+ Gbps datacenter | Total firewall throughput with security services
Data Volume | IPS Throughput | 40 Gbps IPS inspection | 40 Gbps IPS | 80 Gbps IPS | 200+ Gbps IPS | Intrusion prevention system throughput
Technical Environment | Deployment Locations | 1 datacenter + 10 branches | 1 datacenter + 10 branches | 2 datacenters + 25 branches | 4+ datacenters + 50+ branches | Geographic distribution for firewall deployment
Technical Environment | Availability Requirements | High availability (99.9%) | High availability (99.9%) | Mission critical (99.95%) | Five nines (99.99%+) | SLA for firewall uptime and failover
Technical Environment | Infrastructure Complexity | Active/passive HA | Active/passive HA | Active/active HA multi-zone | Clustered HA multi-tenant | SRX HA architecture and redundancy design
Security & Compliance | Security Services | IPS ATP Cloud SecIntel | IPS ATP Cloud SecIntel | + SSL Inspection + URL Filtering | + Advanced Malware + Sandbox | Advanced security subscriptions and threat prevention
Security & Compliance | Compliance Frameworks | PCI DSS SOC 2 | 1-2 basic standards | 3-4 industry standards | Multiple complex frameworks (FedRAMP HIPAA) | Regulatory compliance for firewall security
Performance | Inspection Requirements | Standard L3/L4 + IPS | Standard L3/L4 + IPS | Deep packet inspection + SSL | Full DPI + SSL + Sandboxing | Firewall inspection depth and performance requirements
Performance | Session Capacity | 2 million concurrent sessions | 2 million sessions | 8 million sessions | 20+ million sessions | Concurrent firewall session capacity
Environment | Deployment Environments | 2 environments (lab prod) | 2 environments (lab prod) | 3 environments (lab stage prod) | 4+ environments with DR | Environment management for firewall deployment

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Security Architecture Assessment, Policy Migration Analysis, Network Topology Documentation, Requirements Gathering)
Planning | PLANNING_MX | 1 | All Planning phase tasks (SRX Security Architecture Design, Policy Migration Strategy, SD-WAN Design, Implementation Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Lab Environment Setup, Datacenter/Branch SRX Deployment, Security Policy Implementation, Advanced Security Services, VPN Configuration, Security Director Setup, SIEM Integration)
Testing | TESTING_MX | 1 | All Testing phase tasks (Lab Validation Testing, Performance Testing, HA Failover Testing, Security Validation, User Acceptance Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Datacenter Production Cutover, Branch Production Deployment, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (SRX Administrator Training, Security Operations Training, Documentation Development)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline)
Management | MANAGEMENT_MX | 1.5 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Security Architecture Assessment | Analyze current firewall infrastructure security policies and network topology | EO Engineer | 40 |  |  | 225 |  |  | Document existing ASA/firewall rules and security zones for migration analysis
Discovery | Policy Migration Analysis | Review and analyze 500+ firewall rules for migration and optimization | EO Engineer | 48 |  |  | 225 |  |  | Identify redundant rules consolidation opportunities and policy cleanup
Discovery | Network Topology Documentation | Document datacenter and branch network architecture with traffic flows | EO Engineer | 24 |  |  | 200 |  |  | Include all security zones DMZ trust untrust and cloud connectivity
Discovery | Requirements Gathering | Conduct stakeholder interviews for security and compliance requirements | EO Engineer | 16 |  |  | 200 |  |  | PCI DSS SOC 2 compliance and audit requirements documentation
Planning | SRX Security Architecture Design | Design security zones segmentation and SRX HA architecture | EO Engineer | 56 |  |  | 225 |  | Security Architecture Assessment | Deliverable: Multi-zone design with DMZ trust untrust and management zones
Planning | Policy Migration Strategy | Develop policy migration approach with optimization and testing plan | EO Engineer | 40 |  |  | 225 |  | Policy Migration Analysis | Lab validation before production deployment with rollback procedures
Planning | SD-WAN Design | Design branch SD-WAN architecture with application-based routing | EO Engineer | 32 |  |  | 200 |  | SRX Security Architecture Design | 10 branch sites with SRX300 and centralized Security Director management
Planning | Implementation Planning | Develop detailed cutover strategy and timeline with risk mitigation | EO Engineer | 24 |  |  | 150 |  | Policy Migration Strategy | Deliverable: Zero-downtime parallel deployment approach with maintenance windows
Development | Lab Environment Setup | Build lab validation environment for SRX testing and policy validation | EO Engineer | 32 |  |  | 180 |  | Implementation Planning | Replicate production network zones for accurate firewall testing
Development | Datacenter SRX4600 Deployment | Deploy and configure SRX4600 HA pair with base networking and routing | EO Engineer | 64 |  |  | 200 |  | Lab Environment Setup | Active/passive HA with sub-second failover and chassis cluster configuration
Development | Security Policy Implementation | Migrate and implement 500+ firewall rules with optimization | EO Engineer | 72 |  |  | 200 |  | Datacenter SRX4600 Deployment | Zone-based policies with application control ALG and logging
Development | Advanced Security Services | Configure IPS ATP Cloud SecIntel and SSL inspection | EO Engineer | 48 |  |  | 225 |  | Security Policy Implementation | 40 Gbps IPS 20 Gbps SSL inspection with threat intelligence feeds
Development | Branch SRX300 Deployment | Deploy and configure 10 branch SRX300 firewalls with SD-WAN | EO Engineer | 80 |  |  | 200 |  | Advanced Security Services | Standardized security policies and SD-WAN routing across all branch locations
Development | VPN Configuration | Configure 30 site-to-site IPsec VPN and 100 SSL VPN for remote users | EO Engineer | 40 |  |  | 200 |  | Branch SRX300 Deployment | AWS Azure GCP cloud VPN tunnels and branch-to-datacenter connectivity
Development | Security Director Setup | Deploy and configure Junos Space Security Director for centralized management | EO Engineer | 32 |  |  | 200 |  | VPN Configuration | Centralized policy management visibility and compliance reporting for all SRX devices
Development | SIEM Integration | Integrate SRX with Splunk SIEM for security event correlation and alerting | EO Engineer | 24 |  |  | 200 |  | Security Director Setup | Syslog forwarding for threat logs traffic logs and NetFlow integration
Testing | Lab Validation Testing | Test policy migration HA failover and performance in lab environment | EO Engineer | 40 |  |  | 200 |  | SIEM Integration | Validate all security policies before production deployment
Testing | Performance Testing | Conduct throughput testing with 80 Gbps firewall and 40 Gbps IPS | EO Engineer | 24 |  |  | 200 |  | Lab Validation Testing | Validate performance with all security services enabled under load
Testing | HA Failover Testing | Test active/passive failover and traffic recovery | EO Engineer | 16 |  |  | 200 |  | Performance Testing | Sub-second failover with zero packet loss validation
Testing | Security Validation | Validate IPS ATP and SSL inspection threat detection | EO Engineer | 24 |  |  | 225 |  | HA Failover Testing | Test malware detection command and control blocking and threat prevention
Testing | User Acceptance Testing | Coordinate UAT with network and security teams for production readiness | EO Engineer | 32 |  |  | 150 |  | Security Validation | Validate all security zones VPN tunnels and SD-WAN functionality
Deployment | Datacenter Production Cutover | Migrate datacenter traffic zone-by-zone to SRX4600 with rollback capability | EO Engineer | 48 |  |  | 225 |  | User Acceptance Testing | Parallel deployment during maintenance windows with incremental cutover
Deployment | Branch Production Deployment | Deploy and cutover production traffic at 10 branch locations | EO Engineer | 40 |  |  | 200 |  | Datacenter Production Cutover | Pilot site deployment first then standardized rollout to remaining branches
Deployment | Go-Live Support | Provide 24x7 support during production cutover and stabilization | EO Engineer | 80 |  |  | 200 |  | Branch Production Deployment | First 2 weeks post-deployment with on-call support and rapid issue resolution
Training | SRX Administrator Training | Train firewall administrators on SRX management Junos OS and troubleshooting | EO Engineer | 16 |  |  | 200 |  | Datacenter Production Cutover | 2-day hands-on training for up to 8 network and security administrators
Training | Security Operations Training | Train SOC team on policy management threat investigation and Security Director | EO Engineer | 8 |  |  | 200 |  | SRX Administrator Training | 1-day training for security operations and monitoring teams
Training | Documentation Development | Create as-built diagrams runbooks and operational procedures | EO Engineer | 40 |  |  | 150 |  | Security Operations Training | Deliverable: Architecture diagrams configuration guides and troubleshooting runbooks
Closeout | Knowledge Transfer | Transfer solution ownership to client operations and security teams | EO Engineer | 16 |  |  | 200 |  | Documentation Development | Comprehensive handover including operational procedures escalation paths and maintenance
Closeout | Performance Baseline | Establish performance baselines security metrics and monitoring SLAs | EO Engineer | 8 |  |  | 150 |  | Knowledge Transfer | Throughput metrics security events blocked threats and uptime monitoring
Management | Technical Leadership | Security architecture oversight and technical review throughout project | EO Quarterback |  |  |  | 225 |  |  | 25% of engineering effort for architecture guidance and technical escalation
Management | Project Management | Project coordination stakeholder management and timeline oversight | EO Project Manager |  |  |  | 150 |  |  | 20% of engineering effort for project delivery and stakeholder coordination
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase-based multipliers in Estimate Settings based on firewall deployment scope

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
Juniper Partner Services Credit | -12000 | Juniper Partner Network credit for security architecture and SRX deployment services
Implementation Discount | 0 | No implementation discount applicable
TOTAL