## Cover
[VENDOR LOGO]
Level Of Effort Estimate
Presales Document
Generated: | November 16, 2025
Solution: | Document Intelligence
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Document Types | 3 document types (invoices receipts forms) | 2-3 document types | 4-6 document types | 8+ document types or complex variations | Standard document types for IDP
Solution Scope | AI/ML Complexity | Azure Document Intelligence pre-built | Azure Document Intelligence only | Custom classification models | Advanced custom models + NLP | Pre-built vs custom model development
Integration | External System Integrations | 2 REST APIs (CRM ERP) | 2 REST APIs | 4-6 systems | 8+ systems or complex protocols | Standard REST/API integrations for document flow
Integration | Data Sources | Blob Storage and SharePoint | 2-3 data sources | 4-6 data sources | 8+ data sources or complex formats | Document input channels and storage
User Base | Total Users | 75 users | 50 users | 100-250 users | 500+ users | Users submitting and reviewing documents
User Base | User Roles | 3 roles (submitter reviewer admin) | 2-3 standard roles | 4-6 roles | 8+ roles with complex permissions | Document processors reviewers administrators
Data Volume | Document Processing Volume | 2000 docs/month | 1000-5000 docs/month | 10000-50000 docs/month | 100000+ docs/month | Monthly document processing volume
Data Volume | Data Storage Requirements | 250 GB | 500 GB | 2 TB | 10+ TB | Document storage and retention
Technical Environment | Deployment Regions | Single Azure region (East US) | Single Azure region | 2-3 regions | Global multi-region | Geographic distribution for IDP
Technical Environment | Availability Requirements | Standard (99.5%) | Standard (99.5%) | High availability (99.9%) | Mission critical (99.95%+) | SLA for document processing
Technical Environment | Infrastructure Complexity | Serverless (Functions Blob Doc Intel) | Basic serverless | Multi-tier standard | Complex distributed with custom ML | Azure Functions Blob Storage Document Intelligence architecture
Security & Compliance | Security Requirements | RBAC encryption at rest/transit | Basic encryption RBAC | Industry standard (SOC2 HIPAA) | Advanced (FedRAMP multi-jurisdiction) | Document security and access controls
Security & Compliance | Compliance Frameworks | SOC2 | 1-2 basic standards | 2-3 industry standards | Multiple complex frameworks | Regulatory compliance for documents
Performance | Accuracy Requirements | 95%+ extraction accuracy | 95%+ standard | 98%+ enhanced | 99%+ with human review | Data extraction accuracy targets
Performance | Processing Speed | Batch processing | Standard batch processing | Near real-time processing | Real-time with sub-second response | Document processing speed requirements
Environment | Deployment Environments | 2 environments (dev prod) | 2 environments (dev prod) | 3 environments (dev staging prod) | 4+ environments with ML pipelines | Environment management for IDP

## Estimate Settings
INSTRUCTIONS: How to Use Estimate Settings
This sheet contains phase-based multiplier variables that control effort scaling for each project phase.
The EO Sales Engineer updates these multipliers based on customer scope compared to baseline assumptions.
How It Works:
1. Review customer requirements from Discovery Questionnaire
2. Compare customer scope to Baseline Assumptions (see 'Scope Assumptions' sheet)
3. Update YELLOW HIGHLIGHTED multiplier values below (Column C) for each phase
4. All tasks in that phase on the 'LOE' sheet automatically update their Actual Hours
5. Total cost recalculates automatically
Multiplier Guidelines:
• 1.0 = Matches baseline exactly (Small scope)
• 1.5-2.0 = Medium scope (moderately above baseline)
• 2.0-3.0 = Large scope (significantly above baseline)
• 3.0+ = Very large/complex (substantially above baseline, document rationale)
Example: Customer needs comprehensive testing due to compliance → Set TESTING_MX to 2.0
Example: Complex architecture requiring more technical oversight → Set LEADERSHIP_MX to 1.5
ESTIMATE SETTINGS - Update phase multipliers in Column C below:
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Requirements Gathering, Document Analysis, Azure Assessment, Compliance Review)
Planning | PLANNING_MX | 1 | All Planning phase tasks (IDP Solution Design, Data Flow Design, Security Architecture, Project Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Azure Infrastructure, Document Pipeline, AI/ML Integration, Custom Models, API Development)
Testing | TESTING_MX | 1 | All Testing phase tasks (Unit Testing, Document Testing, Performance Testing, Accuracy Testing, Security Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, Model Deployment, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, Business User Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline)
Management | MANAGEMENT_MX | 1.5 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours

## LOE
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Requirements Gathering | Conduct stakeholder interviews for IDP requirements | EO Engineer | 32 |  |  | 150 |  |  | Includes requirements documentation and document processing workflow analysis
Discovery | Document Analysis | Analyze document types volumes and data extraction requirements | EO Engineer | 24 |  |  | 200 |  |  | Customer must provide representative document samples for each document type
Discovery | Azure Environment Assessment | Evaluate Azure infrastructure and AI/ML services readiness | EO Engineer | 24 |  |  | 200 |  |  | Customer must provide Azure subscription access and service limits information
Discovery | Compliance Review | Assess data privacy compliance and security requirements | EO Engineer | 16 |  |  | 175 |  |  | Identifies PII/PHI handling requirements and document retention policies
Planning | IDP Solution Design | Design Azure AI/ML architecture with Document Intelligence and Cognitive Services | EO Engineer | 40 |  |  | 200 |  | Requirements Gathering | Deliverable: Azure architecture diagram with AI/ML service integration design
Planning | Data Flow Design | Design document ingestion processing and output workflows | EO Engineer | 24 |  |  | 180 |  | Document Analysis | Deliverable: Document processing workflow and data flow diagrams
Planning | Security Architecture | Design security controls encryption and access for documents | EO Engineer | 24 |  |  | 175 |  | Compliance Review | Document encryption at rest/transit RBAC roles and audit logging design
Planning | Project Planning | Develop implementation timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  | IDP Solution Design | Deliverable: Project plan with phased rollout and milestone schedule
Development | Azure Infrastructure Setup | Provision Document Intelligence Cognitive Services Blob Storage and Functions | EO Engineer | 40 |  |  | 160 |  | IDP Solution Design | Includes Blob Storage containers Functions Logic Apps and Monitor setup
Development | Document Processing Pipeline | Build document ingestion and processing workflows | EO Engineer | 64 |  |  | 130 |  | Azure Infrastructure Setup | Serverless event-driven pipeline with error handling and retry logic
Development | AI/ML Model Integration | Integrate Azure Document Intelligence and Text Analytics services | EO Engineer | 48 |  |  | 170 |  | Document Processing Pipeline | Configure Document Intelligence APIs Text Analytics entity recognition workflows
Development | Custom Classification Models | Develop minimal classification logic for 2-3 document types | EO Engineer | 24 |  |  | 165 |  | AI/ML Model Integration | Simple classification using Azure pre-built services - not full custom ML models
Development | Data Extraction Logic | Build structured data extraction and validation logic | EO Engineer | 32 |  |  | 130 |  | Custom Classification Models | Includes field validation business rules and confidence scoring
Development | API Development | Create REST APIs for document submission and retrieval | EO Engineer | 24 |  |  | 125 |  | Data Extraction Logic | API Management endpoints with authentication and rate limiting
Development | Web Interface | Build document upload and results viewing interface | EO Engineer | 32 |  |  | 125 |  | API Development | Simple upload UI with drag-drop and results dashboard - not full application
Testing | Unit Testing | Develop automated tests for all processing components | EO Engineer | 32 |  |  | 120 |  | Data Extraction Logic | Automated test suite for Functions and API endpoints
Testing | Document Processing Testing | Test various document types formats and qualities | EO Engineer | 32 |  |  | 120 |  | Web Interface | Customer must provide comprehensive test document library with variations
Testing | Performance Testing | Test system performance with high document volumes | EO Engineer | 24 |  |  | 140 |  | Document Processing Testing | Load testing with realistic document volumes and concurrent processing
Testing | Accuracy Testing | Validate AI/ML model accuracy and data extraction quality | EO Engineer | 24 |  |  | 170 |  | Performance Testing | Statistical validation of extraction accuracy against labeled test dataset
Testing | Security Testing | Perform security testing on document handling pipeline | EO Engineer | 16 |  |  | 175 |  | Accuracy Testing | Includes RBAC policy validation encryption testing and audit log verification
Deployment | Production Deployment | Deploy IDP solution to production Azure environment | EO Engineer | 24 |  |  | 160 |  | Security Testing | Blue-green deployment with rollback procedures and smoke testing
Deployment | Model Deployment | Deploy trained ML models to production endpoints | EO Engineer | 16 |  |  | 170 |  | Production Deployment | Deploy classification logic and configure production Document Intelligence
Deployment | Go-Live Support | Provide support during initial production rollout | EO Engineer | 40 |  |  | 110 |  | Model Deployment | Daily monitoring rapid issue response and accuracy validation during hypercare
Training | Administrator Training | Train system administrators on IDP solution management | EO Engineer | 16 |  |  | 130 |  | Production Deployment | Includes Azure service management Monitor and troubleshooting
Training | Business User Training | Train users on document submission and results review | EO Engineer | 16 |  |  | 120 |  | Administrator Training | Role-based training for document processors and quality reviewers
Training | Documentation | Create user guides technical documentation and runbooks | EO Engineer | 24 |  |  | 110 |  | Business User Training | Deliverable: Operations runbook user guides and troubleshooting procedures
Closeout | Knowledge Transfer | Transfer solution ownership to client operations team | EO Engineer | 16 |  |  | 140 |  | Documentation | Comprehensive handover including Azure architecture model details and procedures
Closeout | Performance Baseline | Establish performance metrics and monitoring baselines | EO Engineer | 8 |  |  | 130 |  | Knowledge Transfer | Establishes accuracy SLAs processing time metrics and cost monitoring
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  |  | 200 |  |  | Azure AI/ML architecture review and technical escalation support
Management | Project Management | Project coordination planning and management activities | EO Project Manager |  |  |  | 150 |  |  | Includes weekly status reporting risk management and stakeholder coordination
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase-based multipliers in Estimate Settings based on customer document processing scope