## Cover
[VENDOR LOGO]
Level Of Effort Estimate
Presales Document
Generated: | November 16, 2025
Solution: | Enterprise Landing Zone
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Management Groups | 3-tier hierarchy | 3-tier hierarchy | 4-5 tier hierarchy | 6+ tier complex hierarchy | Azure management group structure
Solution Scope | Subscriptions | 5-10 subscriptions | 5-10 subscriptions | 10-25 subscriptions | 25+ subscriptions | Subscription organization model
Integration | Hybrid Connectivity | ExpressRoute circuit | VPN only | ExpressRoute | ExpressRoute + VPN redundancy | On-premises to Azure connectivity
Integration | Identity Federation | Azure AD Connect sync | Basic AD sync | AD Connect with PTA | AD FS federation | Identity synchronization method
User Base | Total Users | 500 Azure users | 100-500 users | 500-2000 users | 2000+ users | Users with Azure access
User Base | User Roles | 10 custom RBAC roles | 5-10 roles | 10-20 roles | 20+ roles with PIM | Role-based access control
Data Volume | Workloads to Onboard | 20-30 applications | 10-30 apps | 30-50 apps | 50+ applications | Applications deploying to landing zone
Data Volume | Policy Assignments | 50 policy assignments | 25-50 policies | 50-100 policies | 100+ policies | Azure Policy governance
Technical Environment | Target Azure Regions | 2 regions (East US West US) | Single region | 2-3 regions | 4+ global regions | Azure region deployment
Technical Environment | Availability Requirements | Standard (99.9%) | Standard (99.5%) | High availability (99.9%) | Mission critical (99.95%+) | Platform availability SLA
Technical Environment | Infrastructure Complexity | Hub-spoke network topology | Basic hub-spoke | Advanced hub-spoke with FW | Multi-hub global mesh | Network architecture complexity
Security & Compliance | Security Requirements | Azure Defender Standard | Basic security center | Azure Defender Standard | Defender for Cloud advanced | Cloud security posture management
Security & Compliance | Compliance Frameworks | SOC2 ISO27001 | 1-2 basic standards | 2-3 industry standards | Multiple complex frameworks | Regulatory compliance requirements
Performance | Cost Management | Azure Cost Management | Basic budgets | Cost Management + optimization | FinOps practice | Cloud cost governance
Performance | Governance Automation | Policy-driven governance | Manual governance | Policy automation | GitOps policy management | Governance automation level
Environment | Deployment Environments | Landing zones for dev staging prod | 2 landing zones | 3-4 landing zones | 5+ specialized landing zones | Landing zone segregation

## Estimate Settings
INSTRUCTIONS: How to Use Estimate Settings
This sheet contains phase-based multiplier variables that control effort scaling for each project phase.
The EO Sales Engineer updates these multipliers based on customer scope compared to baseline assumptions.
How It Works:
1. Review customer requirements from Discovery Questionnaire
2. Compare customer scope to Baseline Assumptions (see 'Scope Assumptions' sheet)
3. Update YELLOW HIGHLIGHTED multiplier values below (Column C) for each phase
4. All tasks in that phase on the 'LOE' sheet automatically update their Actual Hours
5. Total cost recalculates automatically
Multiplier Guidelines:
• 1.0 = Matches baseline exactly (Small scope)
• 1.5-2.0 = Medium scope (moderately above baseline)
• 2.0-3.0 = Large scope (significantly above baseline)
• 3.0+ = Very large/complex (substantially above baseline, document rationale)
Example: Customer needs comprehensive testing due to compliance → Set TESTING_MX to 2.0
Example: Complex architecture requiring more technical oversight → Set LEADERSHIP_MX to 1.5
ESTIMATE SETTINGS - Update phase multipliers in Column C below:
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Requirements Gathering, Environment Assessment, Azure Services Assessment, Compliance Review)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Landing Zone Design, Identity Design, Network Architecture, Project Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Management Groups, Policy Implementation, Network Infrastructure, Identity Implementation, Monitoring)
Testing | TESTING_MX | 1 | All Testing phase tasks (Unit Testing, Integration Testing, Performance Testing, Security Testing, UAT)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, End User Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline)
Management | MANAGEMENT_MX | 1.5 | Project Management overhead - 20% of actual engineering hours
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead - 25% of actual engineering hours

## LOE
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Azure Requirements Gathering | Conduct stakeholder interviews for Azure cloud strategy | EO Engineer | 40 |  |  | 150 |  |  | Focus on governance scalability and business alignment
Discovery | Current Environment Assessment | Analyze existing infrastructure and Azure readiness | EO Engineer | 32 |  |  | 200 |  |  | Include identity networking and application assessment
Discovery | Azure Services Assessment | Evaluate Azure services and landing zone requirements | EO Engineer | 24 |  |  | 200 |  |  | Focus on management groups policies and compliance
Discovery | Compliance Review | Assess governance security and regulatory requirements | EO Engineer | 16 |  |  | 175 |  |  | Include Azure Policy and compliance frameworks
Planning | Azure Landing Zone Design | Design Azure landing zone architecture and governance model | EO Engineer | 48 |  |  | 200 |  | Requirements Gathering | Include management groups policies and blueprints
Planning | Identity and Access Design | Design Azure AD integration and access management strategy | EO Engineer | 32 |  |  | 180 |  | Environment Assessment | Include SSO RBAC conditional access and PIM
Planning | Network Architecture Design | Design Azure networking security and hybrid connectivity | EO Engineer | 24 |  |  | 175 |  | Azure Services Assessment | Include hub-spoke VNet peering and security
Planning | Project Planning | Develop Azure implementation timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  | Landing Zone Design | Coordinate with infrastructure security and compliance teams
Development | Management Groups and Subscriptions | Configure Azure management groups subscription structure and policies | EO Engineer | 40 |  |  | 160 |  | Landing Zone Design | Include policy inheritance governance and billing
Development | Azure Policy Implementation | Implement Azure policies governance controls and compliance | EO Engineer | 60 |  |  | 145 |  | Management Groups | Include policy definitions initiatives and remediation
Development | Network Infrastructure | Build Azure networking VNet peering and hybrid connectivity | EO Engineer | 48 |  |  | 140 |  | Network Architecture | Include ExpressRoute VPN and network security
Development | Identity and Access Implementation | Implement Azure AD integration access controls and SSO | EO Engineer | 40 |  |  | 155 |  | Identity Design | Include MFA conditional access and privileged access
Development | Monitoring and Operations | Build Azure monitoring logging alerting and operational tools | EO Engineer | 32 |  |  | 130 |  | Policy Implementation | Include Azure Monitor Log Analytics and automation
Testing | Unit Testing | Develop automated tests for all solution components | EO Engineer | 32 |  |  | 120 |  | Policy Implementation | Include technology-specific testing frameworks
Testing | Integration Testing | Test system integrations data flows and external dependencies | EO Engineer | 40 |  |  | 120 |  | Monitoring Setup | Include end-to-end workflow validation
Testing | Performance Testing | Conduct load performance and scalability testing | EO Engineer | 24 |  |  | 140 |  | Integration Testing | Include production-like environment and stress testing
Testing | Security Testing | Perform security assessments penetration testing and compliance validation | EO Engineer | 16 |  |  | 175 |  | Performance Testing | Include vulnerability scanning and compliance checks
Testing | User Acceptance Testing | Coordinate UAT with business users and stakeholders | EO Engineer | 32 |  |  | 150 |  | Security Testing | Include training feedback collection and sign-off
Deployment | Production Deployment | Deploy landing zone to production environment | EO Engineer | 24 |  |  | 160 |  | UAT | Include blue-green deployment rollback and validation
Deployment | Go-Live Support | Provide comprehensive support during initial production rollout | EO Engineer | 48 |  |  | 110 |  | Production Deployment | Include 24/7 support monitoring and issue resolution
Training | Administrator Training | Train system administrators and technical support teams | EO Engineer | 16 |  |  | 130 |  | Production Deployment | Include hands-on technical training and certification
Training | End User Training | Train business users on solution functionality and workflows | EO Engineer | 24 |  |  | 120 |  | Administrator Training | Include role-based training documentation and support
Training | Documentation | Create comprehensive technical and user documentation | EO Engineer | 32 |  |  | 110 |  | End User Training | Include runbooks troubleshooting guides and best practices
Closeout | Knowledge Transfer | Transfer solution ownership to operations and support teams | EO Engineer | 16 |  |  | 140 |  | Documentation | Include operational procedures escalation and maintenance
Closeout | Performance Baseline | Establish performance metrics monitoring baselines and SLAs | EO Engineer | 8 |  |  | 130 |  | Knowledge Transfer | Include KPI definition monitoring setup and reporting
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  |  | 200 |  |  | Azure architecture review and technical escalation support
Management | Project Management | Project coordination planning and management activities | EO Project Manager |  |  |  | 150 |  |  | Includes weekly status reporting risk management and stakeholder coordination
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase-based multipliers in Estimate Settings based on customer landing zone scope