## Cover
[VENDOR LOGO]
Level Of Effort Estimate
Presales Document
Generated: | November 16, 2025
Solution: | Virtual Wan Global
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Virtual WAN Hubs | 3 regional hubs | 3 regional hubs | Enhanced virtual wan hubs | Enterprise-scale virtual wan hubs | Sizing parameter for Virtual WAN Hubs
Solution Scope | Connected Sites | 10-15 branch locations | 10-15 branch locations | Enhanced connected sites | Enterprise-scale connected sites | Sizing parameter for Connected Sites
Integration | VPN Connections | Site-to-site IPsec VPN | Site-to-site IPsec VPN | Enhanced vpn connections | Enterprise-scale vpn connections | Sizing parameter for VPN Connections
Integration | ExpressRoute Circuits | 2 circuits (primary backup) | 2 circuits (primary backup) | Enhanced expressroute circuits | Enterprise-scale expressroute circuits | Sizing parameter for ExpressRoute Circuits
User Base | Total Users | 1000 users across sites | 1000 users across sites | Enhanced total users | Enterprise-scale total users | Sizing parameter for Total Users
User Base | User Roles | 3 roles (network ops security admin) | 3 roles (network ops security admin) | Enhanced user roles | Enterprise-scale user roles | Sizing parameter for User Roles
Data Volume | Bandwidth Requirements | 1 Gbps aggregate | 1 Gbps aggregate | Enhanced bandwidth requirements | Enterprise-scale bandwidth requirements | Sizing parameter for Bandwidth Requirements
Data Volume | Traffic Volume | 10 TB/month | 10 TB/month | Enhanced traffic volume | Enterprise-scale traffic volume | Sizing parameter for Traffic Volume
Technical Environment | Deployment Regions | 3 Azure regions globally | 3 Azure regions globally | Enhanced deployment regions | Enterprise-scale deployment regions | Sizing parameter for Deployment Regions
Technical Environment | Availability Requirements | High availability (99.95%) | High availability (99.95%) | Enhanced availability requirements | Enterprise-scale availability requirements | Sizing parameter for Availability Requirements
Technical Environment | Infrastructure Complexity | vWAN + Azure Firewall + routing | vWAN + Azure Firewall + routing | Enhanced infrastructure complexity | Enterprise-scale infrastructure complexity | Sizing parameter for Infrastructure Complexity
Security & Compliance | Security Requirements | Azure Firewall DDoS protection | Azure Firewall DDoS protection | Enhanced security requirements | Enterprise-scale security requirements | Sizing parameter for Security Requirements
Security & Compliance | Compliance Frameworks | SOC2 ISO27001 | SOC2 ISO27001 | Enhanced compliance frameworks | Enterprise-scale compliance frameworks | Sizing parameter for Compliance Frameworks
Performance | Latency Requirements | <50ms inter-region | <50ms inter-region | Enhanced latency requirements | Enterprise-scale latency requirements | Sizing parameter for Latency Requirements
Performance | Routing Complexity | BGP route propagation | BGP route propagation | Enhanced routing complexity | Enterprise-scale routing complexity | Sizing parameter for Routing Complexity
Environment | Deployment Environments | 2 environments (non-prod prod) | 2 environments (non-prod prod) | Enhanced deployment environments | Enterprise-scale deployment environments | Sizing parameter for Deployment Environments

## Estimate Settings
INSTRUCTIONS: How to Use Estimate Settings
This sheet contains phase-based multiplier variables that control effort scaling for each project phase.
The EO Sales Engineer updates these multipliers based on customer scope compared to baseline assumptions.
How It Works:
1. Review customer requirements from Discovery Questionnaire
2. Compare customer scope to Baseline Assumptions (see 'Scope Assumptions' sheet)
3. Update YELLOW HIGHLIGHTED multiplier values below (Column C) for each phase
4. All tasks in that phase on the 'LOE' sheet automatically update their Actual Hours
5. Total cost recalculates automatically
Multiplier Guidelines:
• 1.0 = Matches baseline exactly (Small scope)
• 1.5-2.0 = Medium scope (moderately above baseline)
• 2.0-3.0 = Large scope (significantly above baseline)
• 3.0+ = Very large/complex (substantially above baseline, document rationale)
Example: Customer needs comprehensive testing due to compliance → Set TESTING_MX to 2.0
Example: Complex architecture requiring more technical oversight → Set LEADERSHIP_MX to 1.5
ESTIMATE SETTINGS - Update phase multipliers in Column C below:
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks
Planning | PLANNING_MX | 1 | All Planning phase tasks
Development | DEVELOPMENT_MX | 1 | All Development phase tasks
Testing | TESTING_MX | 1 | All Testing phase tasks
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks
Training | TRAINING_MX | 1 | All Training phase tasks
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks
Management | MANAGEMENT_MX | 1.5 | Project Management overhead
Leadership | LEADERSHIP_MX | 1.5 | Technical Leadership overhead

## LOE
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Azure Requirements Gathering | Conduct stakeholder interviews for Azure cloud strategy | EO Engineer | 40 |  |  | 150 |  | $# | ##0"") | $#
Discovery | Current Environment Assessment | Analyze existing infrastructure and Azure readiness | EO Engineer | 32 |  |  | 200 |  | $# | ##0"") | $#
Discovery | Azure Services Assessment | Evaluate Azure services and landing zone requirements | EO Engineer | 24 |  |  | 200 |  | $# | ##0"") | $#
Discovery | Compliance Review | Assess governance security and regulatory requirements | EO Engineer | 16 |  |  | 175 |  | $# | ##0"") | $#
Planning | Azure Landing Zone Design | Design Azure landing zone architecture and governance model | EO Engineer | 48 |  |  | 200 |  | $# | ##0"") | $#
Planning | Identity and Access Design | Design Azure AD integration and access management strategy | EO Engineer | 32 |  |  | 180 |  | $# | ##0"") | $#
Planning | Network Architecture Design | Design Azure networking security and hybrid connectivity | EO Engineer | 24 |  |  | 175 |  | $# | ##0"") | $#
Planning | Project Planning | Develop Azure implementation timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  | $# | ##0"") | $#
Development | Management Groups and Subscriptions | Configure Azure management groups subscription structure and policies | EO Engineer | 40 |  |  | 160 |  | $# | ##0"") | $#
Development | Azure Policy Implementation | Implement Azure policies governance controls and compliance | EO Engineer | 60 |  |  | 145 |  | $# | ##0"") | $#
Development | Network Infrastructure | Build Azure networking VNet peering and hybrid connectivity | EO Engineer | 48 |  |  | 140 |  | $# | ##0"") | $#
Development | Identity and Access Implementation | Implement Azure AD integration access controls and SSO | EO Engineer | 40 |  |  | 155 |  | $# | ##0"") | $#
Development | Monitoring and Operations | Build Azure monitoring logging alerting and operational tools | EO Engineer | 32 |  |  | 130 |  | $# | ##0"") | $#
Testing | Unit Testing | Develop automated tests for all solution components | EO Engineer | 32 |  |  | 120 |  | $# | ##0"") | $#
Testing | Integration Testing | Test system integrations data flows and external dependencies | EO Engineer | 40 |  |  | 120 |  | $# | ##0"") | $#
Testing | Performance Testing | Conduct load performance and scalability testing | EO Engineer | 24 |  |  | 140 |  | $# | ##0"") | $#
Testing | Security Testing | Perform security assessments penetration testing and compliance validation | EO Engineer | 16 |  |  | 175 |  | $# | ##0"") | $#
Testing | User Acceptance Testing | Coordinate UAT with business users and stakeholders | EO Engineer | 32 |  |  | 150 |  | $# | ##0"") | $#
Deployment | Production Deployment | Deploy solution to production environment with monitoring | EO Engineer | 24 |  |  | 160 |  | $# | ##0"") | $#
Deployment | Go-Live Support | Provide comprehensive support during initial production rollout | EO Engineer | 48 |  |  | 110 |  | $# | ##0"") | $#
Training | Administrator Training | Train system administrators and technical support teams | EO Engineer | 16 |  |  | 130 |  | $# | ##0"") | $#
Training | End User Training | Train business users on solution functionality and workflows | EO Engineer | 24 |  |  | 120 |  | $# | ##0"") | $#
Training | Documentation | Create comprehensive technical and user documentation | EO Engineer | 32 |  |  | 110 |  | $# | ##0"") | $#
Closeout | Knowledge Transfer | Transfer solution ownership to operations and support teams | EO Engineer | 16 |  |  | 140 |  | $# | ##0"") | $#
Closeout | Performance Baseline | Establish performance metrics monitoring baselines and SLAs | EO Engineer | 8 |  |  | 130 |  | $# | ##0"") | $#
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  | $# | ##0"")
Management | Project Management | Project coordination and management activities | EO Project Manager |  |  | $# | ##0"")
[5 empty] | TOTAL HOURS |  | TOTAL COST |  | $H$33:$H$59) | $# | ##0"") | EO Sales Engineer: Update multipliers based on customer scope