## Cover
Communication Plan
Delivery Document
Generated: | November 03, 2025
Solution: | Sample Solution
Purpose: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Status Report | Executive Sponsors | High-level project status and key decisions | Weekly | Email Report | Project Manager | Email distribution list |  | Project health, milestones, risks, decisions needed | Executive Sponsor and Business Director | Executive | Report delivered on time and decisions made | Active | [DATE] | Executive summary format with dashboard
COMM-002 | Steering Committee | Project Steering Committee | Strategic direction and issue resolution | Bi-weekly | In-Person Meeting | Project Manager | Meeting invitation | 60 minutes | Strategic decisions, major risks, budget, timeline | Executive Sponsor and Department Heads | Strategic | Meeting attendance >80% and decisions documented | Active | [DATE] | Decision-making authority for scope and budget
COMM-003 | Team Standup | Core Project Team | Daily coordination and impediment removal | Daily | Virtual Meeting | Technical Lead | Video conference | 15 minutes | Yesterday's progress, today's plan, blockers | Development Team and QA Lead | Operational | Daily attendance >90% and blockers resolved | Active | [DATE] | Keep focused on impediments and coordination
COMM-004 | Architecture Review | Technical Stakeholders | Technical design review and approval | Weekly | Technical Meeting | Solution Architect | Meeting invitation | 90 minutes | Architecture decisions, technical risks, design changes | Solution Architect and Technical Leads | Technical | Design decisions made and documented | Active | [DATE] | Include architectural decision records (ADRs)
COMM-005 | Risk Review | Risk Management Team | Risk assessment and mitigation planning | Bi-weekly | Risk Meeting | Risk Manager | Meeting invitation | 45 minutes | New risks, mitigation status, risk escalation | Project Manager and Risk Committee | Management | Risk register updated and mitigations on track | Active | [DATE] | Focus on high and critical risks
COMM-006 | User Feedback | Business Users | User requirements validation and feedback | Weekly | Workshop Session | Business Analyst | Workshop invitation | 120 minutes | Requirements review, prototype feedback, acceptance criteria | Business Stakeholders and End Users | Business | User sign-off on requirements and prototypes | Active | [DATE] | Include hands-on demonstrations and feedback
COMM-007 | Sprint Review | Development Team | Sprint progress and demo | Bi-weekly | Demo Meeting | Development Team Lead | Video conference | 60 minutes | Sprint achievements, demo, retrospective feedback | Development Team and Product Owner | Team | Sprint goals achieved and feedback incorporated | Active | [DATE] | Include live demonstration of working features
COMM-008 | Vendor Coordination | External Vendors | Vendor progress and integration coordination | Weekly | Vendor Call | Integration Specialist | Conference call | 45 minutes | Vendor deliverables, integration progress, issues | Vendor Representatives and Technical Lead | Vendor | Vendor commitments met and issues resolved | Active | [DATE] | Track vendor SLAs and deliverables
COMM-009 | Quality Review | Quality Assurance Team | Test progress and quality metrics | Weekly | QA Meeting | QA Lead | Meeting invitation | 45 minutes | Test execution status, defect metrics, quality gates | QA Team and Development Lead | Quality | Quality gates met and defects within tolerance | Active | [DATE] | Include test coverage and defect trend analysis
COMM-010 | Change Control | Change Control Board | Change request review and approval | As Needed | Change Meeting | Change Manager | Meeting invitation | 60 minutes | Change requests, impact assessment, approval decisions | Change Control Board Members | Governance | Change requests processed within SLA | Active | [DATE] | Follow formal change management process
COMM-011 | Training Update | Training Stakeholders | Training progress and readiness | Bi-weekly | Training Call | Training Manager | Conference call | 30 minutes | Training development, delivery schedule, readiness assessment | Training Team and Business Managers | Operational | Training materials ready and delivery on schedule | Active | [DATE] | Include training effectiveness measurements
COMM-012 | Security Review | Security Team | Security compliance and risk assessment | Monthly | Security Meeting | Security Architect | Meeting invitation | 60 minutes | Security assessments, compliance status, vulnerabilities | Security Team and Compliance Officer | Security | Security requirements met and risks mitigated | Active | [DATE] | Include penetration testing and compliance audits
COMM-013 | Infrastructure Update | Infrastructure Team | Infrastructure readiness and performance | Weekly | Infrastructure Call | DevOps Engineer | Conference call | 30 minutes | Environment status, performance metrics, capacity planning | Infrastructure Team and Operations Manager | Technical | Infrastructure ready and performance targets met | Active | [DATE] | Include capacity planning and monitoring metrics
COMM-014 | Business Readiness | Business Stakeholders | Business readiness and change management | Bi-weekly | Business Meeting | Change Manager | Meeting invitation | 45 minutes | Change readiness, training completion, support preparation | Business Managers and End Users | Business | Business readiness criteria met and users prepared | Active | [DATE] | Include user adoption and change readiness metrics
COMM-015 | Go-Live Preparation | Go-Live Team | Go-live planning and readiness validation | Daily (2 weeks before) | Go-Live Meeting | Project Manager | Video conference | 30 minutes | Go-live checklist, readiness validation, contingency planning | All Team Leads and Operations Manager | Critical | Go-live criteria met and contingency plans ready | Planned | [DATE] | Intensive coordination before go-live event
COMM-016 | Post-Implementation | Project Team | Post-implementation review and lessons learned | Monthly (3 months) | Review Meeting | Project Manager | Meeting invitation | 90 minutes | Performance review, lessons learned, optimization opportunities | Core Project Team and Business Stakeholders | Review | Lessons captured and improvement actions identified | Planned | [DATE] | Include benefits realization and user satisfaction
COMM-017 | Issue Escalation | Issue Resolution Team | Critical issue communication and resolution | As Needed | Emergency Call | Issue Owner | Emergency notification | Variable | Issue description, impact assessment, resolution actions | Incident Response Team and Management | Emergency | Issue resolved within SLA and communication timely | Active | [DATE] | Follow incident management procedures
COMM-018 | Stakeholder Briefing | All Stakeholders | General project updates and milestone communication | Monthly | All-Hands Meeting | Project Manager | Town hall meeting | 45 minutes | Project progress, upcoming milestones, recognition | All Project Stakeholders | Informational | Stakeholder engagement and awareness maintained | Active | [DATE] | Include project achievements and team recognition
COMM-019 | Technical Deep Dive | Technical Teams | Technical knowledge sharing and problem solving | As Needed | Technical Session | Technical Lead | Meeting invitation | 90 minutes | Technical challenges, solution design, knowledge transfer | Technical Team Members | Technical | Technical issues resolved and knowledge shared | Active | [DATE] | Include architectural decisions and best practices
COMM-020 | Client Update | External Client | Client project status and milestone updates | Bi-weekly | Client Call | Project Manager | Client meeting | 45 minutes | Progress update, milestone status, next steps | Client Stakeholders and Account Manager | Client | Client satisfaction maintained and expectations managed | Active | [DATE] | Professional client communication with clear next steps