## Cover
Communication Plan
Delivery Document
Generated: | November 09, 2025
Solution: | Intelligent Document Processing
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Executive Status Report | Executive Sponsors | IDP project status and AI/ML model performance | Weekly | Email Report | EO Project Manager | Email distribution list |  | "Model accuracy metrics, processing volumes, key decisions needed" | EO Quarterback and IT Director | Executive | Report delivered on time and strategic decisions made | Active | [DATE] | Include AI/ML performance dashboard and ROI tracking
COMM-002 | IDP Steering Committee | Project Steering Committee | Strategic direction and scope decisions for AI implementation | Bi-weekly | In-Person Meeting | EO Project Manager | Meeting invitation | 60 minutes | "AI/ML strategy, model performance, budget, timeline, scope changes" | EO Quarterback and Department Heads | Strategic | Meeting attendance >80% and critical decisions documented | Active | [DATE] | Decision authority for AI model requirements and budget
COMM-003 | Development Team Standup | Core IDP Development Team | Daily coordination for AI/ML development and integration | Daily | Virtual Meeting | EO Quarterback | Video conference | 15 minutes | "Model training progress, API development status, integration blockers" | Development Team and ML Engineers | Operational | Daily attendance >90% and technical blockers resolved | Active | [DATE] | Focus on AI/ML development coordination and impediments
COMM-004 | AI/ML Architecture Review | Technical and Data Science Teams | AI model architecture and performance optimization | Weekly | Technical Meeting | EO Quarterback | Meeting invitation | 90 minutes | "Model architecture, training data quality, accuracy improvements" | EO Sales Engineer (Solution Architecture) and Data Scientists | Technical | Model decisions documented and performance targets achieved | Active | [DATE] | Include model validation results and training metrics
COMM-005 | Document Processing Risk Review | Risk Management Team | AI accuracy risks and model performance monitoring | Bi-weekly | Risk Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Model drift risks, accuracy degradation, data quality issues" | EO Project Manager and EO Delivery Engineer (Technical Leadership) | Management | Risk register updated and AI-specific mitigations tracked | Active | [DATE] | Focus on AI/ML operational risks and performance monitoring
COMM-006 | Business User Feedback | Document Processing Users | Requirements validation and AI accuracy feedback | Weekly | Workshop Session | EO Sales Engineer | Workshop invitation | 120 minutes | "Document type requirements, extraction accuracy review, workflow feedback" | Business Stakeholders and Document Processors | Business | User sign-off on AI extraction accuracy and workflow design | Active | [DATE] | Include hands-on testing of document processing workflows
COMM-007 | AI Model Sprint Review | AI/ML Development Team | Model training progress and accuracy demonstrations | Bi-weekly | Demo Meeting | EO Quarterback | Video conference | 60 minutes | "Model training results, accuracy metrics, extraction demonstrations" | Data Science Team and Product Owner | Team | Model accuracy goals achieved and feedback incorporated | Active | [DATE] | Live demonstration of document processing and extraction results
COMM-008 | AWS Services Coordination | AWS Technical Teams | AWS AI service optimization and integration coordination | Weekly | Technical Call | EO Engineer | Conference call | 45 minutes | "Textract performance, Comprehend integration, service optimization" | AWS Technical Team and EO Sales Engineer (Solution Architecture) | Technical | AWS service performance targets met and issues resolved | Active | [DATE] | Track Textract/Comprehend SLAs and optimization opportunities
COMM-009 | Document Quality Review | Quality Assurance and Data Science | Document processing quality and model validation | Weekly | QA Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Model accuracy testing, document quality assessment, validation results" | QA Team and Data Scientists | Quality | Quality gates met and model accuracy within tolerance | Active | [DATE] | Include model validation metrics and document quality analysis
COMM-010 | Change Control Board | Change Control Board | AI model changes and system modification approvals | As Needed | Change Meeting | EO Engineer | Meeting invitation | 60 minutes | "Model updates, processing workflow changes, scope modifications" | Change Control Board Members | Governance | Change requests processed within SLA and impact assessed | Active | [DATE] | Include AI model versioning and rollback procedures
COMM-011 | User Training Update | Training and Business Teams | IDP user training progress and readiness assessment | Bi-weekly | Training Call | EO Engineer | Conference call | 30 minutes | "Training material development, user competency, adoption readiness" | Training Team and Business Managers | Operational | Training materials ready and user competency validated | Active | [DATE] | Include hands-on training with actual document processing
COMM-012 | Security and Compliance Review | Security and Compliance Teams | Data protection and AI model security assessment | Monthly | Security Meeting | EO Quarterback | Meeting invitation | 60 minutes | "Data encryption, model security, compliance validation, audit readiness" | Security Team and Compliance Officer | Security | Security requirements met and compliance validated | Active | [DATE] | Include document data protection and AI model security
COMM-013 | AWS Infrastructure Update | Infrastructure and DevOps Teams | AWS infrastructure performance and capacity planning | Weekly | Infrastructure Call | EO Engineer | Conference call | 30 minutes | "AWS service performance, cost optimization, capacity planning" | Infrastructure Team and Cloud Architect | Technical | Infrastructure performance targets met and costs optimized | Active | [DATE] | Include AWS cost monitoring and service utilization metrics
COMM-014 | Business Readiness Assessment | Business Stakeholders | Document processing workflow readiness and change management | Bi-weekly | Business Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Workflow transition readiness, user adoption, process changes" | Business Managers and Document Processors | Business | Business readiness criteria met and users prepared for automation | Active | [DATE] | Include user acceptance of automated document processing
COMM-015 | Go-Live Preparation | Go-Live Coordination Team | Production deployment and AI model go-live readiness | Daily (2 weeks before) | Go-Live Meeting | EO Project Manager | Video conference | 30 minutes | "Model deployment checklist, production readiness, rollback procedures" | All Team Leads and Operations Manager | Critical | Go-live criteria met and AI model deployment ready | Planned | [DATE] | Intensive coordination for AI model production deployment
COMM-016 | Post-Implementation Review | Project and Operations Teams | AI model performance review and optimization opportunities | Monthly (3 months) | Review Meeting | EO Quarterback | Meeting invitation | 90 minutes | "Model accuracy trends, processing efficiency, optimization opportunities" | Core Project Team and Business Stakeholders | Review | Performance improvements identified and optimization roadmap created | Planned | [DATE] | Include model drift analysis and continuous improvement planning
COMM-017 | Critical Issue Escalation | Emergency Response Team | Critical AI system failures and model performance issues | As Needed | Emergency Call | EO Sales Engineer | Emergency notification | Variable | "Model failures, accuracy degradation, system outages, resolution actions" | Incident Response Team and Management | Emergency | Critical issues resolved within SLA and service restored | Active | [DATE] | Include AI model rollback and emergency procedures
COMM-018 | Stakeholder Briefing | All Project Stakeholders | General IDP project updates and AI/ML achievement communication | Monthly | All-Hands Meeting | EO Project Manager | Town hall meeting | 45 minutes | "AI implementation progress, accuracy achievements, user adoption success" | All Project Stakeholders | Informational | Stakeholder engagement maintained and AI success communicated | Active | [DATE] | Include AI/ML achievements and document processing success stories
COMM-019 | Technical Deep Dive | Technical and Data Science Teams | AI/ML technical knowledge sharing and problem-solving | As Needed | Technical Session | EO Quarterback | Meeting invitation | 90 minutes | "Model architecture challenges, training optimization, integration solutions" | Technical Team Members and Data Scientists | Technical | Technical challenges resolved and AI/ML knowledge shared | Active | [DATE] | Include model training best practices and troubleshooting guides
COMM-020 | Client Update Call | External Client | Client IDP progress and AI model performance updates | Bi-weekly | Client Call | EO Project Manager | Client meeting | 45 minutes | "AI implementation progress, accuracy metrics, business value demonstration" | Client Stakeholders and Account Manager | Client | Client satisfaction maintained and AI value proposition communicated | Active | [DATE] | Professional communication with clear AI business value and ROI
COMM-021 | Model Performance Review | Data Science and Operations | AI model accuracy monitoring and retraining planning | Weekly | Performance Meeting | EO Quarterback | Video conference | 45 minutes | "Accuracy trends, model drift detection, retraining requirements" | Data Scientists and Operations Team | Technical | Model performance maintained above thresholds and drift detected early | Active | [DATE] | Include model monitoring dashboards and retraining schedules
COMM-022 | Document Type Review | Business and Technical Teams | New document type requirements and model expansion | Monthly | Requirements Meeting | EO Quarterback | Meeting invitation | 60 minutes | "New document types, extraction requirements, model enhancement needs" | Business SMEs and AI/ML Team | Business | New requirements captured and model expansion roadmap defined | Active | [DATE] | Include document type classification and extraction complexity assessment