## Cover
Roles
Delivery Document
Generated: | November 09, 2025
Solution: | Intelligent Document Processing
Customer Name: | Data table for roles
Version: | 1.0

## Roles
Role Name | Role Category | Reporting Level | Team | Primary Responsibilities | Required Skills | Experience Level | Allocation % | Duration | Key Deliverables | Performance Metrics | Escalation Path | Training Needs | Notes
EO Project Manager | Leadership | Executive | Project Management Office | Overall project coordination and delivery management | PMP certification project management AI/ML project experience | Senior | 100% | Full project | Project plan status reports milestone delivery | On-time delivery budget adherence stakeholder satisfaction | Executive Sponsor | AI/ML project management training | Central coordination role for IDP initiative using EO Framework™ methodology
EO Sales Engineer (Solution Architecture) | Technical Leadership | Senior Management | Data Science | AI/ML solution design and model strategy | Machine learning AWS AI services solution architecture | Expert | 80% | Design and Build phases | AI/ML architecture model strategy performance optimization | Model accuracy solution scalability technical decisions | CTO | Advanced AWS AI services training | Key technical decision maker for AI components using EO Framework™ principles
EO Delivery Engineer (Platform Implementation) | Technical Leadership | Senior Management | Cloud Infrastructure | AWS cloud architecture and service optimization | AWS certifications cloud architecture security design | Expert | 60% | Full project | AWS infrastructure design service optimization cost management | Infrastructure performance cost efficiency security compliance | Technical Director | AWS advanced architect certification | Responsible for AWS best practices implementation following EO Framework™ standards
EO Delivery Engineer (Technical Leadership) | Technical Leadership | Management | Data Science | ML model development and data strategy oversight | PhD/MS in data science Python R TensorFlow | Expert | 100% | Discovery through Testing | Model development accuracy optimization data strategy | Model performance accuracy metrics training efficiency | EO Sales Engineer (Solution Architecture) | Advanced ML model training | Leads all custom model development efforts with EO Framework™ quality standards
EO Engineer (Data Science) | Technical | Senior | Data Science | Custom ML model development and training | Machine learning Python scikit-learn AWS SageMaker | Senior | 100% | Planning through Testing | Trained models model validation accuracy reports | Model accuracy >95% training efficiency | EO Delivery Engineer (Technical Leadership) | AWS SageMaker advanced training | Focus on document classification models using EO Framework™ methodology
EO Delivery Engineer (Infrastructure) | Technical | Senior | Data Science | ML model deployment and MLOps implementation | MLOps Docker Kubernetes model deployment | Senior | 100% | Build through Deployment | Model deployment pipeline model monitoring | Deployment success model performance monitoring | EO Delivery Engineer (Technical Leadership) | MLOps and model deployment training | Responsible for production model deployment using EO Framework™ standards
EO Delivery Engineer (Platform Implementation) | Technical | Senior | Development | Core application development and API implementation | Python/Java REST APIs microservices AWS Lambda | Senior | 100% | Build through Testing | Document processing APIs core application | Code quality API performance error rates | EO Delivery Engineer (Technical Leadership) | AWS Lambda and API Gateway training | Develops core document processing logic following EO Framework™ best practices
EO Engineer (Frontend Development) | Technical | Mid | Development | User interface development and user experience | React/Angular JavaScript responsive design | Mid-level | 80% | Build through Testing | Web application user interface mobile responsiveness | User experience metrics interface performance | EO Delivery Engineer (Platform Implementation) | Modern web development frameworks | Creates document upload and review interfaces with EO Framework™ quality standards
EO Delivery Engineer (Infrastructure) | Technical | Senior | Infrastructure | Infrastructure automation and deployment | AWS CloudFormation Terraform CI/CD Docker | Senior | 70% | Full project | Infrastructure automation deployment pipelines monitoring | Deployment success infrastructure uptime | EO Delivery Engineer (Platform Implementation) | Advanced AWS DevOps training | Manages all infrastructure automation using EO Framework™ standards
EO Delivery Engineer (Platform Implementation) | Technical | Senior | Infrastructure | AWS infrastructure design and optimization | AWS architecture networking security performance | Senior | 60% | Planning through Deployment | Infrastructure design capacity planning cost optimization | Infrastructure performance cost efficiency | EO Delivery Engineer (Infrastructure) | AWS networking and security training | Designs scalable AWS infrastructure following EO Framework™ methodology
EO Engineer (Security) | Technical | Senior | Security | Security design and compliance implementation | Cybersecurity AWS security compliance frameworks | Senior | 50% | Planning through Testing | Security architecture compliance framework penetration testing | Security compliance audit results | CISO | AWS security best practices training | Ensures comprehensive security implementation with EO Framework™ standards
EO Sales Engineer (Business Analysis) | Business | Mid | Business | Requirements gathering and business process design | Business analysis requirements gathering process design | Mid-level | 80% | Discovery through Testing | Requirements specification business process design UAT coordination | Requirements completeness stakeholder satisfaction | EO Project Manager | AI/ML business analysis training | Bridges business needs with technical implementation using EO Framework™ approach
EO Delivery Engineer (Platform Implementation) | Technical | Senior | Development | System integration and API development | API development integration patterns enterprise systems | Senior | 70% | Build through Testing | Integration specifications API integrations system connections | Integration success data flow accuracy | EO Delivery Engineer (Platform Implementation) | Enterprise integration patterns training | Handles all external system integrations following EO Framework™ standards
EO Engineer (QA) | Technical | Mid | Quality Assurance | Testing strategy and quality validation | Test automation quality assurance AI/ML testing | Mid-level | 100% | Build through Deployment | Test plans test execution defect reports | Test coverage defect detection rates | EO Engineer (QA Lead) | AI/ML testing methodologies training | Focuses on model accuracy and system testing using EO Framework™ quality standards
EO Engineer (QA Lead) | Technical | Senior | Quality Assurance | Quality assurance strategy and team coordination | Test management quality processes automation frameworks | Senior | 60% | Build through Deployment | QA strategy test automation framework | Quality metrics defect rates test coverage | EO Project Manager | Advanced test automation training | Oversees all testing activities and quality following EO Framework™ methodology
EO Engineer (Performance) | Technical | Senior | Quality Assurance | Performance testing and optimization | Performance testing load testing AWS performance optimization | Senior | 40% | Testing phase | Performance test results optimization recommendations | Performance benchmarks scalability metrics | EO Engineer (QA Lead) | AWS performance testing training | Ensures system meets performance requirements using EO Framework™ standards
EO Engineer (Security) | Technical | Senior | Security | Security testing and vulnerability assessment | Security testing penetration testing vulnerability assessment | Senior | 30% | Testing phase | Security test results vulnerability assessment remediation plan | Security compliance test results | EO Engineer (Security) | Advanced security testing training | Validates security implementation using EO Framework™ standards
EO Engineer (Documentation) | Support | Mid | Documentation | Technical documentation and user guides | Technical writing documentation tools user experience | Mid-level | 60% | Build through Closure | User guides technical documentation training materials | Documentation quality user feedback | EO Project Manager | AI/ML technical writing training | Creates all user-facing documentation following EO Framework™ standards
EO Engineer (Training) | Support | Mid | Training | User training and knowledge transfer | Training design adult learning change management | Mid-level | 50% | Testing through Closure | Training materials training delivery knowledge transfer | Training effectiveness user competency | EO Sales Engineer (Business Analysis) | AI/ML user training techniques | Develops and delivers user training programs using EO Framework™ methodology
EO Engineer (Change Management) | Support | Senior | Change Management | Change management and user adoption | Change management organizational psychology communication | Senior | 40% | Planning through Closure | Change strategy communication plan adoption metrics | User adoption rates change readiness | EO Project Manager | AI/ML change management training | Manages organizational change and adoption using EO Framework™ approach
EO Sales Engineer (Business Analysis) | Business | Senior | Finance | Domain expertise for financial document processing | Finance domain knowledge document processing workflows | Expert | 30% | Discovery through Testing | Requirements validation workflow design UAT support | Business accuracy requirements validation | EO Sales Engineer (Business Analysis) | AI/ML business applications training | Provides expertise on financial documents using EO Framework™ methodology
EO Sales Engineer (Business Analysis) | Business | Senior | Legal | Domain expertise for legal document processing | Legal domain knowledge contract analysis compliance | Expert | 20% | Discovery through Testing | Legal requirements validation compliance framework | Legal accuracy compliance validation | EO Sales Engineer (Business Analysis) | AI/ML legal applications training | Provides expertise on legal documents using EO Framework™ methodology
EO Engineer (Support) | Operations | Management | Operations | Operational readiness and support planning | Operations management system administration monitoring | Senior | 30% | Deployment through Closure | Operations procedures support model monitoring framework | Operational metrics system availability | EO Project Manager | AI/ML operations management training | Prepares organization for operational handover using EO Framework™ standards
EO Engineer (Support) | Support | Junior | Operations | User support and issue resolution during go-live | Help desk technical support troubleshooting | Junior | 50% | Go-live through Closure | Support procedures issue resolution user assistance | Support ticket resolution user satisfaction | EO Engineer (Support) | IDP system support training | Provides first-level user support following EO Framework™ methodology
EO Engineer (Compliance) | Compliance | Senior | Compliance | Regulatory compliance and audit preparation | Regulatory knowledge compliance frameworks audit preparation | Senior | 20% | Full project | Compliance framework audit preparation regulatory validation | Compliance metrics audit readiness | Legal Counsel | AI/ML compliance requirements training | Ensures regulatory compliance throughout project using EO Framework™ standards
EO Quarterback | Leadership | C-Level | Executive | Strategic oversight and decision authority | Executive leadership strategic planning budget authority | C-Level | 10% | Full project | Strategic decisions budget approvals stakeholder communication | Project ROI strategic alignment | Board of Directors | AI/ML strategic value training | Provides executive leadership and strategic direction aligned with EO Framework™ methodology