## Cover
Training Plan
Delivery Document
Generated: | November 09, 2025
Solution: | Intelligent Document Processing
Customer Name: | Data table for training plan
Version: | 1.0

## Training Plan
Training ID | Training Category | Training Type | Target Audience | Training Title | Learning Objectives | Duration | Delivery Method | Prerequisites | Materials Required | Trainer | Schedule | Maximum Participants | Assessment Method | Certification | Status | Notes
TRN-001 | Technical | Administrator | System Administrators | AWS IDP Administration Fundamentals | Understand IDP architecture AWS services management and basic troubleshooting | 2 days | Instructor-led with hands-on labs | Basic AWS knowledge | AWS console access training materials | EO Delivery Engineer (Platform Implementation) | Week 15 | 8 | Hands-on lab completion | AWS IDP Administrator Certificate | Planned | Focus on operational aspects
TRN-002 | Technical | Administrator | System Administrators | AWS AI Services Management | Learn to manage Textract Comprehend and SageMaker services | 1 day | Virtual instructor-led | TRN-001 completion | AWS console access service documentation | EO Sales Engineer (Solution Architecture) | Week 15 | 8 | Service configuration assessment | AI Services Management Certificate | Planned | Deep dive into AI service administration
TRN-003 | Technical | Developer | Technical Team | IDP API Development and Integration | Learn IDP APIs integration patterns and troubleshooting | 1 day | Hands-on workshop | Programming experience REST API knowledge | Development environment API documentation | EO Delivery Engineer (Platform Implementation) | Week 14 | 6 | Code review and integration test | API Integration Certificate | Planned | Include authentication and error handling
TRN-004 | Technical | Data Science | Data Science Team | ML Model Management and Monitoring | Learn model deployment monitoring and retraining procedures | 1 day | Technical workshop | Machine learning background SageMaker experience | SageMaker access model artifacts | EO Delivery Engineer (Technical Leadership) | Week 14 | 4 | Model deployment exercise | ML Operations Certificate | Planned | Focus on MLOps best practices
TRN-005 | Business | End User | Document Processors | IDP Document Processing Workflow | Learn to submit documents review results and handle exceptions | 4 hours | Instructor-led demonstration |  | Web browser access training documents | EO Sales Engineer (Business Analysis) | Week 16 | 20 | Workflow completion assessment | User Competency Certificate | Planned | Include real document processing scenarios
TRN-006 | Business | End User | Business Users | Document Upload and Results Review | Learn web interface document submission and results validation | 2 hours | Hands-on training | Basic computer skills | Web browser access sample documents | EO Engineer (Training) | Week 16 | 15 | Task completion assessment | Basic User Certificate | Planned | Focus on daily operational tasks
TRN-007 | Business | Power User | Business Analysts | Advanced IDP Features and Reporting | Learn advanced features reporting and analytics capabilities | 3 hours | Interactive workshop | TRN-006 completion | Web interface access reporting tools | EO Sales Engineer (Business Analysis) | Week 16 | 10 | Report generation exercise | Power User Certificate | Planned | Include dashboard and analytics training
TRN-008 | Business | Management | Managers and Supervisors | IDP Management Dashboard and KPIs | Learn to monitor performance metrics and business KPIs | 2 hours | Executive briefing |  | Dashboard access performance reports | EO Project Manager | Week 16 | 12 | KPI interpretation assessment | Management Overview Certificate | Planned | Focus on business value and ROI
TRN-009 | Technical | Support | Support Staff | IDP Troubleshooting and User Support | Learn common issues troubleshooting and user assistance | 4 hours | Problem-solving workshop | Basic technical knowledge | Support documentation troubleshooting guides | EO Delivery Engineer (Technical Leadership) | Week 15 | 8 | Troubleshooting scenario assessment | Support Specialist Certificate | Planned | Include escalation procedures
TRN-010 | Technical | Support | Operations Team | IDP Monitoring and Performance Optimization | Learn system monitoring performance tuning and optimization | 3 hours | Technical workshop | TRN-009 completion | Monitoring tools performance dashboards | DevOps Engineer | Week 15 | 6 | Performance analysis exercise | Operations Certificate | Planned | Include capacity planning
TRN-011 | Security | Compliance | Security Team | IDP Security and Compliance Management | Learn security controls compliance monitoring and audit procedures | 3 hours | Security briefing | Security background | Security documentation compliance frameworks | Security Architect | Week 15 | 5 | Security assessment review | Security Compliance Certificate | Planned | Include GDPR and audit requirements
TRN-012 | Business | Change Management | All Users | IDP Change Management and Adoption | Understand change process benefits and adoption strategies | 1 hour | All-hands presentation |  | Presentation materials change guides | Change Manager | Week 14 | 50 | Participation and feedback | Change Readiness Certificate | Planned | Focus on user adoption and support
TRN-013 | Technical | Advanced | Technical Leads | IDP Architecture Deep Dive | Advanced understanding of IDP architecture and design decisions | 4 hours | Technical deep dive | Senior technical experience | Architecture documentation technical specifications | AI/ML Architect | Week 14 | 8 | Architecture review exercise | Technical Leadership Certificate | Planned | Include future enhancement planning
TRN-014 | Business | Advanced | Business SMEs | Document Type Configuration and Rules | Learn to configure new document types and extraction rules | 3 hours | Configuration workshop | TRN-007 completion domain expertise | Configuration tools document samples | Data Science Lead | Week 16 | 6 | Configuration exercise | SME Configuration Certificate | Planned | Include business rule definition
TRN-015 | Technical | Specialized | ML Engineers | Custom Model Training and Deployment | Learn custom model development training and deployment | 6 hours | Technical workshop | Machine learning expertise Python programming | SageMaker access training data | Data Science Lead | Week 13 | 4 | Model training exercise | Custom Model Certificate | Planned | Advanced ML techniques for document processing
TRN-016 | Operations | Specialized | Operations Managers | IDP Operations and Maintenance | Learn operational procedures maintenance schedules and escalation | 2 hours | Operations briefing | Operations management experience | Operations documentation procedures | Operations Manager | Week 15 | 6 | Operational readiness assessment | Operations Manager Certificate | Planned | Include budget and resource management
TRN-017 | Business | Specialized | Finance Team | Invoice Processing Optimization | Specialized training for finance team on invoice processing workflows | 2 hours | Department-specific training | Finance domain knowledge | Finance-specific documents workflow guides | Finance SME | Week 16 | 8 | Invoice processing assessment | Finance Specialist Certificate | Planned | Include AP integration and validation
TRN-018 | Business | Specialized | Legal Team | Contract Analysis and Legal Document Processing | Specialized training for legal team on contract and legal document processing | 2 hours | Department-specific training | Legal domain knowledge | Legal document samples compliance guides | Legal SME | Week 16 | 5 | Legal document analysis assessment | Legal Specialist Certificate | Planned | Include compliance and risk considerations
TRN-019 | Support | Refresher | All Users | IDP Quarterly Refresher Training | Ongoing training for updates new features and best practices | 1 hour | Virtual session | Previous IDP training | Updated materials new feature guides | Various trainers | Quarterly | 25 | Knowledge check assessment | Refresher Certificate | Ongoing | Scheduled quarterly sessions
TRN-020 | Support | Advanced | Super Users | IDP Super User Training | Advanced training for power users who assist others | 4 hours | Train-the-trainer session | TRN-007 completion leadership skills | Training materials peer support guides | Business Analyst | Week 16 | 10 | Teaching demonstration | Super User Certificate | Planned | Include peer support and mentoring skills
TRN-021 | Technical | Maintenance | Technical Team | IDP System Updates and Maintenance | Learn system update procedures version management and maintenance | 2 hours | Technical maintenance training | System administration experience | Maintenance procedures update guides | DevOps Engineer | Week 15 | 8 | Maintenance procedure assessment | Maintenance Certificate | Planned | Include rollback and recovery procedures
TRN-022 | Compliance | Audit | Compliance Team | IDP Audit and Documentation Requirements | Learn audit trail analysis compliance reporting and documentation | 2 hours | Compliance training | Compliance background audit experience | Audit documentation compliance templates | Compliance Officer | Week 15 | 4 | Audit procedure assessment | Audit Specialist Certificate | Planned | Include regulatory reporting requirements
TRN-023 | Business | Executive | Executive Team | IDP Strategic Value and ROI Realization | Executive overview of IDP value ROI and strategic benefits | 1 hour | Executive briefing | Executive leadership | Executive summary ROI analysis | Project Manager | Week 16 | 8 | Strategic discussion participation | Executive Overview Certificate | Planned | Focus on business value and future opportunities
TRN-024 | Support | Continuous | All Stakeholders | IDP Best Practices and Lessons Learned | Share best practices lessons learned and continuous improvement | 1 hour | Knowledge sharing session | IDP operational experience | Best practices documentation lessons learned | Project Manager | Monthly | 30 | Best practice sharing | Continuous Improvement Certificate | Ongoing | Encourage knowledge sharing and innovation