## Slide 1
Project Closeout
Google Workspace Deployment
Project Manager | November 27, 2025

## Slide 2
Executive Summary
Project Duration: 12 weeks, on schedule
Budget: $105,200 delivered on budget
Go-Live Date: Week 10 as planned
Quality: Zero data loss during migration
User Adoption: 97% daily active users (target 95%)
Mailbox Migration: 500 mailboxes, 2.5 TB migrated
ROI Status: On track for 24-month payback
Google Workspace Deployment
Notes: *Opening Statement:*
Good [morning/afternoon]. Today we're celebrating the successful completion of the Google Workspace deployment. This project has transformed [Client Name]'s productivity infrastructure from aging Exchange servers and file servers to a modern, cloud-native collaboration platform serving 500 users.
*Key Talking Points - Expand on Each Bullet:*
**Project Duration - 12 Weeks:**
- Executed exactly as planned in the Statement of Work
- Phase 1 (Planning & Pilot): Weeks 1-5 - Environment setup, SSO, pilot migration
- Phase 2 (Phased Migration): Weeks 6-10 - 5 waves of 95 users each
- Phase 3 (Training & Adoption): Weeks 8-12 - Training and hypercare
- No schedule slippage despite Exchange coexistence complexity
**Budget - $105,200 Net:**
- Software Licenses: $105,200 (500 users at $18/month after credits)
- Google Workspace Promotional Credits: $10,000 applied
- Partner Migration Credit: $3,000 applied to services
- Actual spend: $105,142 - under budget
**Zero Data Loss:**
- 2.5 TB email migrated with 100% integrity
- 3 TB files transferred with permissions preserved
- All 150 distribution lists converted to Google Groups
- Calendar and contacts fully migrated
**User Adoption - 97%:**
- Target was 95% daily active users within 90 days
- Achieved 97% within 60 days of go-live
- User satisfaction score: 4.6/5 (target 4.5/5)
- Support tickets 40% below projected volume
*Transition to Next Slide:*
"Let me walk you through exactly what we built together..."

## Slide 3
Solution Architecture
Core Workspace Apps
  Gmail with 30 GB per user storage
  Google Drive with 5 TB per user
  Docs, Sheets, Slides, Meet, Chat
Security & Identity
  Azure AD SAML SSO integration
  DLP policies for sensitive content
  Google Vault 7-year retention
Migration Infrastructure
  GWMT for 500 mailbox migration
  File migration to Shared Drives
  150 Google Groups configured
Google Workspace Deployment
Notes: *Architecture Overview - Walk Through the Diagram:*
"This diagram shows the production Google Workspace architecture we deployed. Let me walk through the key components..."
**Core Workspace Applications:**
- Gmail: 500 mailboxes with 30 GB storage each, unified inbox
- Google Drive: 5 TB per user with Shared Drives for team collaboration
- Google Docs/Sheets/Slides: Real-time co-editing replacing email attachments
- Google Meet: Video conferencing up to 500 participants with recording
- Google Chat: Team messaging with Spaces for project collaboration
- Google Calendar: Shared calendars with room booking integration
**Security & Identity Layer:**
- Cloud Identity Premium for user management
- SAML SSO with Azure AD for seamless authentication
- Google Cloud Directory Sync (GCDS) for automated provisioning
- 2-Step Verification enforced for all 500 users
- Data Loss Prevention policies active (PII, financial data)
- Mobile device management for 300+ managed devices
**Compliance & Governance Layer:**
- Google Vault with 7-year retention policy
- Legal hold capabilities for eDiscovery
- Audit logs for all user and admin activity
- External sharing controls with domain allowlist
**Migration Infrastructure:**
- Google Workspace Migration Tool for Exchange migration
- Migration for Drive for file server transfer
- Custom scripts for distribution list conversion
*Transition:*
"Now let me show you the complete deliverables package we're handing over..."

## Slide 4
Deliverables Inventory
Deliverable | Purpose | Location
Migration Assessment Report | Exchange and file server analysis | `/delivery/assessment-report.docx`
Detailed Design Document | Workspace architecture and security design | `/delivery/detailed-design.docx`
Implementation Guide | Step-by-step migration procedures | `/delivery/implementation-guide.docx`
Project Plan | Timeline, milestones, RACI, communications | `/delivery/project-plan.xlsx`
Test Plan & Results | Migration validation and UAT results | `/delivery/test-plan.xlsx`
Configuration Guide | Environment parameters and settings | `/delivery/configuration.xlsx`
Operations Runbook | Day-to-day admin procedures | `/delivery/docs/runbook.md`
Training Materials | User guides and video recordings | `/delivery/training/`
Google Workspace Deployment
Notes: *Deliverables Deep Dive - Review Each Item:*
**1. Migration Assessment Report:**
- Exchange environment analysis (500 mailboxes, 2.5 TB)
- File server inventory (3 TB across 12 shared folders)
- Distribution list mapping (150 groups)
- User readiness assessment results
- Accepted by [IT Lead] on [Date]
**2. Detailed Design Document:**
- Google Workspace tenant configuration
- Azure AD SSO integration architecture
- DLP policy specifications
- Mobile management policy design
- Security baseline configuration
**3. Implementation Guide:**
- Step-by-step migration procedures
- GWMT configuration for Exchange migration
- File migration with permission mapping
- Rollback procedures documented
**4. Project Plan:**
- Four worksheets: Timeline, Milestones, RACI, Communications
- 5-wave migration schedule documented
- All milestones achieved on schedule
**5. Test Plan & Results:**
- Migration validation tests: 100% pass
- SSO authentication testing: Validated
- User acceptance testing: 25 pilot users signed off
**6. Operations Runbook:**
- Daily health check procedures
- User onboarding/offboarding workflows
- Password reset and account recovery
- Troubleshooting decision trees
**7. Training Materials:**
- End-user quick start guides (Gmail, Drive, Docs, Meet)
- Admin training for Google Admin Console
- Video recordings: 10 sessions, 15 hours total
- Change champion enablement materials
*Training Sessions Delivered:*
- End-user sessions: 10 sessions, 450 attendees
- Admin training: 3 sessions, 12 IT staff
- Change champion training: 2 sessions, 25 champions
*Transition:*
"Let's look at how the platform is performing against our targets..."

## Slide 5
Quality & Performance
Migration Metrics
  Mailbox Success Rate: 100% (500/500)
  File Migration: 100% (3 TB transferred)
  Data Integrity: Zero data loss confirmed
  Distribution Lists: 150/150 converted
  Calendar Migration: 100% appointments
Platform Metrics
  User Adoption: 97% DAU (target 95%)
  User Satisfaction: 4.6/5 (target 4.5)
  Support Tickets: 40% below forecast
  Gmail Uptime: 99.99% (SLA 99.9%)
  Meeting Quality: 4.8/5 Meet rating
Google Workspace Deployment
Notes: *Quality & Performance Deep Dive:*
**Migration Metrics - Detailed Breakdown:**
*Mailbox Migration: 100% Success Rate*
- 500 mailboxes migrated over 5 waves
- 2.5 TB total email data transferred
- Average mailbox size: 5 GB
- Largest mailbox: 25 GB (CEO)
- Migration tool: GWMT with delta sync
- Zero mailbox failures
*File Migration: 100% Complete*
- 3 TB migrated from 12 file server shares
- 450,000 files transferred
- Permission mapping: 98% automated, 2% manual review
- Shared Drives created: 15
- Average transfer rate: 150 GB/day
*Distribution Lists: 150 Google Groups*
- All 150 distribution lists converted
- Membership preserved (8,500 total members)
- External senders: Configured per policy
- Moderation: Enabled for 12 groups
**Platform Metrics - Detailed Analysis:**
*User Adoption: 97% Daily Active Users*
- Target: 95% within 90 days
- Achieved: 97% within 60 days
- Measurement: Google Admin Console usage reports
- Active definition: Logged in within 24 hours
- Highest adoption: Sales team (99%)
- Lowest adoption: Finance team (94%)
*User Satisfaction: 4.6/5*
- Survey sent to all 500 users
- 78% response rate (390 responses)
- Gmail: 4.7/5
- Drive: 4.5/5
- Docs: 4.6/5
- Meet: 4.8/5
- Training: 4.4/5
*Support Tickets: 40% Below Forecast*
- Projected: 250 tickets in first 30 days
- Actual: 148 tickets (40% reduction)
- Most common: Password/login (resolved by SSO training)
- Average resolution: 4 hours (target 8 hours)
**Testing Summary:**
- Test Cases Executed: 45 total
- Pass Rate: 100%
- Critical Defects at Go-Live: 0
*Transition:*
"These platform capabilities translate directly into business value..."

## Slide 6
Benefits Realized
Benefit Category | SOW Target | Achieved | Business Impact
User Adoption | 95% in 90 days | 97% in 60 days | Exceeded target by 30 days
Data Migration | Zero data loss | Zero data loss | 100% integrity confirmed
IT Cost Reduction | 40% annually | 42% projected | $125K annual savings
Collaboration | 10x improvement | 15x measured | Real-time co-editing live
Uptime | 99.9% SLA | 99.99% actual | 8x better than Exchange
Mobile Access | 100% workforce | 100% enabled | No VPN required
Google Workspace Deployment
Notes: *Benefits Analysis - Detailed ROI Discussion:*
**User Adoption - 97% in 60 Days:**
*Before (Email-Centric):*
- Average 50 email attachments sent per user per day
- Version control issues causing rework
- File locking on shared drives
- VPN required for remote file access
*After (Collaboration-First):*
- Real-time co-editing in Google Docs
- Shared Drives replacing file server shares
- Native mobile apps without VPN
- Meet replacing phone conferences
*Business Impact:*
- Faster document completion (estimated 2 hours/user/week saved)
- Eliminated version confusion
- Remote workforce fully enabled
**IT Cost Reduction - 42% Projected:**
*Before (On-Premises):*
- Exchange 2016 servers: 2 FTE maintaining
- File servers: $50K annual storage expansion
- Hardware refresh: $180K upcoming
- Backup infrastructure: $25K annually
- Total: ~$300K annual IT costs
*After (Cloud):*
- Google Workspace licenses: $108K/year
- No hardware maintenance
- No backup infrastructure (built-in)
- IT staff redeployed to strategic projects
- Total: ~$175K annual costs (42% reduction)
*Financial Impact:*
- Year 1 savings: $125K
- 3-year savings: $375K+
- Payback period: 20 months (target 24)
**Collaboration - 15x Improvement:**
*Measurement:*
- Simultaneous editors per document: 15 average (vs. 1 with file locking)
- Documents created in Docs: 2,500/month
- Meet meetings: 800/week (up from 200 phone calls)
- Chat messages: 15,000/week
*Transition:*
"We learned valuable lessons during this deployment..."

## Slide 7
Lessons Learned & Recommendations
What Worked Well
  Phased 5-wave migration approach
  Pilot with IT and early adopters
  Just-in-time training per wave
  Change champion network
  Daily migration status calls
Challenges Overcome
  Large mailbox delta sync timing
  File permission edge cases
  External sharing policy tuning
  Mobile device enrollment
  Calendar delegation migration
Recommendations
  Enable Gemini for Workspace AI
  Implement Google Chat adoption
  Add third-party backup solution
  Quarterly security reviews
  Advanced Drive analytics
Google Workspace Deployment
Notes: *Lessons Learned - Comprehensive Review:*
**What Worked Well - Details:**
*1. Phased 5-Wave Migration Approach:*
- 95 users per wave over 5 weeks
- Limited impact to any single department
- Allowed course correction between waves
- Recommendation: Always use phased approach for 100+ users
*2. Pilot with IT and Early Adopters (Week 5):*
- 25 pilot users validated migration tools
- Identified training content gaps
- Built internal champions
- Recommendation: Include tech-savvy users from each department
*3. Just-in-Time Training:*
- Training delivered 1 week before each wave
- Higher retention than advance training
- 92% attendance rate
- Recommendation: Train close to cutover
*4. Change Champion Network:*
- 25 champions across departments
- First-line support for colleagues
- Escalation path to IT
- Recommendation: 1 champion per 20 users
**Challenges Overcome - Details:**
*1. Large Mailbox Delta Sync:*
- Challenge: CEO 25 GB mailbox took 8 hours
- Resolution: Extended maintenance window
- Learning: Pre-migrate large mailboxes
*2. File Permission Edge Cases:*
- Challenge: Nested permissions on 2% of files
- Resolution: Manual permission review
- Learning: Audit permissions before migration
*3. External Sharing Policy:*
- Challenge: Users blocked from legitimate sharing
- Resolution: Domain allowlist implemented
- Learning: Document sharing requirements upfront
**Recommendations for Future Enhancement:**
*1. Enable Gemini for Workspace:*
- AI-powered writing assistance
- Smart meeting summaries
- Email drafting and suggestions
- Estimated productivity gain: 30 min/user/day
*2. Third-Party Backup Solution:*
- Spanning or Backupify recommended
- Independent backup of Gmail and Drive
- Compliance requirement for some industries
- Cost: ~$1.10/user/month
*Transition:*
"Let me walk you through how we're transitioning support..."

## Slide 8
Support Transition
Hypercare Complete (30 days)
  Daily health checks completed
  148 support tickets resolved
  Knowledge transfer sessions done
  Admin Console training complete
  Team certified and self-sufficient
Steady State Support
  Business hours monitoring active
  Monthly adoption reviews
  Quarterly security assessments
  Feature enablement roadmap
  Documentation fully maintained
Escalation Path
  L1: IT Helpdesk (internal)
  L2: Google Workspace Admin Team
  L3: Google Cloud Support
  Emergency: On-call admin rotation
  Account: Customer Success Manager
Google Workspace Deployment
Notes: *Support Transition - Complete Details:*
**Hypercare Period Summary (30 Days Post-Go-Live):**
*Daily Activities Completed:*
- Morning health check calls (9am) - first 2 weeks
- Admin Console reports review
- Support ticket triage
- User adoption monitoring
- Feature question resolution
*Issues Resolved During Hypercare:*
Issue #1 - Day 3:
- Problem: SSO timeout causing re-authentication
- Root cause: Azure AD token lifetime mismatch
- Resolution: Adjusted token settings
- Prevention: Documented in runbook
Issue #2 - Day 8:
- Problem: External sharing blocked for vendor
- Root cause: Domain not in allowlist
- Resolution: Added domain to sharing policy
- Result: External collaboration enabled
*Knowledge Transfer Sessions Delivered:*
| Session | Date | Attendees | Duration | Recording |
|---------|------|-----------|----------|-----------|
| Admin Console Deep Dive | Week 13 | 6 admins | 3 hours | Yes |
| GAM Scripting Basics | Week 14 | 4 admins | 2 hours | Yes |
| Vault and eDiscovery | Week 14 | 3 legal/IT | 2 hours | Yes |
| Security Dashboard | Week 15 | 6 security | 1.5 hours | Yes |
| Troubleshooting Workshop | Week 15 | 8 helpdesk | 2 hours | Yes |
**Steady State Support Model:**
*What Client Team Handles (L1/L2):*
- Password resets and account recovery
- User onboarding and offboarding
- Basic troubleshooting (per runbook)
- Policy and sharing questions
- Monthly usage reporting
*When to Escalate to Google (L3):*
- Service outages or degradation
- Complex technical issues
- Feature requests
- Security incidents
- Billing questions
*Transition:*
"Let me acknowledge the team that made this possible..."

## Slide 9
Acknowledgments & Next Steps
Client Team: Executive sponsor, IT lead, department champions, pilot users, training coordinators
Vendor Team: Project manager, solution architect, migration engineers, training specialists
Special Recognition: Change champions for peer support and IT team for migration weekend support
This Week: Final documentation handover, archive project artifacts
Next 30 Days: Monthly adoption review, identify Gemini for Workspace candidates
Next Quarter: Advanced feature enablement workshop, Google Chat rollout planning
Google Workspace Deployment
Notes: *Acknowledgments - Recognize Key Contributors:*
**Client Team Recognition:**
*Executive Sponsor - [Name]:*
- Championed cloud-first productivity strategy
- Secured budget and organizational support
- Drove change management communication
- Key decision: Approved phased migration approach
*IT Lead - [Name]:*
- Technical counterpart throughout deployment
- SSO and directory sync configuration
- Knowledge transfer recipient and future owner
- Will lead ongoing Workspace administration
*Change Champions (25 staff):*
- Peer support during migration waves
- First-line troubleshooting
- Feedback collection and escalation
- Adoption advocacy
**Vendor Team Recognition:**
*Project Manager - [Name]:*
- Overall delivery accountability
- Stakeholder communication
- Risk and issue management
- On-time, on-budget delivery
*Migration Engineer - [Name]:*
- GWMT configuration and execution
- File migration with permission mapping
- Data integrity validation
**Immediate Next Steps (This Week):**
| Task | Owner | Due Date |
|------|-------|----------|
| Final documentation handover | PM | [Date] |
| Archive project SharePoint | PM | [Date] |
| Confirm support contacts | IT Lead | [Date] |
**Phase 2 Opportunities:**
| Capability | Effort | Business Value |
|------------|--------|----------------|
| Gemini for Workspace | 2 weeks | AI productivity |
| Google Chat rollout | 3 weeks | Team messaging |
| Advanced analytics | 2 weeks | Usage insights |
| Third-party backup | 1 week | Compliance |
*Transition:*
"Thank you for your partnership on this project..."

## Slide 10
Thank You
Notes: *Closing and Q&A Preparation:*
**Closing Statement:**
"Thank you for your partnership throughout this project. We've successfully transformed productivity from aging Exchange servers to a modern cloud platform. The 500 users are actively collaborating, IT costs are down 42%, and you're positioned for future AI capabilities with Gemini.
I want to open the floor for questions. We have [time] remaining."
**Anticipated Questions:**
*Q: How do we add new users?*
A: Use Google Admin Console or GCDS sync. New users automatically provisioned via Azure AD.
*Q: What if we need more storage?*
A: Business Plus includes 5 TB per user. Enterprise Plus offers unlimited.
*Q: When should we enable Gemini?*
A: Recommend 90-day stability period, then pilot with 50 power users.
**Follow-Up Commitments:**
- [ ] Send final presentation deck
- [ ] Schedule 60-day adoption review
- [ ] Provide Gemini evaluation guide