## Cover
Test Plan
Generated: | November 27, 2025
Solution: | Workspace
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
FT-001 | Unit | Workspace Tenant Validation | Verify Google Workspace tenant is properly configured | Tenant created and domain verified | 1. Login to Admin Console; 2. Verify domain status; 3. Check subscription; 4. Validate organization settings | Tenant accessible with Business Plus edition active for 500 users | Critical | Not Started
FT-002 | Unit | Organizational Unit Structure | Verify OU structure matches design with 5 departments | Tenant configured | 1. Navigate to Directory; 2. Expand OU tree; 3. Verify 5 department OUs; 4. Check user assignments | 5 OUs visible (Sales Marketing Operations Finance Executive) | High | Not Started
FT-003 | Unit | SAML SSO Authentication | Verify Azure AD SSO integration works correctly | SSO configured with Azure AD | 1. Navigate to Google login; 2. Enter corporate email; 3. Verify redirect to Azure AD; 4. Complete authentication | Users authenticate via Azure AD SSO without password prompt | Critical | Not Started
FT-004 | Unit | Directory Sync Validation | Verify GCDS syncs users from Active Directory | GCDS installed and configured | 1. Check GCDS sync status; 2. Verify users in Admin Console; 3. Confirm group sync; 4. Validate attributes | Users and groups synced within 4-hour interval | High | Not Started
FT-005 | Unit | 2-Step Verification Enforcement | Verify 2SV is enforced for all users | 2SV policy configured | 1. Attempt login without 2SV; 2. Verify enrollment prompt; 3. Complete 2SV setup; 4. Test subsequent login | Users required to enroll in 2SV before accessing Workspace | Critical | Not Started
FT-006 | Unit | Gmail Functionality | Verify Gmail is accessible and functional for users | User accounts created | 1. Login to Gmail; 2. Send test email; 3. Receive test email; 4. Verify labels and filters | Gmail fully functional with send receive and organization features | High | Not Started
FT-007 | Unit | Google Drive Access | Verify Drive storage and sharing works correctly | User accounts created | 1. Login to Drive; 2. Upload test file; 3. Create shared folder; 4. Test sharing permissions | Drive accessible with 5 TB storage and sharing working | High | Not Started
FT-008 | Unit | Shared Drives Configuration | Verify Shared Drives created for team collaboration | Drive configured | 1. Navigate to Shared Drives; 2. Verify 15 Shared Drives; 3. Test file upload; 4. Check member access | 15 Shared Drives operational with correct permissions | High | Not Started
FT-009 | Unit | Google Meet Functionality | Verify Meet video conferencing works correctly | Meet enabled | 1. Create test meeting; 2. Join meeting; 3. Test video and audio; 4. Test screen sharing; 5. Test recording | Meet functional with video audio sharing and recording | High | Not Started
FT-010 | Unit | DLP Policy Enforcement | Verify DLP policies detect and block sensitive data | DLP policies configured | 1. Create document with PII; 2. Attempt to share externally; 3. Verify DLP warning; 4. Test block action | DLP detects sensitive data and blocks or warns per policy | Critical | Not Started
FT-011 | Unit | Google Vault Retention | Verify Vault retains data per 7-year policy | Vault configured | 1. Access Vault admin; 2. Verify retention rules; 3. Search retained emails; 4. Create legal hold | Vault retaining Gmail and Drive data per 7-year policy | Critical | Not Started
FT-012 | Unit | Mobile Device Management | Verify MDM policies apply to enrolled devices | MDM configured | 1. Enroll test device; 2. Verify passcode requirement; 3. Test app installation; 4. Verify remote wipe capability | Devices managed with passcode and wipe capabilities | High | Not Started
FT-013 | Integration | Exchange Migration - Pilot | Verify pilot mailbox migration completes successfully | GWMT configured | 1. Select 25 pilot mailboxes; 2. Start migration; 3. Monitor progress; 4. Validate data integrity | 25 pilot mailboxes migrated with all emails folders and labels | Critical | Not Started
FT-014 | Integration | File Migration Validation | Verify file server data migrates to Drive correctly | Migration tool configured | 1. Map source folders; 2. Start file migration; 3. Monitor transfer; 4. Validate permissions | Files migrated with folder structure and permissions preserved | Critical | Not Started
FT-015 | Integration | Distribution List Migration | Verify distribution lists convert to Google Groups | Groups configured | 1. Import distribution list; 2. Verify membership; 3. Test email delivery; 4. Check external senders | 150 distribution lists converted to Groups with membership intact | High | Not Started
FT-016 | Integration | Calendar Migration | Verify calendar data migrates correctly | Migration configured | 1. Migrate pilot calendars; 2. Verify appointments; 3. Check recurring events; 4. Validate sharing | Calendars migrated with all appointments and sharing settings | High | Not Started
FT-017 | Integration | Wave 1 Migration Complete | Verify Sales department migration successful | Pilot validated | 1. Migrate 95 Sales mailboxes; 2. Migrate Sales files; 3. Validate data; 4. User acceptance | Sales department (95 users) fully migrated and operational | Critical | Not Started
FT-018 | Integration | Wave 2-5 Migration Complete | Verify remaining departments migrate successfully | Wave 1 complete | 1. Execute Waves 2-5 per schedule; 2. Validate each wave; 3. Monitor issues; 4. User sign-off | All 500 users migrated with zero data loss | Critical | Not Started

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
NFT-001 | Performance | Email Delivery Performance | Verify email delivery meets performance targets | Gmail operational | 1. Send bulk test emails; 2. Measure delivery time; 3. Test attachment handling; 4. Verify queuing | Emails delivered within 30 seconds for internal and 2 minutes external | High | Not Started
NFT-002 | Performance | Drive Sync Performance | Verify Drive File Stream sync performance | Drive configured | 1. Install Drive File Stream; 2. Sync large folder; 3. Measure sync time; 4. Test offline access | Files sync within 5 minutes for 1 GB folder | Medium | Not Started
NFT-003 | Performance | Meet Video Quality | Verify Meet video quality under load | Meet enabled | 1. Create 50-participant meeting; 2. Test video quality; 3. Test screen sharing; 4. Measure latency | Video quality maintained at 720p with latency under 200ms | Medium | Not Started
NFT-004 | Performance | Migration Throughput | Verify migration completes within timeline | Migration tools ready | 1. Measure mailbox migration rate; 2. Measure file transfer rate; 3. Calculate total duration | Migration rate of 10 GB per hour sustained | High | Not Started
NFT-005 | Security | SSO Security Validation | Verify SSO security controls are effective | SSO configured | 1. Test invalid credentials; 2. Test session timeout; 3. Test logout; 4. Verify audit logs | Invalid logins blocked and all auth events logged | Critical | Not Started
NFT-006 | Security | DLP Effectiveness Test | Verify DLP catches sensitive data patterns | DLP policies active | 1. Test SSN patterns; 2. Test credit card patterns; 3. Test custom patterns; 4. Verify actions | DLP detects 95%+ of sensitive data patterns | Critical | Not Started
NFT-007 | Security | Mobile Security Validation | Verify MDM security policies are enforced | MDM configured | 1. Test without passcode; 2. Test compromised device; 3. Test remote wipe; 4. Verify encryption | Non-compliant devices blocked and wipe functional | High | Not Started
NFT-008 | Availability | Service Uptime Validation | Verify Google Workspace meets 99.9% SLA | Production environment | 1. Monitor service status; 2. Track any outages; 3. Calculate uptime; 4. Compare to SLA | Workspace services maintain 99.9%+ uptime | High | Not Started
NFT-009 | Compliance | Vault Retention Compliance | Verify Vault meets 7-year retention requirement | Vault configured | 1. Verify retention policy; 2. Test search across 7 years; 3. Test legal hold; 4. Verify export | Data retained and searchable for 7-year period | Critical | Not Started
NFT-010 | Compliance | Audit Log Completeness | Verify audit logs capture all required events | Logging enabled | 1. Review admin logs; 2. Review user logs; 3. Verify completeness; 4. Test log export | All admin and user activities logged and exportable | High | Not Started

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
UAT-001 | Acceptance | Pilot User Email Access | Verify pilot users can send and receive email | Pilot migration complete | 1. Pilot user logs in; 2. Access Gmail; 3. Send test email; 4. Receive reply | Pilot users can send and receive email without issues | Critical | Not Started
UAT-002 | Acceptance | Pilot User File Access | Verify pilot users can access migrated files | Pilot migration complete | 1. Pilot user logs in; 2. Access Drive; 3. Open migrated files; 4. Edit and save | Pilot users can access and edit all migrated files | Critical | Not Started
UAT-003 | Acceptance | Pilot User Collaboration | Verify pilot users can collaborate in real-time | Pilot training complete | 1. Create shared document; 2. Invite collaborators; 3. Edit simultaneously; 4. Track changes | Multiple users can edit documents simultaneously | High | Not Started
UAT-004 | Acceptance | Mobile Access Validation | Verify users can access Workspace from mobile devices | MDM enrolled | 1. Install Gmail app; 2. Install Drive app; 3. Access email; 4. Access files | Users can access email and files from managed mobile devices | High | Not Started
UAT-005 | Acceptance | End-User Training Effectiveness | Verify users can perform key tasks after training | Training delivered | 1. Send email with attachment; 2. Share Drive file; 3. Schedule Meet; 4. Create Docs | Users can perform all trained tasks independently | High | Not Started
UAT-006 | Acceptance | Department Migration Sign-off | Verify each department approves migration quality | Wave migration complete | 1. Department review; 2. Data validation; 3. Functionality test; 4. Sign-off | Each department lead signs off on migration quality | Critical | Not Started
UAT-007 | Acceptance | Admin Console Operations | Verify IT team can manage Workspace effectively | Admin training complete | 1. Create user; 2. Reset password; 3. Manage groups; 4. Run reports | IT admins can perform all required admin tasks | High | Not Started
UAT-008 | Acceptance | Support Readiness Validation | Verify helpdesk can support Workspace users | Support training complete | 1. Handle password reset; 2. Troubleshoot login; 3. Resolve Drive issue; 4. Escalate appropriately | Helpdesk can resolve common issues per runbook | High | Not Started