## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Sd Wan Enterprise
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | EO Project Manager | Not Started
Discovery | Network Assessment | 5 days | [START_DATE+1] | [START_DATE+6] | Project Kickoff | EO Network Architect | Not Started
Discovery | Site Survey and Inventory | 4 days | [START_DATE+4] | [START_DATE+8] | Network Assessment | EO Network Engineer | Not Started
Discovery | Application Traffic Analysis | 4 days | [START_DATE+6] | [START_DATE+10] | Site Survey | EO Network Architect | Not Started
Discovery | SD-WAN Design Workshop | 3 days | [START_DATE+9] | [START_DATE+12] | Traffic Analysis | EO Network Architect | Not Started
Foundation | vManage Cluster Deployment | 4 days | [START_DATE+12] | [START_DATE+16] | Discovery Complete | EO Network Engineer | Not Started
Foundation | vSmart Controller Setup | 3 days | [START_DATE+15] | [START_DATE+18] | vManage Deployment | EO Network Engineer | Not Started
Foundation | vBond Orchestrator Setup | 2 days | [START_DATE+17] | [START_DATE+19] | vSmart Setup | EO Network Engineer | Not Started
Foundation | Certificate Authority Config | 2 days | [START_DATE+18] | [START_DATE+20] | vBond Setup | EO Security Engineer | Not Started
Foundation | Control Plane Validation | 2 days | [START_DATE+20] | [START_DATE+22] | Certificate Config | EO Network Engineer | Not Started
Policy | Application-Aware Policies | 5 days | [START_DATE+22] | [START_DATE+27] | Control Plane Ready | EO Network Architect | Not Started
Policy | QoS Profile Configuration | 4 days | [START_DATE+25] | [START_DATE+29] | App Policies | EO Network Engineer | Not Started
Policy | Security Policy Design | 4 days | [START_DATE+27] | [START_DATE+31] | QoS Profiles | EO Security Engineer | Not Started
Policy | SLA Class Definition | 3 days | [START_DATE+30] | [START_DATE+33] | Security Policies | EO Network Architect | Not Started
Policy | Cloud OnRamp Configuration | 4 days | [START_DATE+32] | [START_DATE+36] | SLA Classes | EO Network Engineer | Not Started
Deployment | Pilot Site Migration (5) | 5 days | [START_DATE+36] | [START_DATE+41] | Policies Complete | EO Network Engineer | Not Started
Deployment | Wave 1: Hub Sites (10) | 5 days | [START_DATE+41] | [START_DATE+46] | Pilot Complete | EO Network Engineer | Not Started
Deployment | Wave 2: Regional Sites (35) | 7 days | [START_DATE+46] | [START_DATE+53] | Wave 1 Complete | EO Network Engineer | Not Started
Deployment | Wave 3: Branch Sites (50) | 10 days | [START_DATE+53] | [START_DATE+63] | Wave 2 Complete | EO Network Engineer | Not Started
Deployment | Wave 4: Remote Sites (50) | 10 days | [START_DATE+63] | [START_DATE+73] | Wave 3 Complete | EO Network Engineer | Not Started
Testing | Functional Testing | 5 days | [START_DATE+73] | [START_DATE+78] | Wave 4 Complete | EO QA Engineer | Not Started
Testing | Failover Testing | 4 days | [START_DATE+76] | [START_DATE+80] | Functional Testing | EO Network Engineer | Not Started
Testing | Performance Testing | 4 days | [START_DATE+78] | [START_DATE+82] | Failover Testing | EO QA Engineer | Not Started
Testing | Security Validation | 3 days | [START_DATE+80] | [START_DATE+83] | Performance Testing | EO Security Engineer | Not Started
Testing | User Acceptance Testing | 4 days | [START_DATE+82] | [START_DATE+86] | Security Validation | Client Network Team | Not Started
Training | Network Engineer Training | 8 hours | [START_DATE+83] | [START_DATE+84] | Security Validation | EO Network Architect | Not Started
Training | NOC Operator Training | 8 hours | [START_DATE+84] | [START_DATE+85] | Engineer Training | EO Network Architect | Not Started
Training | Security Team Training | 4 hours | [START_DATE+85] | [START_DATE+86] | NOC Training | EO Security Engineer | Not Started
Go-Live | MPLS Circuit Cutover | 3 days | [START_DATE+86] | [START_DATE+89] | UAT Complete | EO Network Engineer | Not Started
Go-Live | Production Go-Live | 2 days | [START_DATE+89] | [START_DATE+91] | Cutover Complete | EO Project Manager | Not Started
Support | Hypercare Week 1 | 7 days | [START_DATE+91] | [START_DATE+98] | Go-Live | EO Network Engineer | Not Started
Support | Hypercare Week 2 | 7 days | [START_DATE+98] | [START_DATE+105] | Hypercare Week 1 | EO Network Engineer | Not Started
Closure | Performance Optimization | 3 days | [START_DATE+102] | [START_DATE+105] | Hypercare Week 2 | EO Network Architect | Not Started
Closure | Knowledge Transfer | 2 days | [START_DATE+105] | [START_DATE+107] | Optimization | EO Project Manager | Not Started
Closure | Documentation Delivery | 2 days | [START_DATE+107] | [START_DATE+109] | Knowledge Transfer | EO Network Architect | Not Started
Closure | Project Closure | 1 day | [START_DATE+109] | [START_DATE+110] | Documentation | EO Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Design Complete | [START_DATE+12] | SD-WAN architecture approved; Site inventory complete; Policy framework defined | EO Network Architect | Not Started
M2 | Control Plane Ready | [START_DATE+22] | vManage cluster operational; vSmart HA active; Certificate authority configured | EO Network Engineer | Not Started
M3 | Policies Deployed | [START_DATE+36] | 25 app policies active; QoS profiles validated; Security zones configured | EO Network Architect | Not Started
M4 | Sites Migrated | [START_DATE+73] | 150 sites on SD-WAN; MPLS circuits decommissioned; Cloud onramps active | EO Network Engineer | Not Started
M5 | Testing Complete | [START_DATE+86] | Functional tests passed; Failover validated; Security assessment cleared | EO QA Engineer | Not Started
M6 | Go-Live | [START_DATE+91] | Production operational; 99.99% availability target; NOC monitoring active | EO Project Manager | Not Started
M7 | Hypercare Complete | [START_DATE+110] | Support transition done; Team trained (1680 hrs); Documentation delivered | EO Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | NetArch | NetEng | SecEng | QA | NOC | AppOwners | Client
Project Charter and Kickoff | A | C | I | I | I | I | I | C
SD-WAN Architecture Design | A | R | C | C | I | I | I | I
Site Survey and Inventory | A | C | R | I | I | I | I | C
vManage Cluster Deployment | A | C | R | I | I | I | I | I
vSmart Controller Setup | A | C | R | I | I | I | I | I
Application Policy Design | A | R | C | I | I | I | C | I
QoS Profile Configuration | A | C | R | I | I | I | C | I
Security Policy Implementation | A | C | C | R | I | I | I | I
Cloud OnRamp Configuration | A | C | R | I | I | I | I | I
Pilot Site Migration | A | C | R | I | C | I | I | I
Wave Deployments | A | C | R | I | I | I | I | C
Functional Testing | A | I | C | I | R | I | I | I
Failover Testing | A | C | R | I | C | I | I | I
Security Validation | A | C | C | R | C | I | I | I
User Acceptance Testing | A | I | C | I | C | I | R | A
NOC Operator Training | A | R | C | I | I | R | I | I
MPLS Cutover | A | C | R | I | I | C | I | C
Production Go-Live | A | C | R | C | C | C | I | R
Hypercare Support | A | C | R | C | C | R | I | I
Knowledge Transfer | A | R | C | C | I | C | I | C
Documentation Delivery | A | R | C | C | I | C | I | I
Legend:
R | A A A A A A A A A A A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on SD-WAN transformation objectives | EO Project Manager | Day 1
Steering Committee | Bi-weekly | Executive sponsors and IT leadership | Strategic direction and network investment decisions | EO Project Manager | Alternate Tuesdays
Project Status Meeting | Weekly | Core project team | Review progress and address blockers across workstreams | EO Project Manager | Mondays 10:00
Architecture Review | Weekly | Network architects and engineers | SD-WAN design decisions and policy configuration | EO Network Architect | Wednesdays 14:00
Migration Standup | Daily | Migration team | Site migration progress and deployment issues | EO Network Engineer | Daily 09:30
NOC Coordination | Weekly | NOC and network team | Monitoring setup and incident procedures | EO Network Engineer | Thursdays 11:00
Security Review | Bi-weekly | Security and network teams | Security policies and compliance validation | EO Security Engineer | Alternate Fridays
Site Readiness | Weekly | Site coordinators | Site preparation and cutover scheduling | EO Project Manager | Fridays 14:00
Risk and Issue Review | Bi-weekly | PM and Risk Manager | Risk assessment and mitigation tracking | EO Project Manager | Alternate Fridays
Go-Live Readiness | Daily (2 wks pre) | Go-live team | Deployment preparation and cutover checklist | EO Project Manager | Daily 09:00
Hypercare Review | Daily (hypercare) | Support and operations | Network stability and issue resolution | EO Network Engineer | Daily 10:00
Project Closeout | Once | All stakeholders | Hypercare completion and operational handoff | EO Project Manager | Week 16