## Cover
Test Plan
Generated: | November 28, 2025
Solution: | Sd Wan Enterprise
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Name | Description | Expected Result | Priority | Duration
FT-001 | vManage Cluster Health | Verify vManage cluster operational status and node synchronization | All 3 vManage nodes healthy with synchronized databases | Critical | 30 min
FT-002 | vSmart Controller Connectivity | Validate vSmart HA pair control connections to vManage | Both vSmart controllers connected and distributing policies | Critical | 20 min
FT-003 | vBond Orchestrator Function | Test vBond device authentication and NAT traversal | vEdge devices authenticate and establish tunnels via vBond | Critical | 20 min
FT-004 | vEdge Device Onboarding | Validate zero-touch provisioning for new vEdge devices | Devices auto-provision with correct templates and policies | High | 45 min
FT-005 | OMP Route Advertisement | Test OMP route propagation across SD-WAN fabric | Routes advertised and received at all sites within 30 seconds | Critical | 25 min
FT-006 | IPsec Tunnel Establishment | Verify IPsec data plane tunnels between sites | Full mesh tunnels established with correct encryption | Critical | 30 min
FT-007 | TLOC Color Assignment | Test transport locator color configuration and routing | Traffic routes correctly based on TLOC color preferences | High | 20 min
FT-008 | Application Recognition | Validate DPI engine application identification accuracy | Applications correctly identified and classified | High | 35 min
FT-009 | App-Aware Routing Policy | Test application-based traffic steering decisions | Traffic follows defined application-aware policies | High | 40 min
FT-010 | QoS Policy Enforcement | Verify QoS markings and queue assignments per policy | Voice/video traffic prioritized with correct DSCP values | High | 30 min
FT-011 | SLA Class Application | Test SLA-based path selection for business-critical apps | Traffic uses paths meeting defined SLA thresholds | High | 35 min
FT-012 | VPN Segmentation | Validate traffic isolation between VPN segments | No traffic leakage between isolated VPN segments | Critical | 25 min
FT-013 | Zone-Based Firewall | Test firewall rules and inter-zone traffic control | Traffic blocked/permitted per zone-based policy rules | High | 40 min
FT-014 | IPS Threat Detection | Verify IPS engine detects and blocks known threats | Malicious traffic detected and blocked with alerts | High | 45 min
FT-015 | URL Filtering | Test web content filtering and category blocking | Blocked categories denied with user notification | Medium | 30 min
FT-016 | Cloud OnRamp AWS | Validate AWS Direct Connect integration and routing | AWS traffic routes via Cloud OnRamp with optimization | High | 35 min
FT-017 | Cloud OnRamp Azure | Test Azure ExpressRoute connectivity and failover | Azure workloads accessible via dedicated connection | High | 35 min
FT-018 | SaaS Optimization O365 | Verify Microsoft 365 direct internet breakout | M365 traffic bypasses backhaul with improved latency | High | 30 min
FT-019 | Template Push to vEdge | Test configuration template deployment to edge devices | Templates applied successfully without service impact | High | 25 min
FT-020 | Centralized Policy Update | Validate policy updates propagate to all devices | Policy changes effective at all sites within 60 seconds | High | 20 min

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Name | Description | Expected Result | Priority | Duration
NF-001 | Dual Transport Failover | Simulate MPLS failure and verify Internet failover | Traffic fails over to Internet within 3 seconds | Critical | 45 min
NF-002 | vSmart Controller Failover | Test control plane HA by failing primary vSmart | Secondary vSmart assumes control within 5 seconds | Critical | 30 min
NF-003 | vManage Node Failure | Simulate vManage node failure in cluster | Remaining nodes maintain operations with no data loss | Critical | 40 min
NF-004 | BFD Session Recovery | Test BFD rapid failure detection and recovery | BFD detects failure and triggers reroute within 1 second | High | 25 min
NF-005 | Throughput Benchmark | Measure aggregate throughput across SD-WAN fabric | Sustained 10 Gbps throughput at hub sites achieved | High | 60 min
NF-006 | Latency Measurement | Validate latency SLA for voice and video traffic | Voice latency under 150ms with less than 1% jitter | High | 45 min
NF-007 | Concurrent Tunnel Scale | Test maximum concurrent IPsec tunnels per device | Support 8000 tunnels per vEdge without degradation | High | 50 min
NF-008 | Policy Scale Test | Validate system performance with maximum policies | 25 app policies and 12 security zones perform correctly | Medium | 40 min
NF-009 | Software Upgrade Procedure | Test software upgrade with minimal service impact | Upgrade completes with less than 30 seconds traffic loss | High | 90 min
NF-010 | Configuration Rollback | Verify rollback capability for failed changes | Configuration rolls back within 60 seconds on failure | High | 30 min
NF-011 | DR Site Activation | Test disaster recovery site activation procedure | DR site active within 15 minutes of primary failure | Critical | 120 min
NF-012 | Certificate Renewal | Validate automated certificate renewal process | Certificates renew without manual intervention or outage | Medium | 45 min

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Name | Description | Expected Result | Priority | Duration
UAT-001 | vManage Dashboard Access | Network team validates dashboard usability and views | Team can navigate and interpret all dashboard widgets | High | 60 min
UAT-002 | Template Creation Workflow | Validate self-service template creation process | Engineers create and deploy templates independently | High | 90 min
UAT-003 | Troubleshooting Tools | Test vManage troubleshooting and diagnostic tools | NOC can diagnose issues using built-in tools | High | 75 min
UAT-004 | Voice Quality Validation | Business users validate voice call quality over SD-WAN | Voice calls clear with no perceptible quality issues | Critical | 60 min
UAT-005 | Video Conference Testing | Validate video conference quality and reliability | Video conferences maintain HD quality throughout | High | 45 min
UAT-006 | Application Performance | Business validates critical application performance | ERP and CRM applications perform at or above baseline | High | 90 min