## Cover
Project Plan
Generated: | November 27, 2025
Solution: | Vxrail Hci
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Planning | Project Kickoff | 1 day | Week 1 Day 1 | Week 1 Day 1 | None | Project Manager | Not Started
Planning | Current State Assessment | 2 days | Week 1 Day 1 | Week 1 Day 2 | Project Kickoff | VMware Architect | Not Started
Planning | VM Inventory and Sizing | 2 days | Week 1 Day 2 | Week 1 Day 3 | Assessment Start | Solutions Architect | Not Started
Planning | Network Requirements Review | 2 days | Week 1 Day 3 | Week 1 Day 4 | VM Inventory | Network Engineer | Not Started
Planning | VxRail Configuration Design | 2 days | Week 1 Day 4 | Week 2 Day 1 | All Assessments | VMware Architect | Not Started
Planning | Dell Hardware Order Submission | 1 day | Week 2 Day 1 | Week 2 Day 1 | Design Approved | Procurement | Not Started
Planning | Data Center Preparation | 5 days | Week 2 Day 1 | Week 2 Day 5 | Order Submitted | Facilities Team | Not Started
Planning | VLAN and Switch Configuration | 3 days | Week 2 Day 3 | Week 2 Day 5 | Data Center Prep | Network Engineer | Not Started
Deployment | Hardware Delivery and Rack | 1 day | Week 3 Day 1 | Week 3 Day 1 | Dell Delivery | Dell ProDeploy | Not Started
Deployment | VxRail Node Cabling | 1 day | Week 3 Day 1 | Week 3 Day 1 | Hardware Racked | Dell ProDeploy | Not Started
Deployment | VxRail Manager Initialization | 1 day | Week 3 Day 2 | Week 3 Day 2 | Cabling Complete | VMware Architect | Not Started
Deployment | Cluster Creation and vSAN Config | 2 days | Week 3 Day 2 | Week 3 Day 3 | VxRail Init | VMware Architect | Not Started
Deployment | vCenter Integration | 1 day | Week 3 Day 4 | Week 3 Day 4 | Cluster Created | VMware Architect | Not Started
Deployment | vSAN Policy Configuration | 1 day | Week 3 Day 4 | Week 3 Day 4 | vCenter Integrated | VMware Architect | Not Started
Deployment | Distributed Switch Configuration | 1 day | Week 3 Day 5 | Week 3 Day 5 | Policies Created | Network Engineer | Not Started
Deployment | Veeam Backup Integration | 2 days | Week 4 Day 1 | Week 4 Day 2 | VDS Complete | Backup Admin | Not Started
Migration | Migration Wave Planning | 1 day | Week 4 Day 1 | Week 4 Day 1 | Backup Ready | VMware Architect | Not Started
Migration | Wave 1 VM Migration (50 VMs) | 2 days | Week 4 Day 2 | Week 4 Day 3 | Wave Planning | VMware Admin | Not Started
Migration | Wave 2 VM Migration (50 VMs) | 2 days | Week 4 Day 4 | Week 4 Day 5 | Wave 1 Complete | VMware Admin | Not Started
Migration | Wave 3 VM Migration (50 VMs) | 2 days | Week 5 Day 1 | Week 5 Day 2 | Wave 2 Complete | VMware Admin | Not Started
Migration | Wave 4 VM Migration (50 VMs) | 2 days | Week 5 Day 2 | Week 5 Day 3 | Wave 3 Complete | VMware Admin | Not Started
Migration | Wave 5 VM Migration (50 VMs) | 2 days | Week 5 Day 4 | Week 5 Day 5 | Wave 4 Complete | VMware Admin | Not Started
Validation | HCIBench Performance Testing | 1 day | Week 5 Day 5 | Week 5 Day 5 | Migration Complete | VMware Architect | Not Started
Validation | vSAN Health Validation | 1 day | Week 6 Day 1 | Week 6 Day 1 | Performance Testing | VMware Architect | Not Started
Training | VxRail Administration Training | 1 day | Week 6 Day 1 | Week 6 Day 1 | Validation Complete | Training Lead | Not Started
Training | vSAN Troubleshooting Training | 0.5 day | Week 6 Day 2 | Week 6 Day 2 | Admin Training | Training Lead | Not Started
Training | Veeam Backup Training | 0.5 day | Week 6 Day 2 | Week 6 Day 2 | Admin Training | Training Lead | Not Started
Closure | Documentation Finalization | 2 days | Week 6 Day 3 | Week 6 Day 4 | All Training | Technical Writer | Not Started
Closure | Project Acceptance Sign-off | 1 day | Week 6 Day 4 | Week 6 Day 4 | Documentation | Project Manager | Not Started
Closure | Hypercare Handover | 1 day | Week 6 Day 5 | Week 6 Day 5 | Acceptance | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Hardware Ordered | Week 2 | Dell VxRail purchase order submitted and delivery scheduled | Project Manager | Not Started
M2 | Hardware Delivered | Week 3 | 4 VxRail E560 nodes delivered racked and cabled | Dell ProDeploy | Not Started
M3 | Cluster Operational | Week 3 | VxRail cluster created with vSAN and vCenter integrated | VMware Architect | Not Started
M4 | Migration Complete | Week 5 | All 250 VMs migrated to VxRail with zero data loss | VMware Admin | Not Started
M5 | Validation Complete | Week 6 | HCIBench benchmarks passed and vSAN health verified | VMware Architect | Not Started
M6 | Project Closure | Week 6 | Training complete documentation accepted support transitioned | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Arch | VMware | NetEng | Storage | Backup | IT | Client
Project Charter and Kickoff | A | C | C | I | I | I | C | I
Current State Assessment | A | R | C | C | C | I | C | C
VxRail Configuration Design | A | R | C | C | C | I | I | I
Dell Hardware Procurement | A | C | I | I | I | I | R | C
VxRail Cluster Deployment | A | R | C | C | I | I | C | I
vSAN Configuration | A | R | C | I | C | I | I | I
Network Switch Configuration | A | C | C | R | I | I | C | I
Veeam Backup Integration | A | C | C | I | I | R | C | I
VM Migration Execution | A | C | R | C | I | I | C | I
HCIBench Performance Testing | A | R | C | I | I | I | I | I
VxRail Administration Training | A | I | R | I | I | C | C | C
Documentation Delivery | A | R | C | C | C | C | C | I
Production Go-Live Approval | A | C | C | C | C | C | C | R
Legend:
R | A A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders PM Architect IT Lead | Launch project and align on scope and timeline | Project Manager | Week 1 Day 1
Steering Committee | Weekly | Executive sponsors PM IT Director | Strategic updates budget review issue escalation | Project Manager | Fridays 10:00
Daily Standup | Daily | Core project team | Review progress blockers and daily priorities | Project Manager | Daily 09:00
Technical Review | Weekly | Architect VMware Admin Network Storage | Technical decisions and implementation progress | VMware Architect | Wednesdays 14:00
Migration Checkpoint | Daily | VMware Admin Architect Backup Admin | VM migration progress and issue resolution | VMware Admin | Week 4-5 Daily
Validation Review | Daily | Architect VMware Admin QA | Benchmark results and health check findings | VMware Architect | Week 6 Daily
Training Coordination | Once | Training Lead VMware Admin IT Team | Training schedule and logistics confirmation | Training Lead | Week 5 Day 5
Go-Live Readiness | Daily | All stakeholders | Go-live checklist and final preparation | Project Manager | Week 6 Daily