## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Virtual Wan Global
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff and Network Assessment | 1 day | [START_DATE] | [START_DATE+1] | None | Project Manager | Not Started
Discovery | Current Network Infrastructure Assessment | 7 days | [START_DATE+1] | [START_DATE+8] | Project Kickoff | Network Architect | Not Started
Discovery | Azure Environment and Service Availability Assessment | 7 days | [START_DATE+3] | [START_DATE+10] | Current Network Assessment | Cloud Engineer | Not Started
Discovery | Branch Site Survey and Connectivity Requirements | 10 days | [START_DATE+5] | [START_DATE+15] | Current Network Assessment | Network Engineer | Not Started
Planning | Virtual WAN Hub Architecture Design | 12 days | [START_DATE+10] | [START_DATE+22] | Azure Environment Assessment | Network Architect | Not Started
Planning | Hub-and-Spoke Topology and Routing Design | 10 days | [START_DATE+15] | [START_DATE+25] | Architecture Design | Network Architect | Not Started
Planning | Security Architecture and Firewall Design | 10 days | [START_DATE+18] | [START_DATE+28] | Current Network Assessment | Security Architect | Not Started
Planning | ExpressRoute Circuit Planning and Design | 10 days | [START_DATE+20] | [START_DATE+30] | Architecture Design | Network Engineer | Not Started
Infrastructure | Azure Virtual WAN Foundation Setup | 7 days | [START_DATE+30] | [START_DATE+37] | Architecture Design | Cloud Engineer | Not Started
Infrastructure | Regional Virtual WAN Hub Deployment | 15 days | [START_DATE+35] | [START_DATE+50] | Foundation Setup | Cloud Engineer | Not Started
Infrastructure | ExpressRoute Circuit Provisioning | 40 days | [START_DATE+25] | [START_DATE+65] | ExpressRoute Planning | Network Engineer | Not Started
Infrastructure | Azure Firewall Deployment and Configuration | 10 days | [START_DATE+45] | [START_DATE+55] | Hub Deployment | Security Engineer | Not Started
Development | Site-to-Site VPN Gateway Configuration | 20 days | [START_DATE+50] | [START_DATE+70] | Site Survey Complete | Network Engineer | Not Started
Development | ExpressRoute Circuit Hub Integration | 10 days | [START_DATE+65] | [START_DATE+75] | Circuit Provisioning | Network Engineer | Not Started
Development | Traffic Routing and Optimization Policies | 13 days | [START_DATE+55] | [START_DATE+68] | Topology Design | Network Engineer | Not Started
Development | Firewall Rules and Security Policy Implementation | 10 days | [START_DATE+60] | [START_DATE+70] | Firewall Deployment | Security Engineer | Not Started
Development | Network Monitoring and Analytics Configuration | 10 days | [START_DATE+70] | [START_DATE+80] | Hub Deployment | Cloud Engineer | Not Started
Testing | Hub-to-Hub Connectivity and Routing Tests | 10 days | [START_DATE+75] | [START_DATE+85] | Routing Policies | Network Engineer | Not Started
Testing | Branch Site Connectivity and Application Tests | 15 days | [START_DATE+80] | [START_DATE+95] | VPN Configuration | Network Engineer | Not Started
Testing | Network Performance and Load Testing | 7 days | [START_DATE+85] | [START_DATE+92] | Monitoring Configuration | Performance Engineer | Not Started
Testing | Security Validation and Firewall Testing | 15 days | [START_DATE+75] | [START_DATE+90] | Security Implementation | Security Engineer | Not Started
Testing | Failover and Redundancy Testing | 7 days | [START_DATE+90] | [START_DATE+97] | Performance Testing | Network Engineer | Not Started
Testing | User Acceptance Testing and Business Validation | 10 days | [START_DATE+95] | [START_DATE+105] | Security Validation | Business Analyst | Not Started
Deployment | Production Cutover Planning and Preparation | 7 days | [START_DATE+100] | [START_DATE+107] | Foundation Setup | Project Manager | Not Started
Deployment | Phased Site Migration to Virtual WAN | 20 days | [START_DATE+105] | [START_DATE+125] | Cutover Planning | Network Engineer | Not Started
Deployment | Production Network Validation | 2 days | [START_DATE+125] | [START_DATE+127] | Site Migration | Network Engineer | Not Started
Training | Network Administrator Training Program | 10 days | [START_DATE+110] | [START_DATE+120] | UAT Complete | Training Specialist | Not Started
Training | Network Operations Center Staff Training | 7 days | [START_DATE+120] | [START_DATE+127] | Production Validation | Training Specialist | Not Started
Training | Technical Documentation and Runbooks | 15 days | [START_DATE+115] | [START_DATE+130] | Production Validation | Technical Writer | Not Started
Go-Live | Production Go-Live and Network Cutover | 2 days | [START_DATE+127] | [START_DATE+129] | Training Complete | Project Manager | Not Started
Support | Intensive Go-Live Support Period | 7 days | [START_DATE+129] | [START_DATE+136] | Production Go-Live | Support Team | Not Started
Support | Performance Monitoring and Optimization | 30 days | [START_DATE+136] | [START_DATE+166] | Go-Live Support | Network Engineer | Not Started
Closure | Knowledge Transfer to Operations Team | 10 days | [START_DATE+150] | [START_DATE+160] | Documentation Complete | Project Manager | Not Started
Closure | Project Closure and Lessons Learned | 2 days | [START_DATE+166] | [START_DATE+168] | Performance Baseline | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
MS-001 | Project Kickoff Complete | [START_DATE+1] | Project charter signed; team mobilized; stakeholders aligned | Project Manager | Pending
MS-002 | Architecture Design Approved | [START_DATE+22] | Virtual WAN hub design validated; routing topology finalized; security architecture approved | Network Architect | Pending
MS-003 | Infrastructure Foundation Ready | [START_DATE+37] | Azure Virtual WAN deployed; resource groups configured; subscriptions prepared | Cloud Engineer | Pending
MS-004 | Hub Deployment Complete | [START_DATE+50] | All regional hubs operational; VPN gateways configured; ExpressRoute gateways ready | Cloud Engineer | Pending
MS-005 | Security Implementation Complete | [START_DATE+70] | Azure Firewall deployed; security policies active; threat protection enabled | Security Engineer | Pending
MS-006 | ExpressRoute Integration Complete | [START_DATE+75] | ExpressRoute circuits connected; Global Reach configured; routing validated | Network Engineer | Pending
MS-007 | Security Validation Passed | [START_DATE+90] | Firewall rules tested; threat detection verified; compliance validated | Security Engineer | Pending
MS-008 | User Acceptance Testing Complete | [START_DATE+105] | Business validation passed; performance metrics achieved; stakeholder sign-off obtained | Business Analyst | Pending
MS-009 | Production Cutover Complete | [START_DATE+127] | All sites migrated; production traffic flowing; network performance validated | Project Manager | Pending
MS-010 | Project Closure | [START_DATE+168] | Knowledge transfer complete; documentation delivered; project closed | Project Manager | Pending

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Arch | Eng | Sec | QA | Client IT | Client Sec | Sponsor
Project Kickoff and Charter | A | C | C | C | I | R | I | R
Current Network Assessment | C | R | R | C | I | A | C | I
Virtual WAN Architecture Design | C | A | R | C | I | C | I | I
Security Architecture Design | C | C | R | A | I | C | R | I
Azure Infrastructure Setup | C | R | A | C | I | C | I | I
Virtual Hub Deployment | R | R | A | C | I | C | I | I
ExpressRoute Provisioning | C | R | A | I | I | C | I | I
Azure Firewall Configuration | C | C | R | A | I | C | C | I
VPN Gateway Configuration | C | R | A | C | I | C | I | I
Routing Policy Implementation | C | R | A | I | I | C | I | I
Security Policy Implementation | C | C | R | A | I | C | A | I
Monitoring Configuration | C | R | A | I | I | C | I | I
Connectivity Testing | R | R | A | C | R | C | I | I
Security Validation Testing | R | C | R | A | A | C | R | I
Performance Testing | R | C | A | I | R | C | I | I
User Acceptance Testing | C | I | C | I | R | A | C | I
Production Cutover Planning | A | R | R | C | I | C | I | R
Site Migration Execution | R | C | A | C | I | C | I | I
Network Administrator Training | C | R | R | C | I | A | I | I
NOC Staff Training | C | R | R | I | I | A | I | I
Documentation Delivery | R | R | A | C | C | A | I | I
Knowledge Transfer | R | R | R | C | I | A | I | I
Production Go-Live | A | R | R | C | I | C | I | R
Go-Live Support | R | C | A | C | I | C | I | I
Project Closure | A | C | I | I | I | C | I | R
Legend:
R | A C C C C R C C C C C C R R R C A R C C R R A R A: Responsible - Does the work
A | A C C C C R C C C C C C R R R C A R C C R R A R A: Accountable - Ultimate ownership
C | A C C C C R C C C C C C R R R C A R C C R R A R A: Consulted - Provides input
I | A C C C C R C C C C C C R R R C A R C C R R A R A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | One-time | All stakeholders and project team | Align on objectives and deliverables | Project Manager | [TBD]
Weekly Status Meeting | Weekly | PM ¦ Arch ¦ Eng ¦ Client IT Lead | Review progress and address issues | Project Manager | Mondays 10am
Steering Committee | Bi-weekly | PM ¦ Sponsor ¦ Client Management ¦ Arch | Executive updates and decisions | Project Manager | Thursdays 2pm
Technical Design Review | As needed | Arch ¦ Eng ¦ Sec ¦ Client IT | Review and approve technical designs | Network Architect | [TBD]
Security Review | Bi-weekly | Sec ¦ Client Sec ¦ PM ¦ Arch | Security compliance and validation | Security Architect | Wednesdays 11am
Testing Status | Weekly | QA ¦ Eng ¦ PM ¦ Client IT | Testing progress and issue resolution | QA Lead | Fridays 9am
Training Sessions | As scheduled | Training Lead ¦ Client IT ¦ Operations | Knowledge transfer and training | Training Specialist | [TBD]
Go-Live Readiness | Daily during cutover | PM ¦ Arch ¦ Eng ¦ Client IT ¦ Sponsor | Production readiness validation | Project Manager | [TBD]
Post-Go-Live Support | Daily for 2 weeks | Support Team ¦ Client IT ¦ NOC | Monitor production and resolve issues | Support Lead | [TBD]
Project Retrospective | One-time at closure | All project team members | Lessons learned and best practices | Project Manager | [TBD]