## Cover
Test Plan
Generated: | November 28, 2025
Solution: | Virtual Wan Global
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Name | Description | Test Steps | Expected Results | Priority | Status
FT-001 | Virtual WAN Hub Connectivity | Verify connectivity between regional Virtual WAN hubs | 1. Deploy primary and secondary hubs 2. Configure hub-to-hub routing 3. Test connectivity from hub1 to hub2 4. Verify routing tables | Successful connectivity between all hubs with <50ms latency; routing tables correctly populated | Critical | Planned
FT-002 | Site-to-Site VPN Connection | Validate VPN connectivity from branch sites to Virtual WAN hub | 1. Configure VPN site in Virtual WAN 2. Configure on-premises VPN device 3. Establish VPN tunnel 4. Test data transfer | VPN tunnel establishes successfully; stable connection with <2% packet loss | Critical | Planned
FT-003 | ExpressRoute Integration | Test ExpressRoute circuit connectivity to Virtual WAN hub | 1. Provision ExpressRoute circuit 2. Connect circuit to Virtual WAN hub 3. Configure BGP peering 4. Verify route propagation | ExpressRoute circuit connected; BGP peers established; routes advertised correctly | Critical | Planned
FT-004 | Azure Firewall Traffic Inspection | Validate Azure Firewall inspects traffic between spokes and to internet | 1. Deploy Azure Firewall in hub 2. Configure firewall rules 3. Send test traffic 4. Review firewall logs | All traffic routed through firewall; rules applied correctly; logs captured | High | Planned
FT-005 | VNet Peering to Hub | Test virtual network connections to Virtual WAN hub | 1. Create spoke VNet 2. Connect VNet to Virtual WAN hub 3. Test connectivity from spoke to other resources 4. Verify effective routes | VNet successfully connected to hub; resources accessible across spokes via hub | High | Planned
FT-006 | Point-to-Site VPN | Validate remote user VPN connectivity | 1. Configure P2S VPN gateway 2. Generate client certificates 3. Connect remote client 4. Test access to hub resources | Remote clients connect successfully; access to hub and spoke resources functional | High | Planned
FT-007 | BGP Route Propagation | Test BGP routing between on-premises and Azure Virtual WAN | 1. Configure BGP on VPN device 2. Establish BGP peering 3. Advertise routes 4. Verify route tables in Azure | BGP peers established; routes propagated correctly; traffic uses optimal paths | High | Planned
FT-008 | Custom Route Tables | Validate custom routing policies in Virtual WAN | 1. Create custom route table 2. Define custom routes 3. Associate with connections 4. Test traffic flow | Custom routes applied successfully; traffic routed according to policy | Medium | Planned
FT-009 | Global VNet Peering | Test VNet connectivity across regions through Virtual WAN | 1. Create VNets in different regions 2. Connect to respective hubs 3. Test cross-region connectivity 4. Measure latency | Cross-region VNet communication functional; latency within acceptable range | Medium | Planned
FT-010 | DNS Resolution | Validate DNS name resolution across Virtual WAN topology | 1. Configure Azure DNS or custom DNS 2. Create DNS records 3. Test resolution from different locations 4. Verify DNS forwarding | DNS resolution functional across all connected networks; custom domains resolve correctly | Medium | Planned
FT-011 | Network Security Groups | Test NSG rules on subnets connected to Virtual WAN | 1. Configure NSG rules 2. Associate with subnets 3. Test allowed traffic 4. Test blocked traffic | NSG rules enforced correctly; allowed traffic passes; blocked traffic denied | Medium | Planned
FT-012 | Hub Gateway Scale Units | Verify gateway scaling for increased throughput | 1. Configure initial scale units 2. Generate baseline traffic 3. Increase scale units 4. Test increased capacity | Gateway scales successfully; throughput increases proportionally to scale units | Low | Planned

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Name | Description | Test Steps | Expected Results | Priority | Status
NFT-001 | Network Performance Baseline | Establish baseline performance metrics for Virtual WAN | 1. Configure monitoring tools 2. Generate typical traffic load 3. Measure latency and throughput 4. Document baseline metrics | Baseline established for latency (<50ms inter-hub) and throughput (95% of gateway capacity) | Critical | Planned
NFT-002 | VPN Gateway Throughput | Test maximum throughput capacity of VPN gateways | 1. Configure VPN connections 2. Generate maximum traffic load 3. Measure sustained throughput 4. Identify bottlenecks | VPN gateway achieves rated throughput based on scale units; no packet loss under sustained load | High | Planned
NFT-003 | ExpressRoute Throughput | Validate ExpressRoute circuit bandwidth utilization | 1. Generate traffic through ExpressRoute 2. Monitor bandwidth usage 3. Test at different traffic levels 4. Verify QoS policies | ExpressRoute utilizes full circuit bandwidth; QoS policies applied correctly | High | Planned
NFT-004 | Concurrent Connection Scalability | Test Virtual WAN with maximum number of concurrent connections | 1. Establish baseline connections 2. Gradually increase connections 3. Monitor performance 4. Identify scaling limits | Virtual WAN handles maximum concurrent connections without degradation | High | Planned
NFT-005 | Hub-to-Hub Latency | Measure latency between Virtual WAN hubs under various loads | 1. Deploy hubs in target regions 2. Generate traffic at different loads 3. Measure latency continuously 4. Compare to SLA | Inter-hub latency within SLA (<50ms for regional; <150ms for global) | High | Planned
NFT-006 | Firewall Performance Impact | Assess performance impact of Azure Firewall on traffic flow | 1. Test traffic without firewall 2. Enable firewall inspection 3. Test with firewall 4. Compare metrics | Firewall adds <10ms latency; maintains throughput within firewall capacity limits | High | Planned
NFT-007 | Failover Time | Measure time to failover between redundant paths | 1. Establish redundant connections 2. Simulate primary path failure 3. Measure failover time 4. Verify traffic continuity | Failover completes within 30 seconds; minimal packet loss during transition | Critical | Planned
NFT-008 | System Availability | Validate Virtual WAN availability meets SLA requirements | 1. Monitor uptime continuously 2. Document all outages 3. Calculate availability percentage 4. Review against SLA | Virtual WAN availability meets Azure SLA of 99.95% for hubs | Critical | Planned
NFT-009 | Monitoring and Alerting Response | Test monitoring system response time and alert delivery | 1. Configure monitoring and alerts 2. Trigger alert conditions 3. Measure detection time 4. Verify notification delivery | Alerts triggered within 5 minutes of condition; notifications delivered to all channels | High | Planned
NFT-010 | Configuration Change Impact | Assess impact of configuration changes on active connections | 1. Establish baseline connections 2. Apply configuration change 3. Monitor connection status 4. Measure disruption | Configuration changes applied without disrupting existing connections | Medium | Planned
NFT-011 | Log Analytics Query Performance | Test performance of monitoring queries on large datasets | 1. Ingest significant log volume 2. Execute common queries 3. Measure query response time 4. Optimize as needed | Queries return results within 30 seconds for 30-day data range | Medium | Planned
NFT-012 | Multi-Region Traffic Distribution | Validate traffic distribution across multi-region deployment | 1. Deploy hubs in multiple regions 2. Generate distributed traffic 3. Monitor traffic patterns 4. Verify load distribution | Traffic distributes according to routing policies; no single hub overloaded | Low | Planned

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Name | Description | Test Steps | Expected Results | Priority | Status
UAT-001 | Branch Office Connectivity | Business users validate branch office connectivity to Azure resources | 1. Connect from branch office 2. Access Azure applications 3. Test file transfers 4. Verify application performance | Branch users access Azure resources without issues; performance meets expectations | Critical | Planned
UAT-002 | Remote Worker VPN Access | Remote employees validate Point-to-Site VPN functionality | 1. Install VPN client 2. Connect to Azure 3. Access required applications 4. Perform daily work tasks | Remote workers connect successfully; access all required resources; performance acceptable | Critical | Planned
UAT-003 | Application Performance | Validate business application performance across Virtual WAN | 1. Access line-of-business applications 2. Perform typical transactions 3. Test during peak hours 4. Compare to baseline | Applications perform at or better than pre-Virtual WAN baseline; no user complaints | Critical | Planned
UAT-004 | Internet Breakout | Business users validate internet access through Azure Firewall | 1. Access internet from branch offices 2. Test various websites and services 3. Verify security policies applied 4. Assess performance | Internet access functional with security policies enforced; browsing performance acceptable | High | Planned
UAT-005 | Multi-Site Collaboration | Test collaboration tools across sites connected via Virtual WAN | 1. Initiate Teams video call across sites 2. Share files between locations 3. Test real-time collaboration 4. Assess quality | Collaboration tools work seamlessly; video quality good; file sharing fast | High | Planned
UAT-006 | Database Access Performance | Validate database connectivity and performance from branch sites | 1. Connect to Azure SQL databases 2. Execute typical queries 3. Test during business hours 4. Measure response times | Database access reliable; query performance within acceptable range; no timeouts | High | Planned
UAT-007 | Network Management Tools | IT staff validate management and monitoring capabilities | 1. Access network management consoles 2. Review network topology 3. Test monitoring dashboards 4. Create test alerts | Network management tools provide needed visibility; dashboards intuitive; alerts functional | High | Planned
UAT-008 | Security Operations | Security team validates firewall and threat detection capabilities | 1. Review firewall logs and rules 2. Test threat detection 3. Simulate security incident 4. Verify response workflows | Security tools provide adequate visibility; threat detection functional; incident response effective | High | Planned
UAT-009 | New Site Onboarding | Test process for connecting new branch site to Virtual WAN | 1. Follow onboarding procedures 2. Configure new site 3. Establish connectivity 4. Validate access | New site onboarding process clear and efficient; connectivity established within expected timeframe | Medium | Planned
UAT-010 | Incident Response Procedures | Validate network incident detection and response processes | 1. Simulate network issue 2. Follow incident response procedures 3. Test escalation 4. Measure resolution time | Incident detected promptly; procedures clear; escalation works; resolution timely | Medium | Planned
UAT-011 | Backup Path Testing | Users validate experience during primary path failover | 1. Establish normal connectivity 2. Simulate primary path failure 3. Observe failover 4. Assess user impact | Failover transparent to users or minimal disruption; connectivity restored quickly | Medium | Planned
UAT-012 | Documentation and Training | IT staff validate operational documentation completeness | 1. Review network documentation 2. Follow operational procedures 3. Test runbooks 4. Provide feedback | Documentation complete and accurate; procedures clear; runbooks effective for operations | Medium | Planned