## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Dgx Superpod
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff and Team Alignment | 2 days | Week 1 Day 1 | Week 1 Day 2 | None | Project Manager | Not Started
Discovery | AI Workload Requirements Analysis | 5 days | Week 1 Day 3 | Week 2 Day 2 | Project Kickoff | AI Lead | Not Started
Discovery | Datacenter Site Survey and Assessment | 3 days | Week 2 Day 1 | Week 2 Day 3 | Project Kickoff | Facilities Lead | Not Started
Discovery | Power and Cooling Capacity Analysis | 3 days | Week 2 Day 3 | Week 3 Day 1 | Site Survey | Infrastructure Architect | Not Started
Discovery | InfiniBand Fabric Design and Topology | 4 days | Week 3 Day 1 | Week 3 Day 4 | Requirements Analysis | Network Engineer | Not Started
Discovery | DGX SuperPOD Architecture Design | 5 days | Week 3 Day 2 | Week 4 Day 1 | Fabric Design | Solution Architect | Not Started
Discovery | Assessment Report and Implementation Plan | 3 days | Week 4 Day 1 | Week 4 Day 3 | Architecture Design | Project Manager | Not Started
Site Prep | Power Infrastructure Upgrade (500 kW) | 15 days | Week 5 Day 1 | Week 7 Day 5 | Assessment Approved | Facilities Team | Not Started
Site Prep | Cooling System Enhancement | 10 days | Week 5 Day 3 | Week 7 Day 2 | Assessment Approved | Facilities Team | Not Started
Site Prep | Rack Installation and Cable Management | 5 days | Week 7 Day 1 | Week 7 Day 5 | Power Upgrade Started | Infrastructure Team | Not Started
Site Prep | InfiniBand Cabling Installation | 5 days | Week 7 Day 3 | Week 8 Day 2 | Rack Installation | Network Team | Not Started
Site Prep | Network Infrastructure Validation | 2 days | Week 8 Day 1 | Week 8 Day 2 | IB Cabling Complete | Network Engineer | Not Started
Deployment | DGX H100 Systems Installation (8 nodes) | 10 days | Week 8 Day 3 | Week 10 Day 2 | Site Ready | Hardware Team | Not Started
Deployment | InfiniBand Switch Configuration | 5 days | Week 10 Day 1 | Week 10 Day 5 | DGX Installation | Network Engineer | Not Started
Deployment | InfiniBand Fabric Validation (RDMA) | 3 days | Week 10 Day 3 | Week 11 Day 1 | Switch Configuration | Network Engineer | Not Started
Deployment | Base Command Storage Deployment (1 PB) | 5 days | Week 10 Day 3 | Week 11 Day 2 | DGX Installation | Storage Engineer | Not Started
Deployment | DGX OS and Driver Installation | 3 days | Week 11 Day 1 | Week 11 Day 3 | IB Fabric Validated | Systems Engineer | Not Started
Deployment | NGC Catalog and Container Runtime Setup | 2 days | Week 11 Day 3 | Week 12 Day 1 | DGX OS Installed | AI Engineer | Not Started
Deployment | AI Framework Deployment (PyTorch/TF) | 3 days | Week 12 Day 1 | Week 12 Day 3 | NGC Setup | AI Engineer | Not Started
Deployment | Slurm Workload Manager Configuration | 4 days | Week 12 Day 2 | Week 12 Day 5 | AI Frameworks | Systems Engineer | Not Started
Deployment | LDAP/AD Integration and User Setup | 3 days | Week 12 Day 4 | Week 13 Day 1 | Slurm Configured | Security Engineer | Not Started
Deployment | DCGM Monitoring and Grafana Dashboards | 3 days | Week 12 Day 5 | Week 13 Day 2 | DGX OS Installed | Operations Engineer | Not Started
Testing | Multi-GPU Performance Benchmarking | 3 days | Week 13 Day 2 | Week 13 Day 4 | Full Stack Deployed | Performance Engineer | Not Started
Testing | InfiniBand Fabric Performance Validation | 2 days | Week 13 Day 3 | Week 13 Day 4 | Benchmarking Started | Network Engineer | Not Started
Testing | Storage Throughput Testing (14 GB/s) | 2 days | Week 13 Day 4 | Week 14 Day 1 | Fabric Validated | Storage Engineer | Not Started
Testing | Distributed Training Scalability Tests | 3 days | Week 13 Day 5 | Week 14 Day 2 | Performance Tests | AI Engineer | Not Started
Testing | Security and Access Control Validation | 2 days | Week 14 Day 1 | Week 14 Day 2 | User Setup Complete | Security Engineer | Not Started
Testing | User Acceptance Testing with AI Team | 3 days | Week 14 Day 2 | Week 14 Day 4 | All Tests Complete | AI Lead | Not Started
Testing | Go-Live Readiness Review | 1 day | Week 14 Day 5 | Week 14 Day 5 | UAT Complete | Project Manager | Not Started
Handover | Administrator Training Delivery | 3 days | Week 15 Day 1 | Week 15 Day 3 | Go-Live Approved | Training Lead | Not Started
Handover | Data Scientist Training Sessions | 3 days | Week 15 Day 2 | Week 15 Day 4 | Go-Live Approved | Training Lead | Not Started
Handover | Operations Runbook Validation | 2 days | Week 15 Day 3 | Week 15 Day 4 | Training Started | Operations Lead | Not Started
Handover | As-Built Documentation Delivery | 2 days | Week 15 Day 4 | Week 16 Day 1 | Runbook Validated | Solution Architect | Not Started
Handover | Knowledge Transfer Sessions | 3 days | Week 16 Day 1 | Week 16 Day 3 | Documentation Complete | Technical Lead | Not Started
Hypercare | Go-Live and Production Support | 1 day | Week 15 Day 1 | Week 15 Day 1 | Go-Live Approved | Support Team | Not Started
Hypercare | Hypercare Period (30 days) | 20 days | Week 15 Day 2 | Week 19 Day 1 | Go-Live Complete | Support Team | Not Started
Hypercare | Project Closure and Sign-off | 2 days | Week 19 Day 2 | Week 19 Day 3 | Hypercare Complete | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | Week 1 | All stakeholders attended kickoff; project charter approved; team assignments confirmed | Project Manager | Not Started
M2 | Assessment Complete | Week 4 | Site assessment report delivered; architecture design approved; implementation plan signed off | Solution Architect | Not Started
M3 | Datacenter Ready | Week 7 | 500 kW power upgrade complete; cooling enhanced; racks installed; InfiniBand cabling done | Facilities Lead | Not Started
M4 | Hardware Installed | Week 10 | 8x DGX H100 systems installed and powered on; initial connectivity validated | Hardware Lead | Not Started
M5 | InfiniBand Operational | Week 11 | Quantum-2 fabric configured; RDMA validated; <2μs latency confirmed; GPUDirect enabled | Network Engineer | Not Started
M6 | Software Stack Deployed | Week 13 | DGX OS; NGC catalog; AI frameworks; Slurm; monitoring all operational and validated | Systems Engineer | Not Started
M7 | Go-Live | Week 15 | 32 petaFLOPS validated; 14 GB/s storage throughput; UAT complete; production traffic enabled | Project Manager | Not Started
M8 | Project Closure | Week 19 | Hypercare complete; all documentation delivered; NVIDIA support transition; formal sign-off | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | SA | NE | SE | FacLead | AILead | OpLead | Client
Project Charter and Kickoff | A | C | I | I | I | C | I | C
AI Workload Requirements | A | C | I | I | I | R | I | C
Datacenter Site Assessment | A | R | C | C | R | I | I | C
DGX SuperPOD Architecture Design | A | R | C | C | C | C | I | I
Power and Cooling Upgrades | A | C | I | I | R | I | I | C
InfiniBand Fabric Design | A | C | R | I | I | I | I | I
DGX H100 Installation | A | C | I | R | C | I | I | I
InfiniBand Configuration | A | C | R | C | I | I | I | I
Base Command Storage Deployment | A | C | I | R | I | I | I | I
Software Stack Deployment | A | C | I | R | I | C | I | I
Slurm Workload Manager Setup | A | C | I | R | I | C | I | I
Performance Benchmarking | A | C | R | R | I | C | I | I
Security and Access Control | A | C | I | R | I | I | I | C
User Acceptance Testing | A | I | I | C | I | R | I | R
Administrator Training | A | R | C | C | I | I | R | C
Data Scientist Training | A | C | I | I | I | R | I | R
Operations Runbook | A | C | C | C | I | I | R | I
Knowledge Transfer | A | R | R | R | I | C | R | C
Go-Live Approval | A | C | C | C | C | C | C | R
Hypercare Support | A | C | C | R | I | I | R | I
Legend:
R | A: Responsible - Does the work
A | A: Accountable - Ultimate ownership
C | A: Consulted - Provides input
I | A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders and project team | Launch project; align on objectives and timeline | Project Manager | Week 1 Day 1
Executive Steering | Bi-weekly | Executive sponsors and PM | Strategic direction; budget approval; issue escalation | Project Manager | Alternate Tuesdays
Project Status | Weekly | Core project team | Progress review; risk tracking; issue resolution | Project Manager | Mondays 10:00 AM
Technical Review | Weekly | Solution architect and engineers | Architecture decisions; technical issues; design validation | Solution Architect | Wednesdays 2:00 PM
Facilities Coordination | Weekly | Facilities and infrastructure teams | Power/cooling progress; site readiness tracking | Facilities Lead | Tuesdays 9:00 AM
InfiniBand Fabric Review | Weekly | Network engineers and NVIDIA support | Fabric design validation; configuration issues | Network Engineer | Thursdays 11:00 AM
AI Workload Planning | Bi-weekly | AI lead and research teams | Workload requirements; training priorities; resource allocation | AI Lead | Alternate Fridays
Go-Live Readiness | Daily | Go-live team (2 weeks pre-launch) | Go-live preparation; checklist validation; risk review | Project Manager | Daily 9:00 AM
Hypercare Standup | Daily | Support team (first 2 weeks) | Production issues; performance monitoring; user feedback | Operations Lead | Daily 9:30 AM