## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Gpu Compute Cluster
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff and Stakeholder Alignment | 2 days | Week 1 Day 1 | Week 1 Day 2 | None | Project Manager | Not Started
Discovery | AI Workload Requirements Analysis | 4 days | Week 1 Day 3 | Week 2 Day 1 | Project Kickoff | Data Science Lead | Not Started
Discovery | Infrastructure Assessment and Sizing | 3 days | Week 2 Day 1 | Week 2 Day 3 | Requirements Analysis | Infrastructure Architect | Not Started
Discovery | Kubernetes Architecture Design | 4 days | Week 2 Day 3 | Week 3 Day 2 | Infrastructure Assessment | Kubernetes Architect | Not Started
Discovery | MLOps Platform Design (Kubeflow/MLflow) | 3 days | Week 3 Day 1 | Week 3 Day 3 | Kubernetes Design | MLOps Engineer | Not Started
Discovery | Assessment Report and Implementation Plan | 2 days | Week 3 Day 3 | Week 3 Day 5 | All Design Complete | Project Manager | Not Started
Infrastructure | GPU Server Installation (8x Dell R750xa) | 8 days | Week 4 Day 1 | Week 5 Day 3 | Assessment Approved | Hardware Team | Not Started
Infrastructure | 100 GbE Network Switch Deployment | 4 days | Week 5 Day 1 | Week 5 Day 4 | Server Installation Started | Network Engineer | Not Started
Infrastructure | RoCE Configuration and Validation | 3 days | Week 5 Day 4 | Week 6 Day 2 | Network Switches Deployed | Network Engineer | Not Started
Infrastructure | NetApp Storage Deployment (200 TB) | 5 days | Week 5 Day 3 | Week 6 Day 3 | Network Ready | Storage Engineer | Not Started
Infrastructure | Ubuntu 22.04 and NVIDIA Driver Install | 3 days | Week 6 Day 2 | Week 6 Day 4 | Servers Ready | Systems Engineer | Not Started
Infrastructure | GPU Validation (32x A100 40GB) | 2 days | Week 6 Day 4 | Week 7 Day 1 | Drivers Installed | GPU Engineer | Not Started
Kubernetes | Kubernetes Control Plane Deployment (3-node HA) | 3 days | Week 7 Day 1 | Week 7 Day 3 | Infrastructure Ready | Kubernetes Engineer | Not Started
Kubernetes | GPU Worker Nodes Configuration (8 nodes) | 3 days | Week 7 Day 3 | Week 8 Day 1 | Control Plane Ready | Kubernetes Engineer | Not Started
Kubernetes | NVIDIA GPU Operator Installation | 2 days | Week 8 Day 1 | Week 8 Day 2 | Worker Nodes Ready | GPU Engineer | Not Started
Kubernetes | GPU Device Plugin and Time-Slicing Config | 2 days | Week 8 Day 2 | Week 8 Day 4 | GPU Operator Installed | GPU Engineer | Not Started
Kubernetes | Container Registry and NGC Integration | 2 days | Week 8 Day 4 | Week 9 Day 1 | GPU Plugin Configured | DevOps Engineer | Not Started
Kubernetes | Storage Class and PV Provisioner Setup | 2 days | Week 9 Day 1 | Week 9 Day 2 | Storage Ready | Storage Engineer | Not Started
MLOps | Kubeflow Installation and Configuration | 4 days | Week 9 Day 2 | Week 10 Day 1 | Kubernetes Ready | MLOps Engineer | Not Started
MLOps | MLflow Deployment and Model Registry | 3 days | Week 10 Day 1 | Week 10 Day 3 | Kubeflow Ready | MLOps Engineer | Not Started
MLOps | Triton Inference Server Deployment | 3 days | Week 10 Day 3 | Week 11 Day 1 | MLflow Ready | AI Engineer | Not Started
MLOps | JupyterHub Multi-User Setup | 2 days | Week 11 Day 1 | Week 11 Day 2 | Triton Ready | DevOps Engineer | Not Started
MLOps | LDAP Integration and User Namespaces | 2 days | Week 11 Day 2 | Week 11 Day 4 | JupyterHub Ready | Security Engineer | Not Started
Testing | GPU Performance Benchmarking (32 GPUs) | 2 days | Week 11 Day 4 | Week 12 Day 1 | Full Stack Deployed | Performance Engineer | Not Started
Testing | Distributed Training Validation | 2 days | Week 12 Day 1 | Week 12 Day 3 | Benchmarks Complete | AI Engineer | Not Started
Testing | MLOps Pipeline End-to-End Testing | 2 days | Week 12 Day 3 | Week 13 Day 1 | Distributed Training OK | MLOps Engineer | Not Started
Testing | User Acceptance Testing with DS Team | 3 days | Week 13 Day 1 | Week 13 Day 3 | Pipeline Testing OK | Data Science Lead | Not Started
Testing | Security and Access Control Validation | 2 days | Week 13 Day 3 | Week 13 Day 5 | UAT Complete | Security Engineer | Not Started
Handover | Administrator Training Delivery | 2 days | Week 14 Day 1 | Week 14 Day 2 | Go-Live Approved | Training Lead | Not Started
Handover | Data Scientist Training Sessions | 3 days | Week 14 Day 2 | Week 14 Day 4 | Admin Training Done | Training Lead | Not Started
Handover | Operations Runbook Validation | 2 days | Week 14 Day 4 | Week 15 Day 1 | Training Complete | Operations Lead | Not Started
Handover | Documentation Delivery | 2 days | Week 15 Day 1 | Week 15 Day 2 | Runbook Validated | Technical Lead | Not Started
Hypercare | Go-Live and Production Support | 1 day | Week 14 Day 1 | Week 14 Day 1 | Go-Live Approved | Support Team | Not Started
Hypercare | Hypercare Period (14 days) | 10 days | Week 14 Day 2 | Week 16 Day 1 | Go-Live Complete | Support Team | Not Started
Hypercare | Project Closure and Sign-off | 2 days | Week 16 Day 2 | Week 16 Day 3 | Hypercare Complete | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | Week 1 | All stakeholders aligned; project charter approved; team assignments confirmed | Project Manager | Not Started
M2 | Assessment Complete | Week 3 | Architecture design approved; implementation plan signed off; procurement initiated | Solution Architect | Not Started
M3 | Infrastructure Ready | Week 7 | 8 servers installed; 32 GPUs validated; network and storage operational | Infrastructure Lead | Not Started
M4 | Kubernetes Operational | Week 9 | Control plane HA; GPU Operator installed; all nodes schedulable | Kubernetes Engineer | Not Started
M5 | MLOps Platform Live | Week 11 | Kubeflow; MLflow; Triton; JupyterHub all operational and validated | MLOps Lead | Not Started
M6 | Go-Live | Week 14 | All tests passing; UAT complete; 20+ users onboarded; production traffic enabled | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | SA | KE | GE | ME | SE | OpLead | Client
Project Charter and Kickoff | A | C | I | I | I | I | I | C
AI Workload Requirements | A | C | I | I | C | I | I | R
Infrastructure Architecture Design | A | R | C | C | I | C | I | I
Kubernetes Architecture Design | A | C | R | C | C | I | I | I
GPU Server Installation | A | C | I | R | I | I | I | I
Network Deployment (100 GbE) | A | C | I | I | I | R | I | I
Kubernetes Cluster Deployment | A | C | R | C | I | I | I | I
NVIDIA GPU Operator Setup | A | C | C | R | I | I | I | I
Kubeflow Installation | A | C | C | I | R | I | I | I
MLflow Deployment | A | C | I | I | R | I | I | I
Triton Inference Server | A | C | I | C | R | I | I | I
Performance Benchmarking | A | C | I | R | C | I | I | I
User Acceptance Testing | A | I | C | I | C | I | I | R
Administrator Training | A | R | C | C | C | I | R | C
Data Scientist Training | A | C | I | I | R | I | I | R
Operations Runbook | A | C | C | C | C | I | R | I
Go-Live Approval | A | C | C | C | C | C | C | R
Hypercare Support | A | C | C | R | R | I | R | I
Legend:
R | A: Responsible - Does the work
A | A: Accountable - Ultimate ownership
C | A: Consulted - Provides input
I | A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders and project team | Launch project; align on objectives and timeline | Project Manager | Week 1 Day 1
Executive Steering | Bi-weekly | Executive sponsors and PM | Strategic direction; budget approval; issue escalation | Project Manager | Alternate Tuesdays
Project Status | Weekly | Core project team | Progress review; risk tracking; issue resolution | Project Manager | Mondays 10:00 AM
Technical Review | Weekly | Architects and engineers | Architecture decisions; technical issues; integration | Solution Architect | Wednesdays 2:00 PM
Data Science Sync | Bi-weekly | Data science leads and MLOps team | Workload requirements; user feedback; training needs | Data Science Lead | Alternate Fridays
Kubernetes Planning | Weekly | Kubernetes and GPU engineers | Platform configuration; scheduling optimization | Kubernetes Engineer | Thursdays 11:00 AM
Go-Live Readiness | Daily | Go-live team (2 weeks pre-launch) | Go-live preparation; checklist validation; risk review | Project Manager | Daily 9:00 AM
Hypercare Standup | Daily | Support team (first week) | Production issues; user feedback; optimization | Operations Lead | Daily 9:30 AM