## Cover
Project Plan
Generated: | November 28, 2025
Solution: | Omniverse Enterprise
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | Project Manager | Not Started
Discovery | 3D Workflow Analysis & Collaboration Requirements | 5 days | [START_DATE+1] | [START_DATE+6] | Project Kickoff | Business Analyst | Not Started
Discovery | CAD Tool Inventory & Connector Requirements | 5 days | [START_DATE+3] | [START_DATE+8] | Project Kickoff | Solution Architect | Not Started
Discovery | Network & Infrastructure Assessment | 5 days | [START_DATE+5] | [START_DATE+10] | Workflow Analysis | Network Architect | Not Started
Discovery | Sample USD Scene Collection & Validation | 4 days | [START_DATE+6] | [START_DATE+10] | Workflow Analysis | Design Lead | Not Started
Planning | Omniverse Architecture Design | 7 days | [START_DATE+10] | [START_DATE+17] | CAD Assessment | Solution Architect | Not Started
Planning | Nucleus HA & Storage Design | 5 days | [START_DATE+12] | [START_DATE+17] | Architecture Design | Infrastructure Lead | Not Started
Planning | Security Architecture & AD Integration Design | 5 days | [START_DATE+14] | [START_DATE+19] | Architecture Design | Security Architect | Not Started
Planning | Workstation Deployment & Imaging Strategy | 4 days | [START_DATE+15] | [START_DATE+19] | Architecture Design | Desktop Engineer | Not Started
Build | Nucleus Server Infrastructure Deployment | 7 days | [START_DATE+19] | [START_DATE+26] | Infrastructure Planning | DevOps Engineer | Not Started
Build | NetApp Storage Configuration & NFS Exports | 4 days | [START_DATE+22] | [START_DATE+26] | Infrastructure Deployment | Storage Engineer | Not Started
Build | Network Infrastructure & VLAN Configuration | 6 days | [START_DATE+20] | [START_DATE+26] | Infrastructure Deployment | Network Engineer | Not Started
Build | Nucleus Server Software Installation | 5 days | [START_DATE+26] | [START_DATE+31] | Storage Configuration | System Administrator | Not Started
Build | Nucleus HA Configuration & Failover Setup | 4 days | [START_DATE+31] | [START_DATE+35] | Nucleus Installation | System Administrator | Not Started
Build | Pilot Workstation Deployment (10 workstations) | 7 days | [START_DATE+35] | [START_DATE+42] | Nucleus HA Setup | Desktop Engineer | Not Started
Build | Autodesk Revit Connector Installation | 3 days | [START_DATE+42] | [START_DATE+45] | Pilot Workstations | Integration Engineer | Not Started
Build | SolidWorks Connector Installation | 3 days | [START_DATE+44] | [START_DATE+47] | Revit Connector | Integration Engineer | Not Started
Build | Rhino Connector Installation | 3 days | [START_DATE+46] | [START_DATE+49] | SolidWorks Connector | Integration Engineer | Not Started
Build | Blender & Maya Connector Installation | 4 days | [START_DATE+48] | [START_DATE+52] | Rhino Connector | Integration Engineer | Not Started
Build | Active Directory Integration & SSO | 5 days | [START_DATE+45] | [START_DATE+50] | Nucleus HA Setup | Security Engineer | Not Started
Build | Monitoring Infrastructure (Prometheus/Grafana) | 5 days | [START_DATE+50] | [START_DATE+55] | AD Integration | DevOps Engineer | Not Started
Build | Full Workstation Deployment (40 remaining) | 10 days | [START_DATE+52] | [START_DATE+62] | Pilot Validation | Desktop Engineer | Not Started
Test | Unit Testing - Nucleus Functionality | 5 days | [START_DATE+55] | [START_DATE+60] | Monitoring Setup | QA Engineer | Not Started
Test | Connector Integration Testing | 7 days | [START_DATE+55] | [START_DATE+62] | All Connectors | Integration Engineer | Not Started
Test | Multi-User Collaboration Testing | 5 days | [START_DATE+62] | [START_DATE+67] | Integration Testing | QA Engineer | Not Started
Test | Performance & Rendering Benchmarks | 5 days | [START_DATE+65] | [START_DATE+70] | Collaboration Testing | Performance Engineer | Not Started
Test | Security Testing & Access Control Validation | 5 days | [START_DATE+67] | [START_DATE+72] | Collaboration Testing | Security Engineer | Not Started
Test | User Acceptance Testing with Design Teams | 7 days | [START_DATE+70] | [START_DATE+77] | Performance Testing | Design Lead | Not Started
Deploy | Production Environment Validation | 3 days | [START_DATE+75] | [START_DATE+78] | Security Testing | QA Lead | Not Started
Deploy | User Training Delivery (50 designers) | 7 days | [START_DATE+73] | [START_DATE+80] | UAT Complete | Training Lead | Not Started
Deploy | Go-Live | 2 days | [START_DATE+80] | [START_DATE+82] | Production Validation | Project Manager | Not Started
Closure | Hypercare Support | 30 days | [START_DATE+82] | [START_DATE+112] | Go-Live | Support Team | Not Started
Closure | Knowledge Transfer & Documentation | 7 days | [START_DATE+85] | [START_DATE+92] | Go-Live | Project Manager | Not Started
Closure | Project Closure & Lessons Learned | 3 days | [START_DATE+112] | [START_DATE+115] | Hypercare Complete | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | [START_DATE] | Stakeholders aligned; project charter approved; Nucleus server access confirmed | Project Manager | Not Started
M2 | Discovery Complete | [START_DATE+10] | CAD tools inventoried (5 connectors); 3D workflows documented; sample USD scenes collected | Business Analyst | Not Started
M3 | Architecture Approved | [START_DATE+19] | Omniverse architecture approved; Nucleus HA design signed off; security design validated | Solution Architect | Not Started
M4 | Infrastructure Ready | [START_DATE+35] | Nucleus servers deployed (2x HA); storage configured (100 TB); network fabric operational | DevOps Engineer | Not Started
M5 | Connectors Integrated | [START_DATE+52] | All 5 CAD connectors validated (Revit/SolidWorks/Rhino/Blender/Maya); USD workflows tested | Integration Engineer | Not Started
M6 | Workstations Deployed | [START_DATE+62] | 50 RTX workstations deployed; all users configured in AD; Omniverse client installed | Desktop Engineer | Not Started
M7 | Testing Complete | [START_DATE+77] | All test phases passed; rendering <60 minutes; 10+ concurrent users validated; no critical defects | QA Lead | Not Started
M8 | Go-Live | [START_DATE+82] | Production deployment successful; 50 designers trained; monitoring active | Project Manager | Not Started
M9 | Project Closure | [START_DATE+115] | Hypercare complete; knowledge transfer done; lessons learned documented | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | SA | BA | TL | Dev | QA | DevOps | SecArch | Client
Project Charter & Kickoff | A | C | C | I | I | I | I | I | C
3D Workflow Requirements | A | C | R | C | I | I | I | I | C
CAD Tool & Connector Assessment | A | R | C | C | I | I | C | C | I
Solution Architecture Design | A | R | C | C | C | I | C | C | I
Security & AD Integration Design | A | C | I | C | I | I | I | R | C
Infrastructure Provisioning | A | C | I | C | I | I | R | C | I
Sample USD Scene Collection | A | I | R | I | I | I | I | I | C
Nucleus Server Deployment | A | C | I | R | C | I | C | I | I
Storage & Network Configuration | A | C | I | R | C | I | R | I | I
RTX Workstation Deployment | A | I | I | R | R | I | C | I | C
CAD Connector Integration | A | C | C | R | R | I | I | I | C
Active Directory Integration | A | I | I | C | C | I | I | R | C
Test Planning & Execution | A | I | C | C | C | R | I | C | I
Collaboration Validation | A | C | C | R | C | C | I | I | C
Security Testing | A | I | I | C | I | C | I | R | I
User Acceptance Testing | A | I | C | I | I | C | I | I | R
Production Deployment | A | C | I | C | C | C | R | C | I
Designer Training | A | I | R | I | I | I | I | I | C
Go-Live Approval | A | C | C | C | C | C | C | C | R
Hypercare Support | A | I | I | C | C | C | R | I | I
Legend:
R | A: Responsible - Does the work
A | A: Accountable - Ultimate ownership
C | A: Consulted - Provides input
I | A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on Omniverse objectives and collaboration strategy | Project Manager | Day 1
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic direction and major decisions on platform implementation | Project Manager | Alternate Tuesdays
Project Status Meeting | Weekly | Core project team | Review progress and address blockers across all workstreams | Project Manager | Mondays 10:00
Technical Architecture Review | Weekly | Technical leads | Nucleus design decisions and CAD integration challenges | Solution Architect | Wednesdays 14:00
Infrastructure Standup | Daily | Infrastructure and DevOps team | Deployment progress and coordination | Technical Lead | Daily 09:30
Risk & Issue Review | Bi-weekly | PM and Risk Manager | Risk assessment and mitigation tracking | Risk Manager | Alternate Fridays
QA & Testing Review | Weekly | QA and Integration teams | Test progress and connector validation metrics | QA Lead | Thursdays 11:00
Security Review | Bi-weekly | Security team and architects | Security controls and AD integration validation | Security Architect | Alternate Wednesdays
Design Team Feedback | Weekly | Design stakeholders and pilot users | USD workflow validation and user experience feedback | Business Analyst | Fridays 14:00
Go-Live Readiness | Daily (2 weeks pre) | Go-live team | Deployment preparation and checklist review | Project Manager | Daily 09:00
Post Go-Live Review | Weekly (first month) | Support and operations | Production stability and collaboration performance monitoring | Support Lead | Mondays 11:00