# Statement of Work

Cisco Systems - Cisco ISE Secure Network Access

| Client: | [Client Name] |
| --- | --- |
| Date: | [Month DD] |
| Consulting Company: | [Consulting Company Name] |
| Submitted By: | [Contact Name ¦ Email ¦ Phone] |
| Opportunity No: | [OPP-YYYY-###] |
| Version: | [1.0] |

# Table of Contents

1 Introduction
    1.1 Purpose
        1.1.1 Scope
2 Table Content
3 Image Section
4 Additional Content
5 Sign-Off

# List of Figures

Figure 1: Sample Architecture Diagram

# List of Tables

Table 1: Sample Deliverables Table

# 1 Executive Summary

This Statement of Work (SOW) defines the scope, deliverables, roles, and terms for the Cisco ISE Secure Network Access project for [Client Name]. This engagement will deliver a zero-trust network access solution with 802.1X authentication, TrustSec micro-segmentation, and BYOD support, reducing unauthorized access by 90% and eliminating 70% of helpdesk tickets through self-service provisioning.

Project Duration: 16 weeks

# 2 Background & Objectives

## 2.1 Current State

[Client Name] currently operates a network without centralized authentication and authorization. Key challenges include:

• Unauthorized Access: No authentication required for wired network access creating security risk

• No Visibility: Unable to identify who is connecting what device where and when

• Manual BYOD Provisioning: Helpdesk manually provisions certificates for iOS and Android devices

• Compliance Gaps: Difficulty meeting PCI DSS and HIPAA requirements for network access control

• Lateral Threat Movement: No segmentation allowing malware to spread across network

## 2.2 Business Objectives

• Eliminate Unauthorized Access: Deploy 802.1X authentication achieving 100% device authentication compliance

• Enable Zero Trust: Implement TrustSec micro-segmentation reducing lateral threat movement by 85%

• Automate BYOD: Self-service onboarding reducing helpdesk tickets by 70% and provisioning time to 5 minutes

• Achieve Compliance: Complete audit trails and access control meeting PCI DSS and HIPAA requirements

• Improve Visibility: Real-time visibility into all connected devices with profiling and classification

• Reduce Security Incidents: 90% reduction in network security breaches through mandatory authentication

## 2.3 Success Metrics

• 100% device authentication compliance (wired and wireless)

• 90% reduction in unauthorized access incidents

• 70% reduction in BYOD helpdesk tickets

• ROI realization within 24 months

• Complete who/what/when/where audit trail for compliance

# 3 Scope of Work

## 3.1 In Scope

• Network assessment for 802.1X readiness (switches and WLCs)

• ISE appliance deployment (primary + secondary HA)

• Active Directory integration with LDAP

• Authentication and authorization policy framework design

• 802.1X wired and wireless deployment

• BYOD self-service portal for iOS and Android

• Guest portal with sponsor-based workflow

• TrustSec security group tag (SGT) design and deployment

• Network infrastructure integration (switches and WLCs)

• Lab validation and pilot with IT department (50-100 users)

• Phased production rollout (wired → wireless → BYOD → guest)

• Team training (40 hours) for administrators and helpdesk

• 4-week hypercare support period

### 3.1.1 Scope Parameters

This engagement is sized based on the following parameters:

| Category | Parameter | Scope |
| --- | --- | --- |
| Solution Scope | Primary Features/Capabilities | ISE for 1000 users 2000 devices |
| Solution Scope | Customization Level | Standard ISE deployment |
| Integration | External System Integrations | 2 systems (AD + switches) |
| Integration | Data Sources | User identity only |
| User Base | Total Users | 1000 employees and guests |
| User Base | User Roles | 2 roles (employee + guest) |
| Data Volume | Data Processing Volume | 2000 endpoint authentications |
| Data Volume | Data Storage Requirements | 100 GB (90-day logs) |
| Technical Environment | Deployment Regions | Single site |
| Technical Environment | Availability Requirements | Standard (99.5%) |
| Technical Environment | Infrastructure Complexity | Basic campus network |
| Security & Compliance | Security Requirements | Basic 802.1X authentication |
| Security & Compliance | Compliance Frameworks | Basic logging |
| Performance | Performance Requirements | Standard authentication speed |
| Environment | Deployment Environments | Production only |

Table 1: Engagement Scope Parameters

Table: Engagement Scope Parameters

Note: Changes to these parameters may require scope adjustment and additional investment.

## 3.2 Out of Scope

These items are not in scope unless added via change control:

• Hardware procurement beyond ISE 3615 appliances

• Network switch or wireless controller upgrades

• Certificate authority (CA) deployment (client-provided)

• Mobile Device Management (MDM) integration

• Posture assessment and compliance scanning (optional add-on)

• NAC for IoT devices beyond basic MAB (optional add-on)

• Managed services post-hypercare period

## 3.3 Activities

### 3.3.1 Phase 1 – Foundation (Weeks 1-4)

Network infrastructure is assessed and ISE foundation deployed.

Key activities:

• Network assessment for 802.1X readiness and switch/WLC compatibility

• ISE appliance deployment (primary + secondary HA configuration)

• Active Directory integration with LDAP and identity source setup

• Security requirements gathering and policy framework design

• BYOD and guest access requirements definition

Deliverable: Network Assessment Report and ISE Architecture Design

### 3.3.2 Phase 2 – Policy Development (Weeks 5-8)

Authentication, authorization, and TrustSec policies are configured.

Key activities:

• Authentication and authorization policy framework implementation

• 802.1X wired and wireless configuration with fallback MAB

• BYOD self-service portal configuration for iOS and Android

• Guest portal setup with sponsor workflow and approval process

• Lab validation with end-to-end authentication testing

Deliverable: Policy Configuration Guide and Lab Test Results

### 3.3.3 Phase 3 – TrustSec & Integration (Weeks 9-12)

TrustSec segmentation is deployed and network infrastructure integrated.

Key activities:

• TrustSec security group tag (SGT) design and matrix configuration

• Network infrastructure integration (switches and WLCs configured for 802.1X)

• Pilot deployment with IT department (50-100 users) for validation

• BYOD testing with iOS and Android devices

• Failover testing for ISE HA validation

Deliverable: TrustSec Configuration and Pilot Results Report

### 3.3.4 Phase 4 – Deployment (Weeks 13-16)

Production rollout in phased waves with training and support.

Key activities:

• Production rollout Phase 1: Wired 802.1X deployment (60 hours)

• Production rollout Phase 2: Wireless 802.1X and BYOD (50 hours)

• Guest WiFi enablement with portal and sponsor workflows (24 hours)

• TrustSec policy enforcement activation (40 hours)

• Team training (40 hours) for administrators and helpdesk

• Hypercare support activation (60 hours over 4 weeks)

Deliverable: As-Built Documentation and Operational Runbooks

# 4 Deliverables & Timeline

## 4.1 Deliverables

| # | Deliverable | Type | Due Date | Acceptance By |
| --- | --- | --- | --- | --- |
| 1 | Network Assessment Report | Document | Week 4 | Client IT Lead |
| 2 | Policy Configuration Guide | Document | Week 8 | Security Lead |
| 3 | Pilot Results Report | Document | Week 12 | Network Lead |
| 4 | As-Built Documentation | Document | Week 16 | Client IT Lead |
| 5 | Training Materials | Document | Week 16 | IT Team |

Table 2: Project Deliverables and Acceptance Criteria

## 4.2 Project Milestones

| Milestone | Description | Target Date |
| --- | --- | --- |
| M1 - Foundation Complete | ISE HA deployed with AD integration | Week 4 |
| M2 - Policies Configured | 802.1X and BYOD policies operational | Week 8 |
| M3 - Pilot Success | IT department authenticated via 802.1X | Week 12 |
| M4 - Go-Live | All users authenticated with TrustSec enabled | Week 16 |
| Hypercare End | Support period complete | Week 20 |

Table 3: Project Milestones and Timeline

# 5 Roles & Responsibilities

## 5.1 RACI Matrix

| Task/Role | EO PM | EO Quarterback | EO ISE Eng | EO Security | Client Net | Client Sec | SME |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Discovery & Requirements | A | R | R | C | C | C | C |
| ISE Deployment | C | A | R | C | C | I | I |
| Policy Configuration | C | A | R | R | C | C | I |
| Network Integration | C | R | A | C | A | I | I |
| TrustSec Configuration | C | R | R | A | I | A | I |
| Testing & Validation | R | R | C | R | A | C | I |
| Knowledge Transfer | A | R | R | C | C | I | I |

Table 4: Roles And Responsibilities

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

## 5.2 Key Personnel

Vendor Team:

• EO Project Manager: Overall delivery accountability

• EO Quarterback: Technical design and architecture oversight

• EO ISE Engineer: ISE deployment and policy configuration

• EO Security Engineer: TrustSec and security policy design

Client Team:

• Network Lead: Primary technical contact and switch configuration

• Security Lead: Security policy approval and compliance

• Helpdesk Manager: User support and BYOD workflow training

• Operations Team: Day-to-day authentication operations

# 6 Architecture & Design

## 6.1 Architecture Overview

Figure 1: Solution Architecture

Figure 1: ISE Secure Network Access Architecture - Zero-trust authentication and micro-segmentation

The proposed architecture provides centralized network access control with zero-trust principles. Key components include:

• Identity Platform: Cisco ISE 3615 appliances (primary + secondary HA)

• Identity Source: Active Directory integration with LDAP

• Enforcement Points: Catalyst switches and wireless LAN controllers

• User Access: 802.1X for corporate, BYOD self-service, guest portal

## 6.2 Architecture Type

This solution follows a Policy Service Node (PSN) architecture pattern. Key characteristics:

• Deployment Model: Distributed PSN nodes with centralized policy administration

• High Availability: Primary and secondary nodes with automatic failover

• Authentication Flow: RADIUS-based with CoA for dynamic policy enforcement

• Segmentation: TrustSec security group tags (SGT) for micro-segmentation

The architecture supports 1000 users and 2000 endpoints with scalability to 3000+ users.

## 6.3 Technical Implementation Strategy

The deployment follows a phased rollout approach:

Pilot Phase (Week 12):

• Deploy 802.1X to IT department (50-100 users)

• Validate authentication workflow and troubleshoot issues

• Refine policies based on pilot feedback

Production Phases (Weeks 13-16):

• Phase 1: Wired 802.1X deployment to all corporate users

• Phase 2: Wireless 802.1X and BYOD enablement

• Phase 3: Guest WiFi portal and sponsor workflow

• Phase 4: TrustSec enforcement with security group policies

Change Management:

• Communicate rollout schedule to users

• Helpdesk training before each phase

• Monitor authentication success rates

• Rapid response to authentication failures

# 7 Security & Compliance

## 7.1 Identity & Access Management

• 802.1X authentication with EAP-TLS or PEAP-MSCHAPv2

• Active Directory integration for centralized identity

• Multi-factor authentication (MFA) for administrative access to ISE

• Role-based access control (RBAC) for ISE administrators

## 7.2 Authentication Methods

• 802.1X (EAP): Corporate users and domain-joined devices

• MAC Authentication Bypass (MAB): Printers, IoT devices, legacy systems

• Guest Authentication: Portal-based with sponsor approval workflow

• BYOD: Self-service certificate provisioning for iOS and Android

## 7.3 TrustSec Micro-Segmentation

• Security Group Tags (SGT) for dynamic device classification

• Policy matrix for group-based access control

• Inline tagging on switches and enforcement at network edge

• Scalable segmentation without VLANs

## 7.4 Compliance & Auditing

• Complete audit trail (who, what device, when, where)

• Authentication success/failure logging

• Policy change tracking and approval workflows

• Compliance reporting for PCI DSS and HIPAA

# 8 Testing & Validation

## 8.1 Functional Validation

Comprehensive testing ensures authentication works correctly:

Authentication Testing:

• 802.1X wired authentication (domain computers)

• 802.1X wireless authentication (corporate SSID)

• MAB for printers and IoT devices

• Guest portal authentication and sponsor approval

• BYOD certificate provisioning for iOS and Android

Policy Testing:

• Authorization policies (VLANs, ACLs, SGTs)

• Fallback policies (MAB for non-supplicant devices)

• Failed authentication handling

• Session timeout and re-authentication

## 8.2 Security Testing

Security validation for zero-trust compliance:

Vulnerability Assessment:

• ISE appliance security hardening verification

• Certificate validation and expiration monitoring

• Encrypted RADIUS communication (EAP-TLS)

Compliance Validation:

• Audit logging completeness

• Access control verification

• Authentication success rate monitoring

## 8.3 User Acceptance Testing (UAT)

UAT performed with pilot users:

UAT Approach:

• IT department pilot (50-100 users)

• Corporate device authentication testing

• BYOD onboarding workflow validation

• Guest access workflow testing

Acceptance Criteria:

• Authentication success rate > 95%

• BYOD onboarding < 5 minutes

• Guest portal workflow functional

• Helpdesk can troubleshoot authentication issues

# 9 Handover & Support

## 9.1 Handover Artifacts

Upon successful implementation:

Documentation Deliverables:

• As-built architecture diagrams

• ISE configuration documentation

• Policy framework and authorization rules

• Network infrastructure 802.1X configuration

• TrustSec SGT matrix and policy documentation

Operational Deliverables:

• Operations runbooks for daily tasks

• Troubleshooting guides for authentication failures

• BYOD onboarding user guide

• Guest portal administration guide

• Helpdesk escalation procedures

Knowledge Assets:

• Recorded training sessions (40 hours)

• ISE administrator credentials

• Certificate templates and provisioning workflows

• Vendor support contacts

## 9.2 Knowledge Transfer

Training Sessions:

• 24 hours for ISE administrators

• 16 hours for helpdesk staff

• ISE operations and monitoring

• Policy management and troubleshooting

• BYOD and guest portal administration

• Authentication failure diagnosis

Documentation Package:

• As-built architecture documentation

• Configuration management guide

• Operational runbooks and SOPs

• Troubleshooting guide

• User guides for BYOD and guest access

## 9.3 Hypercare Support

Duration: 4 weeks post-go-live

Coverage:

• Business hours support (8 AM - 6 PM local time)

• 4-hour response time for critical issues

• Daily check-ins (first 2 weeks)

• Weekly status meetings

Scope:

• Authentication issue investigation

• Policy adjustments and fine-tuning

• BYOD and guest portal optimization

• Knowledge transfer continuation

## 9.4 Assumptions

### 9.4.1 General Assumptions

Client Responsibilities:

• Client will provide access to switches and wireless LAN controllers

• Client network team available for 802.1X configuration

• Client Active Directory team available for LDAP integration

• Client will handle internal communication and change management

Technical Environment:

• Network switches support 802.1X and RADIUS authentication

• Wireless LAN controllers support 802.1X and dynamic VLAN assignment

• Active Directory operational with user accounts and OUs defined

• Data center rack space and power available for ISE appliances

Project Execution:

• Project scope and requirements remain stable

• Resources available per project plan

• No major network changes during pilot and rollout

• Security and compliance approvals timely

# 10 Investment Summary

## 10.1 Total Investment

| Cost Category | Year 1 List | AWS/Partner Credits | Year 1 Net | Year 2 | Year 3 | 3-Year Total |
| --- | --- | --- | --- | --- | --- | --- |
| Professional Services | $82,200 | $0 | $82,200 | $0 | $0 | $82,200 |
| Hardware | $80,000 | $0 | $80,000 | $0 | $0 | $80,000 |
| Software | $75,000 | ($10,000) | $65,000 | $75,000 | $75,000 | $215,000 |
| Support | $31,000 | $0 | $31,000 | $31,000 | $31,000 | $93,000 |
| TOTAL INVESTMENT | $268,200 | ($10,000) | $258,200 | $106,000 | $106,000 | $470,200 |

Table 5: Total Investment Summary

## 10.2 Partner Credits

Year 1 Credits Applied: $10,000 (ISE license promotion - 20% discount)

Annual Recurring Cost: $106,000/year (software licenses and support)

## 10.3 Payment Terms

Pricing Model: Fixed price with milestone-based payments

Payment Schedule:

• 30% upon SOW execution and project kickoff ($24,660)

• 30% upon completion of Phase 2 - Policies Configured ($24,660)

• 25% upon completion of Phase 3 - Pilot Success ($20,550)

• 15% upon successful go-live and project acceptance ($12,330)

Invoicing: Monthly invoicing based on milestones completed. Net 30 payment terms.

# 11 Terms & Conditions

## 11.1 General Terms

All services will be delivered in accordance with the executed Master Services Agreement (MSA) between Vendor and Client.

## 11.2 Scope Changes

Any changes to scope, schedule, or cost require a formal Change Request approved by both parties.

## 11.3 Intellectual Property

• Client retains ownership of all deliverables and configurations

• Vendor retains proprietary methodologies and tools

• Pre-existing IP remains with original owner

## 11.4 Confidentiality

• All artifacts under NDA protection

• Client data handled per security requirements

• No disclosure to third parties without consent

# 12 Sign-Off

By signing below, both parties agree to the scope, approach, and terms outlined in this Statement of Work.

| CLIENT | CONSULTING COMPANY |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Title: ___________________________ | Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

eoframework.org