## Cover
Project Plan
Generated: | November 27, 2025
Solution: | Precision Ai Workstation
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Planning | Project Kickoff | 1 day | Week 1 Day 1 | Week 1 Day 1 | None | Project Manager | Not Started
Planning | Data Center Assessment | 2 days | Week 1 Day 1 | Week 1 Day 2 | Project Kickoff | Infrastructure Architect | Not Started
Planning | Power and Cooling Validation | 2 days | Week 1 Day 2 | Week 1 Day 3 | Data Center Assessment | Facilities Team | Not Started
Planning | Network Infrastructure Review | 2 days | Week 1 Day 2 | Week 1 Day 3 | Data Center Assessment | Network Engineer | Not Started
Planning | Hardware Specifications Finalize | 2 days | Week 1 Day 3 | Week 1 Day 4 | All Assessments | Solutions Architect | Not Started
Planning | Dell Purchase Order Submission | 1 day | Week 1 Day 5 | Week 1 Day 5 | Hardware Specs Approved | Procurement | Not Started
Planning | PowerScale NAS Configuration Design | 3 days | Week 1 Day 3 | Week 2 Day 1 | Network Review | Storage Architect | Not Started
Planning | Data Center Preparation | 5 days | Week 1 Day 5 | Week 2 Day 5 | PO Submitted | Facilities Team | Not Started
Deployment | Hardware Delivery and Inventory | 1 day | Week 3 Day 1 | Week 3 Day 1 | Dell Delivery | IT Team | Not Started
Deployment | Dell ProDeploy Installation | 3 days | Week 3 Day 1 | Week 3 Day 3 | Hardware Delivery | Dell ProDeploy | Not Started
Deployment | Network Cabling and VLAN Config | 2 days | Week 3 Day 2 | Week 3 Day 3 | ProDeploy Start | Network Engineer | Not Started
Deployment | Ubuntu 22.04 LTS Installation | 2 days | Week 3 Day 4 | Week 3 Day 5 | ProDeploy Complete | Systems Engineer | Not Started
Deployment | NVIDIA Driver Installation | 2 days | Week 3 Day 5 | Week 4 Day 1 | Ubuntu Installed | Systems Engineer | Not Started
Deployment | CUDA and cuDNN Configuration | 2 days | Week 4 Day 1 | Week 4 Day 2 | NVIDIA Drivers | ML Engineer | Not Started
Deployment | PowerScale NAS Configuration | 2 days | Week 4 Day 1 | Week 4 Day 2 | Network Complete | Storage Engineer | Not Started
Deployment | NFS Mount Configuration | 1 day | Week 4 Day 3 | Week 4 Day 3 | PowerScale Ready | Systems Engineer | Not Started
Deployment | ML Framework Installation | 2 days | Week 4 Day 3 | Week 4 Day 4 | CUDA Complete | ML Engineer | Not Started
Deployment | Datadog Monitoring Setup | 2 days | Week 4 Day 4 | Week 4 Day 5 | All Systems | DevOps Engineer | Not Started
Validation | GPU Performance Benchmarking | 2 days | Week 5 Day 1 | Week 5 Day 2 | All Deployment | ML Engineer | Not Started
Validation | Storage Throughput Validation | 1 day | Week 5 Day 2 | Week 5 Day 2 | Benchmarking Start | Storage Engineer | Not Started
Validation | End-to-End Training Test | 2 days | Week 5 Day 3 | Week 5 Day 4 | All Benchmarks | Data Scientist | Not Started
Validation | Dataset Migration from Cloud | 3 days | Week 5 Day 2 | Week 5 Day 4 | Storage Validated | Data Engineer | Not Started
Training | Data Scientist Workshop Day 1 | 1 day | Week 5 Day 4 | Week 5 Day 4 | E2E Test Complete | Training Lead | Not Started
Training | Data Scientist Workshop Day 2 | 1 day | Week 5 Day 5 | Week 5 Day 5 | Workshop Day 1 | Training Lead | Not Started
Training | Administrator Training | 1 day | Week 6 Day 1 | Week 6 Day 1 | Workshop Complete | Training Lead | Not Started
Closure | Production Go-Live | 1 day | Week 6 Day 2 | Week 6 Day 2 | All Training | Project Manager | Not Started
Closure | Documentation Finalization | 2 days | Week 6 Day 2 | Week 6 Day 3 | Go-Live | Technical Writer | Not Started
Closure | Project Acceptance Sign-off | 1 day | Week 6 Day 4 | Week 6 Day 4 | Documentation | Project Manager | Not Started
Closure | Hypercare Handover | 1 day | Week 6 Day 5 | Week 6 Day 5 | Acceptance | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Hardware Ordered | Week 2 | Dell purchase order submitted and confirmed; delivery date scheduled | Project Manager | Not Started
M2 | Hardware Delivered | Week 3 | All 10 workstations and PowerScale NAS delivered and inventoried | IT Lead | Not Started
M3 | Infrastructure Ready | Week 4 | All workstations operational with Ubuntu CUDA and ML frameworks | Solutions Architect | Not Started
M4 | Validation Complete | Week 5 | GPU benchmarks passed; storage throughput validated; E2E training successful | ML Engineer | Not Started
M5 | Training Complete | Week 6 | All data scientists and administrators trained and certified competent | Training Lead | Not Started
M6 | Project Closure | Week 6 | Production go-live complete; documentation accepted; support transitioned | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | SA | Infra | NetEng | MLEng | DS Lead | IT | Client
Project Charter and Kickoff | A | C | C | I | I | I | C | I
Data Center Assessment | A | C | R | C | I | I | C | C
Hardware Specifications | A | R | C | C | C | C | I | I
Dell Procurement | A | C | I | I | I | I | R | C
Ubuntu and NVIDIA Installation | A | C | R | I | C | I | C | I
CUDA and ML Framework Setup | A | C | C | I | R | C | I | I
PowerScale NAS Configuration | A | C | R | C | I | I | C | I
Network and VLAN Configuration | A | C | C | R | I | I | C | I
GPU Performance Validation | A | C | I | I | R | C | I | I
Data Scientist Training | A | I | I | I | R | C | I | C
Administrator Training | A | I | R | C | C | I | C | C
Production Go-Live Approval | A | C | C | C | C | C | C | R
Documentation Delivery | A | R | C | C | C | C | C | I
Legend:
R | A: Responsible - Does the work
A | A: Accountable - Ultimate ownership
C | A: Consulted - Provides input
I | A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders PM SA IT Lead DS Lead | Launch project and align on objectives and timeline | Project Manager | Week 1 Day 1
Steering Committee | Weekly | Executive sponsors PM IT Director | Strategic direction budget updates and issue escalation | Project Manager | Fridays 10:00
Daily Standup | Daily | Core project team | Review progress blockers and daily priorities | Project Manager | Daily 09:00
Technical Review | Weekly | SA Infrastructure Network ML Engineers | Technical design decisions and implementation issues | Solutions Architect | Wednesdays 14:00
Deployment Checkpoint | Daily | Deployment team Dell ProDeploy | Hardware installation and configuration progress | IT Lead | Daily 11:00
Validation Review | Daily | ML Engineer DS Lead QA | Benchmark results and validation testing progress | ML Engineer | Week 5 Daily
Training Coordination | Weekly | Training Lead DS Lead IT Lead | Training schedule logistics and materials review | Training Lead | Mondays 15:00
Go-Live Readiness | Daily | All stakeholders | Go-live preparation checklist and readiness assessment | Project Manager | Week 6 Daily 09:00