## Cover
Project Plan
Generated: | November 27, 2025
Solution: | Landing Zone
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Planning | Project Kickoff and Stakeholder Alignment | 2 days | Week 1 Day 1 | Week 1 Day 2 | None | Project Manager | Not Started
Planning | Requirements Gathering and Validation | 3 days | Week 1 Day 2 | Week 1 Day 5 | Project Kickoff | GCP Architect | Not Started
Planning | Current State GCP Environment Assessment | 3 days | Week 1 Day 3 | Week 2 Day 1 | Requirements Gathering | GCP Architect | Not Started
Planning | Landing Zone Architecture Design | 5 days | Week 2 Day 1 | Week 2 Day 5 | Environment Assessment | GCP Architect | Not Started
Planning | Security Baseline and Compliance Design | 4 days | Week 2 Day 3 | Week 3 Day 2 | Architecture Design | Security Specialist | Not Started
Foundation | GCP Organization and Billing Setup | 3 days | Week 3 Day 1 | Week 3 Day 3 | Architecture Design | GCP Architect | Not Started
Foundation | Folder Hierarchy Configuration | 2 days | Week 3 Day 3 | Week 3 Day 5 | Organization Setup | Platform Engineer | Not Started
Foundation | Cloud Identity and SAML SSO Integration | 4 days | Week 3 Day 4 | Week 4 Day 3 | Folder Hierarchy | Platform Engineer | Not Started
Foundation | Shared VPC Hub Network Deployment | 5 days | Week 4 Day 1 | Week 4 Day 5 | Organization Setup | Platform Engineer | Not Started
Foundation | Dedicated Interconnect Provisioning | 10 days | Week 1 Day 1 | Week 6 Day 5 | ISP Coordination (parallel) | Network Engineer | Not Started
Network | VLAN Attachment Configuration | 3 days | Week 6 Day 5 | Week 7 Day 3 | Interconnect Provisioning | Network Engineer | Not Started
Network | Cloud Router and BGP Configuration | 2 days | Week 7 Day 3 | Week 7 Day 5 | VLAN Attachments | Network Engineer | Not Started
Network | Cloud NAT Gateway Deployment | 2 days | Week 7 Day 3 | Week 7 Day 5 | Shared VPC Network | Platform Engineer | Not Started
Network | Internal Load Balancer Setup | 2 days | Week 7 Day 4 | Week 8 Day 1 | Cloud NAT | Platform Engineer | Not Started
Security | Security Command Center Premium Setup | 3 days | Week 5 Day 1 | Week 5 Day 3 | Folder Hierarchy | Security Specialist | Not Started
Security | Chronicle SIEM Integration | 4 days | Week 5 Day 3 | Week 6 Day 2 | SCC Premium Setup | Security Specialist | Not Started
Security | Organization Policy Constraints (50+) | 5 days | Week 5 Day 1 | Week 5 Day 5 | Folder Hierarchy | Security Specialist | Not Started
Security | Cloud KMS Key Management Setup | 3 days | Week 6 Day 1 | Week 6 Day 3 | Organization Policies | Security Specialist | Not Started
Security | Cloud Armor and Cloud IDS Deployment | 3 days | Week 6 Day 2 | Week 6 Day 5 | SCC Premium Setup | Security Specialist | Not Started
Automation | Cloud Foundation Toolkit Module Dev | 10 days | Week 6 Day 1 | Week 8 Day 5 | Security Baseline | Platform Engineer | Not Started
Automation | Project Factory Module Configuration | 5 days | Week 8 Day 1 | Week 8 Day 5 | CFT Module Dev | Platform Engineer | Not Started
Automation | CI/CD Pipeline Setup for Terraform | 3 days | Week 8 Day 3 | Week 9 Day 1 | Project Factory Module | Platform Engineer | Not Started
Observability | Cloud Logging Sink Configuration | 3 days | Week 9 Day 1 | Week 9 Day 3 | Project Factory | Platform Engineer | Not Started
Observability | BigQuery Log Export Setup | 2 days | Week 9 Day 3 | Week 9 Day 5 | Logging Sinks | Platform Engineer | Not Started
Observability | Cloud Monitoring Dashboards | 3 days | Week 9 Day 3 | Week 10 Day 1 | Logging Sinks | Platform Engineer | Not Started
Observability | FinOps Dashboards and Budget Alerts | 3 days | Week 10 Day 1 | Week 10 Day 3 | Monitoring Dashboards | Platform Engineer | Not Started
Testing | Infrastructure Validation Testing | 3 days | Week 10 Day 1 | Week 10 Day 3 | All Infrastructure | QA Lead | Not Started
Testing | Network Connectivity Testing | 2 days | Week 10 Day 3 | Week 10 Day 5 | Infrastructure Testing | Network Engineer | Not Started
Testing | Security Baseline Validation | 3 days | Week 10 Day 3 | Week 11 Day 1 | Infrastructure Testing | Security Specialist | Not Started
Testing | Compliance Validation (SOC 2 PCI-DSS) | 2 days | Week 11 Day 1 | Week 11 Day 3 | Security Validation | Security Specialist | Not Started
Testing | User Acceptance Testing with Pilot Teams | 5 days | Week 11 Day 1 | Week 11 Day 5 | All Testing | QA Lead | Not Started
Onboarding | Pilot Team 1 Project Provisioning | 2 days | Week 11 Day 3 | Week 11 Day 5 | UAT Complete | Platform Engineer | Not Started
Onboarding | Pilot Team 2 Project Provisioning | 2 days | Week 11 Day 5 | Week 12 Day 2 | Pilot Team 1 | Platform Engineer | Not Started
Training | Platform Administrator Training | 2 days | Week 11 Day 1 | Week 11 Day 3 | CFT Modules Complete | Project Manager | Not Started
Training | Security Operations Training | 1 day | Week 11 Day 3 | Week 11 Day 4 | Administrator Training | Security Specialist | Not Started
Training | Knowledge Transfer Sessions | 3 days | Week 12 Day 1 | Week 12 Day 3 | All Training | GCP Architect | Not Started
Closure | Documentation Finalization | 3 days | Week 12 Day 1 | Week 12 Day 3 | All Deliverables | Project Manager | Not Started
Closure | Go-Live Readiness Review | 1 day | Week 12 Day 4 | Week 12 Day 4 | Documentation Complete | Project Manager | Not Started
Closure | Production Go-Live | 1 day | Week 12 Day 5 | Week 12 Day 5 | Go-Live Readiness | Project Manager | Not Started
Hypercare | Daily Health Checks and Support | 14 days | Week 13 Day 1 | Week 14 Day 5 | Go-Live | Platform Engineer | Not Started
Hypercare | Issue Resolution and Optimization | 14 days | Week 13 Day 1 | Week 14 Day 5 | Go-Live | Platform Engineer | Not Started
Hypercare | Project Closure and Lessons Learned | 2 days | Week 16 Day 4 | Week 16 Day 5 | Hypercare Period | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | Week 1 | All stakeholders attended kickoff; project charter approved; GCP access confirmed | Project Manager | Not Started
M2 | Architecture Approved | Week 3 | Landing zone architecture design signed off by technical governance | GCP Architect | Not Started
M3 | Foundation Complete | Week 5 | GCP Organization folder hierarchy and Cloud Identity SSO operational | Platform Engineer | Not Started
M4 | Network Operational | Week 8 | Shared VPC and Dedicated Interconnect live with <5ms latency validated | Network Engineer | Not Started
M5 | Security Baseline Active | Week 7 | SCC Premium Chronicle and 50+ organization policies enforced | Security Specialist | Not Started
M6 | Automation Ready | Week 9 | Cloud Foundation Toolkit modules tested; project provisioning <1 hour | Platform Engineer | Not Started
M7 | Testing Complete | Week 11 | All test cases passed; SOC 2 and PCI-DSS compliance validated | QA Lead | Not Started
M8 | Go-Live | Week 12 | 2 pilot teams onboarded; 4 projects operational; platform self-sufficient | Project Manager | Not Started
M9 | Project Closure | Week 16 | Hypercare complete; 30-day warranty fulfilled; lessons learned documented | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Architect | Platform | Security | Network | QA | Training | Client
Project Charter and Kickoff | A | C | I | I | I | I | I | R
Landing Zone Architecture Design | C | R | C | C | C | I | I | A
GCP Organization and Billing Setup | A | R | R | C | I | I | I | C
Folder Hierarchy and IAM | A | C | R | R | I | I | I | C
Shared VPC Network Deployment | A | C | R | C | R | I | I | I
Dedicated Interconnect Setup | A | C | C | I | R | I | I | C
Security Baseline (SCC Chronicle) | A | C | C | R | I | I | I | C
Organization Policy Implementation | A | C | C | R | I | I | I | C
Cloud Foundation Toolkit Modules | A | C | R | C | I | I | I | I
CI/CD Pipeline Configuration | A | C | R | I | I | I | I | I
Logging and Monitoring Setup | A | C | R | C | I | I | I | I
Testing and Validation | A | C | C | C | C | R | I | C
Training Delivery | A | C | C | C | I | I | R | R
Go-Live and Pilot Onboarding | A | C | R | C | C | C | I | R
Legend:
R | A C A A A A A A A A A A A A: Responsible - Does the work
A | A C A A A A A A A A A A A A: Accountable - Ultimate ownership
C | A C A A A A A A A A A A A A: Consulted - Provides input
I | A C A A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders and project team | Launch project and align on objectives and timeline | Project Manager | Week 1 Day 1
Steering Committee | Bi-weekly | Executive sponsors PM and tech leads | Strategic decisions escalations and milestone approval | Project Manager | Alternate Thursdays
Weekly Status Meeting | Weekly | Core project team and client leads | Review progress risks blockers and next week priorities | Project Manager | Mondays 10:00 AM
Technical Design Review | Weekly | GCP Architect Platform Security Network | Architecture decisions and technical issue resolution | GCP Architect | Wednesdays 2:00 PM
Security Review | Bi-weekly | Security Specialist and client security team | Security baseline progress and compliance validation | Security Specialist | Alternate Tuesdays
Go-Live Readiness | Daily (Week 12) | Go-live team and stakeholders | Pre-go-live checklist and issue triage | Project Manager | Daily 9:00 AM
Hypercare Standup | Daily (Weeks 13-14) | Support team and client platform team | Daily health check and issue resolution | Platform Engineer | Daily 9:30 AM
Project Closeout | Once | All stakeholders and project team | Formal closure lessons learned and transition to steady state | Project Manager | Week 16 Day 5