## Cover
Test Plan
Generated: | November 27, 2025
Solution: | Landing Zone
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Functional Tests
Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
FT-001 | Unit | Organization Structure Validation | Verify GCP Organization exists with correct domain and billing account association | GCP Organization created | 1. Login to GCP console; 2. Navigate to IAM & Admin > Resource Manager; 3. Verify Organization with domain; 4. Check billing account association | Organization accessible with correct domain and billing account linked | Critical | Not Started
FT-002 | Unit | Folder Hierarchy Validation | Verify folder structure matches design with dev staging prod and shared-services | Organization created | 1. Navigate to Resource Manager; 2. Expand Organization hierarchy; 3. Verify four folders exist; 4. Check folder names match design | Four folders visible under Organization with correct names | High | Not Started
FT-003 | Unit | Project Creation in Folder | Verify projects can be created within designated folders | Folders created | 1. Navigate to target folder; 2. Create new project; 3. Verify project appears in folder; 4. Check billing account linked | Project created successfully in specified folder | High | Not Started
FT-004 | Unit | Cloud Identity SSO Integration | Verify SAML SSO authentication works with corporate identity provider | Cloud Identity and IdP configured | 1. Navigate to GCP console; 2. Attempt login with SSO; 3. Verify redirect to IdP; 4. Complete authentication; 5. Confirm GCP access | Users can authenticate via corporate IdP with single sign-on | Critical | Not Started
FT-005 | Unit | Directory Sync Validation | Verify GCDS syncs users and groups from Active Directory | GCDS service configured | 1. Check GCDS sync status; 2. Verify users appear in Cloud Identity; 3. Confirm group memberships; 4. Validate email attributes | Users and groups appear in Cloud Identity within sync interval | High | Not Started
FT-006 | Unit | IAM Role Assignment | Verify IAM roles correctly assigned at org folder and project levels | IAM policies applied via Terraform | 1. Check organization IAM; 2. Verify folder-level roles; 3. Test project-level permissions; 4. Validate role inheritance | Users have expected permissions based on role assignments | Critical | Not Started
FT-007 | Unit | 2-Step Verification Enforcement | Verify 2SV is required for all administrator accounts | 2SV policy configured in Cloud Identity | 1. Attempt admin login without 2SV; 2. Verify enrollment prompt; 3. Complete 2SV setup; 4. Test subsequent login | Admin login requires 2SV and non-compliant users blocked | High | Not Started
FT-008 | Unit | Shared VPC Host Project | Verify Shared VPC host project is configured correctly | Host project created via Terraform | 1. Navigate to VPC networks; 2. Check Shared VPC status; 3. Verify APIs enabled; 4. Confirm host project designation | Host project shows as Shared VPC host with all APIs enabled | Critical | Not Started
FT-009 | Unit | Subnet Creation and Configuration | Verify all subnets created with correct CIDR ranges and settings | VPC network created | 1. List all subnets in VPC; 2. Verify CIDR ranges match design; 3. Check Private Google Access; 4. Confirm regions correct | 12 subnets visible across 3 regions with correct CIDRs | High | Not Started
FT-010 | Unit | Service Project Attachment | Verify service projects can attach to Shared VPC | Host and service projects created | 1. Create service project; 2. Attach to Shared VPC; 3. Verify attachment status; 4. Test subnet access | Service project successfully attached to Shared VPC | High | Not Started
FT-011 | Unit | Private Google Access | Verify Private Google Access enabled on all subnets | Subnets configured with PGA | 1. Create VM without external IP; 2. Attempt to access Google APIs; 3. Verify connectivity; 4. Check DNS resolution | VMs without external IPs can access Google APIs | High | Not Started
FT-012 | Unit | Cloud NAT Functionality | Verify Cloud NAT provides internet egress for private VMs | Cloud NAT configured in each region | 1. Create VM without external IP; 2. Attempt internet access; 3. Verify NAT translation; 4. Check NAT logs | VMs without external IPs can reach internet via NAT gateway | High | Not Started
FT-013 | Unit | Firewall Rule Enforcement | Verify firewall rules allow internal traffic and block unauthorized | Firewall rules applied via Terraform | 1. Test internal VM-to-VM connectivity; 2. Test blocked external access; 3. Verify rule logging; 4. Check rule priority | Internal traffic allowed and external traffic blocked per rules | High | Not Started
FT-014 | Integration | Interconnect Provisioning | Verify Dedicated Interconnect is provisioned and active | ISP coordination complete | 1. Navigate to Hybrid Connectivity; 2. Check Interconnect status; 3. Verify link operational; 4. Confirm bandwidth | Interconnect shows ACTIVE state in console with 10 Gbps | Critical | Not Started
FT-015 | Integration | VLAN Attachment Configuration | Verify all 4 VLAN attachments are operational | Interconnect active | 1. List VLAN attachments; 2. Verify each attachment status; 3. Check bandwidth allocation; 4. Confirm router association | 4 VLAN attachments show ACTIVE with correct bandwidth | High | Not Started
FT-016 | Integration | BGP Session Establishment | Verify BGP sessions established with on-premises routers | VLAN attachments configured | 1. Check Cloud Router status; 2. Verify BGP peer state; 3. Confirm route exchange; 4. Test failover | BGP sessions show ESTABLISHED state with route exchange | Critical | Not Started
FT-017 | Integration | Route Advertisement | Verify GCP routes advertised to on-premises network | BGP sessions established | 1. Check advertised routes; 2. Verify on-prem routing table; 3. Test connectivity; 4. Validate path selection | On-prem routers receive GCP subnet routes correctly | High | Not Started
FT-018 | Unit | SCC Premium Activation | Verify Security Command Center Premium is enabled organization-wide | SCC configured via Terraform | 1. Navigate to Security Command Center; 2. Verify Premium tier; 3. Check all features available; 4. Confirm scope | SCC Premium active with all features available organization-wide | Critical | Not Started
FT-019 | Unit | Asset Discovery | Verify SCC discovers all GCP resources | SCC Premium active | 1. Navigate to SCC Assets; 2. Filter by project; 3. Verify resource inventory; 4. Check asset types | All projects and resources visible in SCC inventory | High | Not Started
FT-020 | Integration | Chronicle SIEM Integration | Verify Chronicle receives logs from Cloud Audit Logs | Chronicle configured and log sink created | 1. Login to Chronicle console; 2. Search for recent GCP logs; 3. Verify log types; 4. Check ingestion latency | Audit logs visible in Chronicle within 5 minutes of generation | Critical | Not Started
FT-021 | Unit | Organization Policy Enforcement | Verify organization policies block non-compliant resources | 50+ policies deployed via Terraform | 1. Attempt to create VM with external IP; 2. Verify policy denial; 3. Check error message; 4. Test other constraints | Attempt to create non-compliant resource fails with policy error | Critical | Not Started
FT-022 | Unit | Cloud KMS Key Creation | Verify Cloud KMS keys created and accessible | KMS configured via Terraform | 1. Navigate to KMS; 2. Verify key ring exists; 3. Check 6 keys present; 4. Confirm rotation schedule | 6 keys visible in key ring with 90-day rotation configured | High | Not Started
FT-023 | Unit | Terraform State Backend | Verify Terraform state stored in Cloud Storage with versioning | State bucket created | 1. Verify bucket exists; 2. Check versioning enabled; 3. Confirm encryption; 4. Test terraform init | Terraform init succeeds and state file visible in bucket | High | Not Started
FT-024 | Integration | Project Factory Module | Verify project factory module provisions complete project | CFT modules deployed | 1. Run terraform apply for new project; 2. Verify project created; 3. Check VPC attachment; 4. Confirm IAM and APIs | New project created with VPC attachment IAM and APIs enabled | Critical | Not Started
FT-025 | Integration | CI/CD Pipeline Execution | Verify Cloud Build pipeline executes Terraform successfully | Cloud Build configured | 1. Trigger Cloud Build; 2. Monitor execution; 3. Verify terraform plan; 4. Confirm terraform apply | Pipeline completes terraform plan and apply without errors | High | Not Started
FT-026 | Unit | Cloud Logging Sink | Verify organization log sink exports to BigQuery | Log sink configured | 1. Check log sink status; 2. Query BigQuery dataset; 3. Verify log records; 4. Check export latency | Audit logs appear in BigQuery dataset within 5 minutes | High | Not Started
FT-027 | Unit | VPC Flow Logs | Verify VPC Flow Logs capture network traffic in production | Flow logs enabled on prod subnets | 1. Generate network traffic; 2. Query Cloud Logging; 3. Verify flow log entries; 4. Check sampling rate | Network traffic visible in Cloud Logging within 1 minute | Medium | Not Started
FT-028 | Unit | Dashboard Availability | Verify monitoring dashboards display platform metrics | Dashboards created via Terraform | 1. Navigate to Cloud Monitoring; 2. Open each dashboard; 3. Verify widgets populated; 4. Check data freshness | 4 dashboards visible with real-time metric data | Medium | Not Started
FT-029 | Integration | Alert Policy Triggers | Verify alert policies trigger notifications correctly | Alert policies configured | 1. Simulate alert condition; 2. Verify alert fired; 3. Check notification channel; 4. Confirm alert content | Test alert triggers notification to configured channels | High | Not Started

## Non-Functional Tests
Non-Functional Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
NFT-001 | Performance | Project Provisioning Time | Verify project provisioning completes within target time | Project factory configured and validated | 1. Start timer; 2. Run terraform apply for new project; 3. Verify all resources created; 4. Stop timer; 5. Record duration | New project fully operational within 60 minutes | Critical | Not Started
NFT-002 | Performance | Interconnect Latency | Verify Interconnect latency meets less than 5ms target | Interconnect operational with BGP established | 1. Create VM in GCP; 2. Run ping from on-prem to VM; 3. Record RTT; 4. Test multiple times; 5. Calculate average | Ping from on-prem to GCP VM shows less than 5ms average RTT | Critical | Not Started
NFT-003 | Performance | Interconnect Throughput | Verify Interconnect achieves expected throughput | Interconnect operational | 1. Install iperf on both ends; 2. Run throughput test; 3. Record bandwidth; 4. Test bidirectional; 5. Verify consistency | iperf test shows greater than 9 Gbps throughput sustained | High | Not Started
NFT-004 | Performance | Cloud NAT Throughput | Verify Cloud NAT handles expected traffic volume | Cloud NAT configured | 1. Create multiple VMs; 2. Generate concurrent outbound traffic; 3. Monitor NAT metrics; 4. Check for drops | NAT gateway handles concurrent connections without drops | Medium | Not Started
NFT-005 | Security | CIS Benchmark Compliance | Verify infrastructure passes CIS Google Cloud Foundation Benchmark | All infrastructure deployed | 1. Run SCC CIS scan; 2. Review findings; 3. Check critical items; 4. Validate remediation; 5. Document exceptions | SCC shows no critical CIS benchmark findings | Critical | Not Started
NFT-006 | Security | Penetration Test Simulation | Verify security controls block common attack vectors | Security baseline deployed | 1. Attempt external port scan; 2. Test SQL injection on APIs; 3. Verify IAM escalation blocked; 4. Check network isolation | Simulated attacks blocked by firewall policies and IAM | High | Not Started
NFT-007 | Security | Data Encryption Validation | Verify all data encrypted at rest with CMEK | KMS keys configured | 1. Create storage bucket; 2. Verify CMEK encryption; 3. Check disk encryption; 4. Validate key usage | Storage objects and disks show CMEK encryption applied | Critical | Not Started
NFT-008 | Availability | Interconnect Failover | Verify traffic fails over between VLAN attachments | 4 VLAN attachments active | 1. Establish traffic flow; 2. Disable one attachment; 3. Verify traffic continues; 4. Check failover time; 5. Re-enable attachment | Traffic continues during single attachment failure within 30 seconds | Critical | Not Started
NFT-009 | Availability | Cloud NAT Redundancy | Verify NAT continues during single gateway maintenance | Multi-NAT configured | 1. Generate outbound traffic; 2. Simulate NAT maintenance; 3. Verify traffic continues; 4. Check for packet loss | Outbound traffic continues during NAT maintenance | Medium | Not Started
NFT-010 | Compliance | SOC 2 Control Validation | Verify SOC 2 controls implemented and effective | All infrastructure deployed per design | 1. Review SOC 2 control requirements; 2. Map to GCP controls; 3. Test control effectiveness; 4. Document evidence | All SOC 2 control points documented and validated | Critical | Not Started
NFT-011 | Compliance | PCI-DSS Control Validation | Verify PCI-DSS controls for network segmentation and encryption | Security baseline deployed | 1. Review PCI requirements; 2. Verify network segmentation; 3. Test encryption; 4. Validate access controls | Network segmentation and encryption meet PCI requirements | Critical | Not Started

## User Acceptance Tests
User Acceptance Tests
Test ID | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Status
UAT-001 | Acceptance | Pilot Team 1 Project Access | Verify pilot team 1 can access their provisioned project | Pilot team 1 project created and IAM configured | 1. Team member logs in; 2. Navigate to project; 3. Verify resource visibility; 4. Check permissions | Team members can login and view project resources | Critical | Not Started
UAT-002 | Acceptance | Pilot Team 1 Resource Deployment | Verify pilot team 1 can deploy resources in their project | Project access confirmed | 1. Create Compute Engine VM; 2. Create Cloud Storage bucket; 3. Deploy Cloud Run service; 4. Verify resources operational | Team can create VMs storage and other resources successfully | Critical | Not Started
UAT-003 | Acceptance | Pilot Team 1 Network Connectivity | Verify pilot team workloads have network connectivity | Resources deployed in pilot project | 1. Test VM-to-VM connectivity; 2. Test on-prem connectivity; 3. Test internet via NAT; 4. Verify DNS resolution | VMs can reach other VMs and on-prem systems and internet via NAT | Critical | Not Started
UAT-004 | Acceptance | Pilot Team 2 Project Access | Verify pilot team 2 can access their provisioned project | Pilot team 2 project created and IAM configured | 1. Team member logs in; 2. Navigate to project; 3. Verify resource visibility; 4. Check permissions | Team members can login and view project resources | High | Not Started
UAT-005 | Acceptance | Pilot Team 2 Resource Deployment | Verify pilot team 2 can deploy resources in their project | Project access confirmed | 1. Create Compute Engine VM; 2. Create Cloud Storage bucket; 3. Test GKE deployment; 4. Verify resources operational | Team can create VMs storage and container resources successfully | High | Not Started
UAT-006 | Acceptance | Self-Service Project Request | Verify platform team can provision new projects via Terraform | Training completed and access granted | 1. Clone Terraform repository; 2. Create tfvars for new project; 3. Run terraform apply; 4. Verify project created | Platform admin can request and provision new project independently | Critical | Not Started
UAT-007 | Acceptance | Security Finding Investigation | Verify security team can investigate SCC findings | SCC active with sample findings | 1. Login to SCC; 2. Navigate to Findings; 3. Select finding; 4. Review details; 5. Mark as remediated | Security admin can view investigate and remediate findings | High | Not Started
UAT-008 | Acceptance | Cost Monitoring Access | Verify FinOps team can access cost dashboards | Dashboards configured with IAM access | 1. Login with FinOps account; 2. Navigate to billing; 3. View cost breakdown; 4. Check budget status | FinOps can view cost data and budget status by project | Medium | Not Started