## Cover
Project Plan
Generated: | December 03, 2025
Solution: | Enterprise Landing Zone
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff and Charter | 1 day | 2025-01-15 | 2025-01-15 | None | Project Manager | Not Started
Discovery | Current State Assessment | 5 days | 2025-01-16 | 2025-01-22 | Project Kickoff | Cloud Architect | Not Started
Discovery | Organizational Structure Analysis | 3 days | 2025-01-20 | 2025-01-22 | Assessment Started | Business Analyst | Not Started
Discovery | Compliance Requirements Gathering | 3 days | 2025-01-20 | 2025-01-22 | Assessment Started | Security Architect | Not Started
Discovery | Network Topology Assessment | 3 days | 2025-01-23 | 2025-01-27 | Current State Complete | Network Engineer | Not Started
Discovery | Identity and Access Assessment | 3 days | 2025-01-23 | 2025-01-27 | Current State Complete | Identity Architect | Not Started
Design | Management Group Hierarchy Design | 5 days | 2025-01-28 | 2025-02-03 | All Assessments Complete | Cloud Architect | Not Started
Design | Azure Policy Framework Design | 5 days | 2025-02-03 | 2025-02-07 | MG Design Complete | Governance Lead | Not Started
Design | Hub-Spoke Network Design | 5 days | 2025-02-03 | 2025-02-07 | Network Assessment | Network Engineer | Not Started
Design | Identity and RBAC Strategy | 3 days | 2025-02-06 | 2025-02-10 | Identity Assessment | Identity Architect | Not Started
Design | Security Baseline Design | 5 days | 2025-02-10 | 2025-02-14 | Policy Framework Draft | Security Architect | Not Started
Design | Architecture Design Document | 5 days | 2025-02-10 | 2025-02-14 | All Designs Complete | Cloud Architect | Not Started
Build | Management Group Hierarchy Deployment | 3 days | 2025-02-17 | 2025-02-19 | Design Approved | Cloud Architect | Not Started
Build | Platform Subscriptions Creation | 2 days | 2025-02-20 | 2025-02-21 | MG Hierarchy Complete | Cloud Architect | Not Started
Build | Azure Policy Framework Deployment | 5 days | 2025-02-24 | 2025-02-28 | Subscriptions Created | Governance Lead | Not Started
Build | Hub Virtual Network Deployment | 3 days | 2025-03-03 | 2025-03-05 | Platform Subscriptions | Network Engineer | Not Started
Build | Azure Firewall Configuration | 3 days | 2025-03-06 | 2025-03-10 | Hub VNet Complete | Network Engineer | Not Started
Build | ExpressRoute Circuit Provisioning | 5 days | 2025-03-10 | 2025-03-14 | Firewall Complete | Network Engineer | Not Started
Build | Private DNS Zones Configuration | 2 days | 2025-03-13 | 2025-03-14 | Hub VNet Complete | Network Engineer | Not Started
Build | Azure Bastion Deployment | 2 days | 2025-03-17 | 2025-03-18 | Hub VNet Complete | Security Engineer | Not Started
Build | Log Analytics Workspace Setup | 2 days | 2025-03-17 | 2025-03-18 | Platform Subscriptions | Operations Engineer | Not Started
Build | Azure Sentinel Deployment | 3 days | 2025-03-19 | 2025-03-21 | Log Analytics Complete | Security Engineer | Not Started
Build | Defender for Cloud Activation | 2 days | 2025-03-24 | 2025-03-25 | Sentinel Complete | Security Engineer | Not Started
Build | Data Connector Configuration | 3 days | 2025-03-26 | 2025-03-28 | Sentinel Complete | Security Engineer | Not Started
Build | Azure AD Integration | 3 days | 2025-03-31 | 2025-04-02 | Platform Complete | Identity Architect | Not Started
Build | RBAC Role Assignments | 3 days | 2025-04-03 | 2025-04-07 | Azure AD Complete | Identity Architect | Not Started
Build | Conditional Access Policies | 3 days | 2025-04-08 | 2025-04-10 | Azure AD Complete | Identity Architect | Not Started
Build | Subscription Vending Automation | 5 days | 2025-04-08 | 2025-04-14 | All Platform Complete | DevOps Engineer | Not Started
Build | Monitoring Dashboards Creation | 3 days | 2025-04-14 | 2025-04-16 | All Monitoring Complete | Operations Engineer | Not Started
Test | Functional Testing | 5 days | 2025-04-17 | 2025-04-23 | All Build Complete | QA Engineer | Not Started
Test | Security Testing | 5 days | 2025-04-21 | 2025-04-25 | Functional Testing Started | Security Tester | Not Started
Test | Compliance Validation | 3 days | 2025-04-24 | 2025-04-28 | Security Testing | Compliance Lead | Not Started
Test | Performance Testing | 3 days | 2025-04-28 | 2025-04-30 | Functional Complete | Performance Engineer | Not Started
Test | User Acceptance Testing | 5 days | 2025-05-01 | 2025-05-07 | All Testing Complete | Business Users | Not Started
Deploy | Pre-Production Validation | 3 days | 2025-05-08 | 2025-05-12 | UAT Complete | QA Lead | Not Started
Deploy | Production Cutover | 2 days | 2025-05-13 | 2025-05-14 | Validation Complete | Deployment Team | Not Started
Deploy | Go-Live Support | 5 days | 2025-05-15 | 2025-05-21 | Cutover Complete | Support Team | Not Started
Training | Training Material Development | 10 days | 2025-04-28 | 2025-05-09 | UAT Started | Training Team | Not Started
Training | Platform Administrator Training | 3 days | 2025-05-12 | 2025-05-14 | Materials Ready | Training Team | Not Started
Training | Security Operations Training | 2 days | 2025-05-15 | 2025-05-16 | Materials Ready | Training Team | Not Started
Training | Network Operations Training | 2 days | 2025-05-19 | 2025-05-20 | Materials Ready | Training Team | Not Started
Training | Governance Training | 2 days | 2025-05-21 | 2025-05-22 | Materials Ready | Training Team | Not Started
Closure | Hypercare Support | 30 days | 2025-05-15 | 2025-06-18 | Go-Live | Support Team | Not Started
Closure | Project Documentation | 5 days | 2025-06-16 | 2025-06-20 | Hypercare | Project Manager | Not Started
Closure | Project Closure | 2 days | 2025-06-23 | 2025-06-24 | Documentation Complete | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | 2025-01-15 | Kickoff meeting held; project charter signed; team assigned and onboarded | Project Manager | Not Started
M2 | Assessment Complete | 2025-01-27 | Current state documented; all assessments complete; requirements validated | Cloud Architect | Not Started
M3 | Architecture Approved | 2025-02-14 | Architecture design document signed off; security review passed; network design approved | Cloud Architect | Not Started
M4 | Platform Foundation Ready | 2025-02-28 | Management groups deployed; platform subscriptions created; policy framework active | Cloud Architect | Not Started
M5 | Network Infrastructure Ready | 2025-03-14 | Hub-spoke topology operational; Azure Firewall configured; ExpressRoute provisioned | Network Engineer | Not Started
M6 | Security Monitoring Active | 2025-03-28 | Azure Sentinel operational with 15+ connectors; Defender for Cloud enabled | Security Engineer | Not Started
M7 | Identity Integration Complete | 2025-04-10 | Azure AD integrated; RBAC configured; Conditional Access policies active | Identity Architect | Not Started
M8 | Testing Complete | 2025-05-07 | All test cases passed; compliance validated; UAT signed off; zero P1/P2 defects | QA Lead | Not Started
M9 | Go-Live | 2025-05-14 | Production deployment complete; platform operational; monitoring active | Project Manager | Not Started
M10 | Project Closure | 2025-06-24 | Hypercare complete; documentation delivered; knowledge transfer done; lessons captured | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Cloud Arch | Security | Network | Identity | DevOps | Client IT | Client Sec
Project Charter and Kickoff | A | C | C | C | C | I | C | C
Current State Assessment | A | R | C | C | C | I | C | C
Architecture Design Document | A | R | C | C | C | I | I | I
Management Group Hierarchy | A | R | C | I | C | C | I | I
Azure Policy Framework | A | C | R | C | C | C | I | C
Hub-Spoke Network Design | A | C | C | R | I | C | I | I
Azure Firewall Configuration | A | C | C | R | I | C | I | C
ExpressRoute Provisioning | A | C | I | R | I | C | C | I
Azure Sentinel Deployment | A | C | R | C | I | C | I | C
Defender for Cloud Setup | A | C | R | I | I | C | I | C
Azure AD Integration | A | C | C | I | R | C | C | C
RBAC Configuration | A | C | C | I | R | C | C | C
Conditional Access Policies | A | C | R | I | R | I | I | C
Subscription Vending Automation | A | C | I | I | I | R | I | I
Monitoring and Dashboards | A | C | C | C | I | R | C | I
Legend:
R | A A A A A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders and project team | Launch project and align on objectives and governance approach | Project Manager | Day 1 10:00
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic direction and issue escalation for enterprise transformation | Project Manager | Alternate Tuesdays 14:00
Status Meeting | Weekly | Core project team | Review progress and address blockers across all workstreams | Project Manager | Mondays 10:00
Technical Review | Weekly | Cloud architect and technical leads | Architecture decisions and technical design validation | Cloud Architect | Wednesdays 14:00
Security Review | Weekly | Security architect and security team | Security controls review and compliance validation | Security Architect | Thursdays 11:00
Network Design Review | Weekly | Network engineer and network team | Network topology and connectivity status | Network Engineer | Fridays 10:00
Governance Review | Bi-weekly | Governance lead and compliance team | Policy framework review and compliance status | Governance Lead | Alternate Thursdays 14:00
Go-Live Readiness | Daily (Week -1) | Go-live team and stakeholders | Go-live preparation and cutover checklist review | Project Manager | Daily 09:00
Hypercare Standup | Daily (30 days) | Support team and client operations | Post-go-live issues and platform stabilization | Support Lead | Daily 09:30