## Cover
Project Plan
Generated: | December 03, 2025
Solution: | Sentinel Siem
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Foundation | Project Kickoff and Charter | 1 day | 2025-01-15 | 2025-01-15 | None | Project Manager | Not Started
Foundation | Security Requirements Validation | 3 days | 2025-01-16 | 2025-01-20 | Project Kickoff | Security Architect | Not Started
Foundation | Data Source Inventory | 3 days | 2025-01-16 | 2025-01-20 | Project Kickoff | SIEM Engineer | Not Started
Foundation | Log Analytics Workspace Deployment | 2 days | 2025-01-21 | 2025-01-22 | Requirements Complete | SIEM Engineer | Not Started
Foundation | Azure Sentinel Enablement | 1 day | 2025-01-23 | 2025-01-23 | Workspace Ready | SIEM Engineer | Not Started
Foundation | Initial RBAC Configuration | 2 days | 2025-01-24 | 2025-01-27 | Sentinel Enabled | Security Engineer | Not Started
Connectors | Azure AD Data Connector | 2 days | 2025-01-28 | 2025-01-29 | Sentinel Enabled | SIEM Engineer | Not Started
Connectors | Office 365 Data Connector | 2 days | 2025-01-30 | 2025-01-31 | Sentinel Enabled | SIEM Engineer | Not Started
Connectors | Defender for Cloud Connector | 2 days | 2025-02-03 | 2025-02-04 | Sentinel Enabled | SIEM Engineer | Not Started
Connectors | Defender for Endpoint Connector | 2 days | 2025-02-05 | 2025-02-06 | Sentinel Enabled | SIEM Engineer | Not Started
Connectors | Defender for Identity Connector | 2 days | 2025-02-07 | 2025-02-10 | Sentinel Enabled | SIEM Engineer | Not Started
Connectors | Azure Activity Logs Connector | 1 day | 2025-02-11 | 2025-02-11 | Sentinel Enabled | SIEM Engineer | Not Started
Connectors | CEF/Syslog Connector Setup | 3 days | 2025-02-12 | 2025-02-14 | Sentinel Enabled | SIEM Engineer | Not Started
Connectors | DNS Logs Connector | 2 days | 2025-02-17 | 2025-02-18 | Sentinel Enabled | SIEM Engineer | Not Started
Connectors | Third-Party Connector Integration | 5 days | 2025-02-19 | 2025-02-25 | All Native Connectors | SIEM Engineer | Not Started
Analytics | Built-in Rules Deployment | 3 days | 2025-02-26 | 2025-02-28 | Data Connectors Active | Security Analyst | Not Started
Analytics | Custom Rule Development | 7 days | 2025-03-03 | 2025-03-11 | Built-in Rules Ready | Security Analyst | Not Started
Analytics | UEBA Configuration | 3 days | 2025-03-12 | 2025-03-14 | Custom Rules Complete | Security Analyst | Not Started
Analytics | Threat Intelligence Integration | 3 days | 2025-03-17 | 2025-03-19 | Analytics Rules Active | Security Analyst | Not Started
Analytics | Alert Tuning and Optimization | 5 days | 2025-03-20 | 2025-03-26 | TI Integration Complete | Security Analyst | Not Started
Automation | Logic App Infrastructure | 2 days | 2025-03-27 | 2025-03-28 | Analytics Complete | Automation Engineer | Not Started
Automation | Auto-Enrichment Playbooks | 3 days | 2025-03-31 | 2025-04-02 | Logic Apps Ready | Automation Engineer | Not Started
Automation | Auto-Containment Playbooks | 3 days | 2025-04-03 | 2025-04-07 | Enrichment Playbooks | Automation Engineer | Not Started
Automation | Auto-Ticketing Playbooks | 3 days | 2025-04-08 | 2025-04-10 | Containment Playbooks | Automation Engineer | Not Started
Automation | Notification Playbooks | 2 days | 2025-04-11 | 2025-04-14 | Ticketing Playbooks | Automation Engineer | Not Started
Automation | Playbook Testing and Validation | 3 days | 2025-04-15 | 2025-04-17 | All Playbooks Complete | QA Engineer | Not Started
Test | Functional Testing | 5 days | 2025-04-18 | 2025-04-24 | Automation Complete | QA Engineer | Not Started
Test | Detection Accuracy Testing | 5 days | 2025-04-25 | 2025-05-01 | Functional Complete | Security Analyst | Not Started
Test | Performance Testing | 3 days | 2025-05-02 | 2025-05-06 | Detection Testing | Performance Engineer | Not Started
Test | Security Testing | 3 days | 2025-05-07 | 2025-05-09 | Performance Complete | Security Tester | Not Started
Test | User Acceptance Testing | 5 days | 2025-05-12 | 2025-05-16 | All Testing Complete | SOC Team | Not Started
Deploy | Pre-Production Validation | 2 days | 2025-05-19 | 2025-05-20 | UAT Complete | QA Lead | Not Started
Deploy | Production Cutover | 2 days | 2025-05-21 | 2025-05-22 | Validation Complete | Deployment Team | Not Started
Deploy | Go-Live Support | 5 days | 2025-05-23 | 2025-05-29 | Cutover Complete | Support Team | Not Started
Training | Training Material Development | 10 days | 2025-05-05 | 2025-05-16 | UAT Started | Training Team | Not Started
Training | SOC Analyst Training | 3 days | 2025-05-19 | 2025-05-21 | Materials Ready | Training Team | Not Started
Training | Threat Hunting Training | 2 days | 2025-05-22 | 2025-05-23 | Analyst Training | Training Team | Not Started
Training | Administrator Training | 2 days | 2025-05-26 | 2025-05-27 | Analyst Training | Training Team | Not Started
Closure | Hypercare Support | 30 days | 2025-05-23 | 2025-06-25 | Go-Live | Support Team | Not Started
Closure | Project Documentation | 5 days | 2025-06-23 | 2025-06-27 | Hypercare | Project Manager | Not Started
Closure | Project Closure | 2 days | 2025-06-30 | 2025-07-01 | Documentation Complete | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | 2025-01-15 | Kickoff meeting held; project charter signed; team assigned and onboarded | Project Manager | Not Started
M2 | Foundation Complete | 2025-01-27 | Log Analytics deployed; Sentinel enabled; initial RBAC configured | SIEM Engineer | Not Started
M3 | Data Connectors Active | 2025-02-25 | All 15+ data connectors configured and ingesting; data validation complete | SIEM Engineer | Not Started
M4 | Analytics Rules Deployed | 2025-03-26 | 50+ analytics rules active; alert tuning complete; false positives below threshold | Security Analyst | Not Started
M5 | Automation Complete | 2025-04-17 | 12 SOAR playbooks deployed and tested; auto-remediation operational | Automation Engineer | Not Started
M6 | Testing Complete | 2025-05-16 | All test cases passed; detection accuracy 95%+; UAT signed off | QA Lead | Not Started
M7 | Go-Live | 2025-05-22 | Production deployment complete; SOC operational; monitoring active | Project Manager | Not Started
M8 | Training Complete | 2025-05-27 | All SOC team trained; administrator certified; hunting capability established | Training Team | Not Started
M9 | Project Closure | 2025-07-01 | Hypercare complete; documentation delivered; lessons learned captured | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Sec Arch | SIEM Eng | Sec Analyst | Auto Eng | QA | SOC Mgr | Client Sec
Project Charter and Kickoff | A | C | C | I | I | I | C | C
Security Requirements Document | A | R | C | C | I | I | C | C
Log Analytics Workspace Deployment | A | C | R | I | I | I | I | I
Azure Sentinel Enablement | A | C | R | I | I | I | I | I
Data Connector Configuration | A | C | R | C | I | I | I | C
Analytics Rules Deployment | A | C | C | R | I | I | C | C
Custom Rule Development | A | C | C | R | I | I | C | C
UEBA Configuration | A | C | C | R | I | I | I | I
Threat Intelligence Integration | A | C | C | R | I | I | I | C
SOAR Playbook Development | A | C | C | C | R | I | I | I
Playbook Testing | A | C | C | C | C | R | I | I
Detection Accuracy Testing | A | C | C | R | I | C | C | C
SOC Training Delivery | A | C | C | C | I | I | R | C
Production Deployment | A | C | R | C | C | C | C | I
Legend:
R | A A A A A A A A A A A A A: Responsible - Does the work
A | A A A A A A A A A A A A A: Accountable - Ultimate ownership
C | A A A A A A A A A A A A A: Consulted - Provides input
I | A A A A A A A A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders and project team | Launch project and align on security objectives and detection priorities | Project Manager | Day 1 10:00
Steering Committee | Bi-weekly | Executive sponsors CISO and PMO | Strategic direction and security program alignment | Project Manager | Alternate Tuesdays 14:00
Status Meeting | Weekly | Core project team | Review progress and address blockers across workstreams | Project Manager | Mondays 10:00
Technical Review | Weekly | Security architect and SIEM engineers | Detection strategy and rule development progress | Security Architect | Wednesdays 14:00
SOC Sync | Weekly | SOC manager and security analysts | Alert quality and operational readiness review | SOC Manager | Thursdays 11:00
Detection Review | Weekly | Security analysts and threat hunters | Analytics rule effectiveness and tuning decisions | Security Analyst | Fridays 10:00
Automation Review | Bi-weekly | Automation engineer and SOC team | Playbook development and testing status | Automation Engineer | Alternate Wednesdays 15:00
Go-Live Readiness | Daily (Week -1) | Go-live team and stakeholders | Go-live preparation and cutover checklist review | Project Manager | Daily 09:00
Hypercare Standup | Daily (30 days) | Support team and SOC operations | Post-go-live issues and detection tuning | Support Lead | Daily 09:30