## Cover
Project Plan
Generated: | December 03, 2025
Solution: | Virtual Desktop
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Discovery | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | EO Project Manager | Not Started
Discovery | Current State Assessment | 4 days | [START_DATE+1] | [START_DATE+5] | Project Kickoff | EO Sales Engineer | Not Started
Discovery | Azure Environment Assessment | 5 days | [START_DATE+3] | [START_DATE+8] | Current State Assessment | EO Engineer | Not Started
Discovery | Network Connectivity Review | 5 days | [START_DATE+5] | [START_DATE+10] | Current State Assessment | EO Engineer | Not Started
Planning | AVD Solution Architecture | 10 days | [START_DATE+8] | [START_DATE+18] | Azure Environment Assessment | EO Quarterback | Not Started
Planning | Application Assessment | 8 days | [START_DATE+12] | [START_DATE+20] | AVD Solution Architecture | EO Quarterback | Not Started
Planning | User Profile Strategy | 7 days | [START_DATE+15] | [START_DATE+22] | Current State Assessment | EO Quarterback | Not Started
Planning | Security Architecture | 7 days | [START_DATE+18] | [START_DATE+25] | AVD Solution Architecture | EO Engineer | Not Started
Infrastructure | Azure Infrastructure Setup | 10 days | [START_DATE+25] | [START_DATE+35] | AVD Solution Architecture | EO Engineer | Not Started
Infrastructure | Host Pool Configuration | 10 days | [START_DATE+30] | [START_DATE+40] | Azure Infrastructure Setup | EO Engineer | Not Started
Development | Golden Image Creation | 15 days | [START_DATE+35] | [START_DATE+50] | Application Assessment | EO Engineer | Not Started
Development | Application Packaging | 20 days | [START_DATE+25] | [START_DATE+45] | Application Assessment | EO Engineer | Not Started
Development | Profile Container Setup | 10 days | [START_DATE+45] | [START_DATE+55] | User Profile Strategy | EO Engineer | Not Started
Development | Network Optimization | 10 days | [START_DATE+40] | [START_DATE+50] | Network Connectivity Review | EO Engineer | Not Started
Development | Monitoring Configuration | 10 days | [START_DATE+50] | [START_DATE+60] | Host Pool Configuration | EO Engineer | Not Started
Development | Security Implementation | 10 days | [START_DATE+55] | [START_DATE+65] | Security Architecture | EO Engineer | Not Started
Development | User Access Configuration | 10 days | [START_DATE+60] | [START_DATE+70] | Profile Container Setup | EO Engineer | Not Started
Testing | Infrastructure Testing | 10 days | [START_DATE+65] | [START_DATE+75] | Monitoring Configuration | EO Engineer | Not Started
Testing | Application Testing | 10 days | [START_DATE+75] | [START_DATE+85] | Application Packaging | EO Engineer | Not Started
Testing | User Experience Testing | 7 days | [START_DATE+80] | [START_DATE+87] | User Access Configuration | EO Engineer | Not Started
Testing | Security Testing | 15 days | [START_DATE+70] | [START_DATE+85] | Security Implementation | EO Engineer | Not Started
Testing | Performance Testing | 7 days | [START_DATE+85] | [START_DATE+92] | User Experience Testing | EO Engineer | Not Started
Testing | User Acceptance Testing | 10 days | [START_DATE+90] | [START_DATE+100] | Security Testing | EO Sales Engineer | Not Started
Deployment | Production Environment Setup | 7 days | [START_DATE+95] | [START_DATE+102] | Azure Infrastructure Setup | EO Engineer | Not Started
Deployment | Application Deployment | 5 days | [START_DATE+100] | [START_DATE+105] | Production Environment Setup | EO Engineer | Not Started
Deployment | Production Validation | 2 days | [START_DATE+105] | [START_DATE+107] | Application Deployment | EO Engineer | Not Started
Training | Administrator Training | 10 days | [START_DATE+95] | [START_DATE+105] | User Acceptance Testing | EO Engineer | Not Started
Training | End User Training | 7 days | [START_DATE+105] | [START_DATE+112] | Production Validation | EO Engineer | Not Started
Training | Documentation Delivery | 15 days | [START_DATE+100] | [START_DATE+115] | Production Validation | EO Engineer | Not Started
Go-Live | Production Go-Live | 2 days | [START_DATE+112] | [START_DATE+114] | End User Training | EO Project Manager | Not Started
Support | Go-Live Support | 7 days | [START_DATE+114] | [START_DATE+121] | Production Go-Live | EO Engineer | Not Started
Support | Performance Monitoring | 30 days | [START_DATE+121] | [START_DATE+151] | Go-Live Support | EO Engineer | Not Started
Closure | Knowledge Transfer | 10 days | [START_DATE+140] | [START_DATE+150] | Documentation Delivery | EO Project Manager | Not Started
Closure | Project Closure | 2 days | [START_DATE+151] | [START_DATE+153] | Performance Monitoring | EO Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
MS-001 | Project Kickoff Complete | [START_DATE+1] | Project charter approved and team assembled | EO Project Manager | Not Started
MS-002 | Solution Architecture Approved | [START_DATE+18] | Architecture design signed off by stakeholders | EO Quarterback | Not Started
MS-003 | Profile Strategy Approved | [START_DATE+22] | FSLogix profile management design approved | EO Quarterback | Not Started
MS-004 | Azure Infrastructure Ready | [START_DATE+35] | Virtual network and core services operational | EO Engineer | Not Started
MS-005 | Profile Containers Configured | [START_DATE+55] | FSLogix containers tested and validated | EO Engineer | Not Started
MS-006 | Security Validation Complete | [START_DATE+85] | Security controls tested and compliance verified | EO Engineer | Not Started
MS-007 | UAT Sign-off | [START_DATE+100] | Business users approve virtual desktop experience | EO Sales Engineer | Not Started
MS-008 | Production Validation Complete | [START_DATE+107] | Production environment validated and ready | EO Engineer | Not Started
MS-009 | Production Go-Live | [START_DATE+114] | AVD solution live with user access | EO Project Manager | Not Started
MS-010 | Project Closure | [START_DATE+153] | All deliverables accepted and project closed | EO Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | Arch | Eng | Sec | QA | Client IT | Client Sec | Sponsor
Solution Architecture | C | A | R | C | I | C | I | I
Infrastructure Setup | C | R | R | C | I | C | I | I
Configuration & Tuning | A | R | R | C | I | C | I | I
Integration Development | C | A | R | C | I | C | I | I
Testing & Validation | R | R | R | C | A | C | C | I
Security Implementation | C | R | R | A | C | C | A | I
Knowledge Transfer | A | C | C | I | I | A | I | R
Project Management | A | I | I | I | I | C | I | R
Application Packaging | C | R | A | I | C | C | I | I
User Profile Management | C | R | A | I | C | C | I | I
Monitoring Setup | C | R | A | I | C | C | I | I
Network Optimization | C | A | R | C | I | C | I | I
User Access Control | C | R | R | A | I | C | A | I
Performance Testing | R | C | R | I | A | C | I | I
Go-Live Support | A | C | R | C | C | C | I | R
Legend:
R | A C R C A A C C C C C R A: Responsible - Does the work
A | A C R C A A C C C C C R A: Accountable - Ultimate ownership
C | A C R C A A C C C C C R A: Consulted - Provides input
I | A C R C A A C C C C C R A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Executive Status Report | Weekly | Executive Sponsors | AVD project status and decisions | EO Project Manager | Fridays 2PM
Steering Committee | Bi-weekly | Steering Committee Members | Strategic direction and scope decisions | EO Project Manager | Every other Monday 10AM
Development Team Standup | Daily | Core Development Team | Daily coordination and impediment removal | EO Quarterback | Daily 9AM
Architecture Review | Weekly | Technical and Infrastructure Teams | Architecture decisions and optimization | EO Quarterback | Wednesdays 2PM
Risk Review | Bi-weekly | Risk Management Team | Risk monitoring and mitigation | EO Quarterback | Every other Thursday 3PM
Business User Feedback | Weekly | Desktop Users and Managers | Requirements validation and feedback | EO Sales Engineer | Tuesdays 1PM
Sprint Review | Bi-weekly | Development Team | Infrastructure progress demonstration | EO Quarterback | Every other Friday 10AM
Microsoft Support Call | Weekly | Microsoft Technical Teams | Service optimization coordination | EO Engineer | Thursdays 11AM
User Experience Review | Weekly | QA and User Representatives | Performance and satisfaction validation | EO Quarterback | Wednesdays 10AM
Change Control Board | As Needed | Change Control Board Members | Configuration change approvals | EO Engineer | As Required
Security Review | Monthly | Security and Compliance Teams | Security posture and compliance | EO Quarterback | First Monday 2PM
Go-Live Preparation | Daily (Pre-Launch) | Go-Live Team | Production deployment readiness | EO Project Manager | Daily 8AM
Post-Implementation Review | Monthly (Post-Launch) | Project and Operations Teams | Performance review and optimization | EO Quarterback | Monthly 1PM