## Cover
[DOCUMENT TITLE]
Level of Effort
GOOGLE - Modern-Workspace - Workspace
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
User Base | User Count | 500 licensed users | 100 users | 500 users | 2000+ users | Total Google Workspace licenses
User Base | Workspace Edition | Business Plus | Business Standard | Business Plus | Enterprise Plus | Feature tier and storage capacity
Migration | Email Migration | 500 mailboxes (2.5 TB) | 100 mailboxes | 500 mailboxes | 2000+ mailboxes | Exchange to Gmail migration volume
Migration | File Migration | File servers to Drive (3 TB) | 1 TB | 3 TB | 10+ TB | Document migration complexity
Integration | Identity Integration | SAML SSO with Azure AD | Basic auth | SAML SSO | Federated + directory sync | Authentication complexity
Integration | Distribution Lists | 150 groups | 50 groups | 150 groups | 500+ groups | Email group migration count
Security | DLP Policies | Sensitive content detection | Basic DLP | Standard DLP | Advanced DLP + custom | Data loss prevention complexity
Security | Mobile Management | Advanced mobile device management | Basic MDM | Advanced MDM | Enterprise EMM | Mobile security requirements
Compliance | Retention Policy | 7-year retention (Vault) | 3-year retention | 7-year retention | Unlimited + legal hold | Data retention requirements
Deployment | Deployment Approach | Phased by department (5 waves) | Big bang | Phased rollout | Complex multi-phase | Migration strategy complexity
Training | Training Approach | Virtual + self-service | Self-service only | Virtual training | In-person + virtual | User enablement scope
Technical Environment | Coexistence Period | 4 weeks with Exchange | 2 weeks | 4 weeks | 8+ weeks | Parallel operation complexity
Technical Environment | Directory Sync | GCDS for automated provisioning | Manual sync | Automated GCDS | Complex multi-directory | User provisioning automation

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Migration Assessment, Environment Analysis, Training Needs)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Migration Planning, Stakeholder Alignment)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Workspace Configuration, SSO Setup, DLP Policies, Vault Setup, Mobile Management)
Testing | TESTING_MX | 1 | All Testing phase tasks (Pilot Validation, Migration Testing, UAT)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Pilot Migration, Email/File Migration, Group Migration, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Admin Training, End-User Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Hypercare Support)
Management | MANAGEMENT_MX | 1 | Project Management overhead - 20% of actual engineering hours
Leadership | LEADERSHIP_MX | 1 | Quarterback/Technical Leadership overhead - 25% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Migration Assessment | Exchange and file server inventory and migration planning | EO Engineer | 24 |  |  | 200 |  |  | Customer must provide Exchange admin access and mailbox inventory
Discovery | Environment Analysis | Analyze distribution lists groups and calendar complexity | EO Engineer | 16 |  |  | 200 |  |  | Identify migration dependencies and integration requirements
Discovery | Training Needs Assessment | User training requirements and change management planning | EO Engineer | 8 |  |  | 150 |  |  | Define training approach and communication strategy
Development | Workspace Configuration | Google Workspace tenant setup domain verification and OU structure | EO Engineer | 16 |  |  | 175 |  | Migration Assessment | Deliverable: Configured Workspace tenant with organizational units
Development | SSO Integration | SAML SSO setup with Azure AD and directory sync (GCDS) deployment | EO Engineer | 24 |  |  | 200 |  | Workspace Configuration | Includes SAML metadata exchange and GCDS configuration testing
Development | DLP Configuration | Data Loss Prevention policy setup for sensitive content | EO Engineer | 16 |  |  | 175 |  | Workspace Configuration | Configure DLP rules for PII PHI payment data
Development | Vault Setup | Google Vault configuration for 7-year retention and eDiscovery | EO Engineer | 8 |  |  | 150 |  | Workspace Configuration | Setup retention policies and legal hold capabilities
Development | Mobile Management | Advanced mobile device management policy configuration | EO Engineer | 8 |  |  | 150 |  | Workspace Configuration | Configure device policies passcode requirements remote wipe
Deployment | Pilot Migration | Pilot migration of 25 IT and early adopter users | EO Engineer | 24 |  |  | 140 |  | Vault Setup | Validate migration tools workflows and training materials
Deployment | Email Migration Wave 1-5 | Mailbox migration for 475 users in 5 waves (95 users/week) | EO Engineer | 80 |  |  | 140 |  | Pilot Migration | Exchange to Gmail migration with folder structure preservation
Deployment | File Migration | File server to Google Drive migration (3 TB with permissions) | EO Engineer | 48 |  |  | 130 |  | Email Migration Wave 1-5 | Migrate files with ACL to Drive sharing permission mapping
Deployment | Calendar and Contacts | Calendar and contacts migration for all 500 users | EO Engineer | 16 |  |  | 120 |  | Email Migration Wave 1-5 | Preserve recurring appointments and contact deduplication
Deployment | Distribution Lists | Migration of 150 distribution lists to Google Groups | EO Engineer | 16 |  |  | 120 |  | Email Migration Wave 1-5 | Preserve group membership and email addresses
Testing | Pilot Validation | Pilot user testing and workflow validation | EO Engineer | 16 |  |  | 120 |  | Pilot Migration | Validate Gmail Drive Docs Meet functionality with pilot users
Testing | Migration Testing | Data integrity validation and migration quality checks | EO Engineer | 24 |  |  | 130 |  | File Migration | Ensure 100% data migration with zero data loss
Testing | UAT Coordination | User acceptance testing coordination with business stakeholders | EO Engineer | 16 |  |  | 140 |  | Migration Testing | Business validation of collaboration workflows
Training | Administrator Training | Google Admin Console GAM scripting and troubleshooting training | EO Engineer | 16 |  |  | 150 |  | UAT Coordination | Hands-on training for IT administrators
Training | End-User Training | Virtual training sessions for Gmail Drive Docs Meet (10 sessions) | EO Engineer | 40 |  |  | 125 |  | Administrator Training | 2 sessions per migration wave covering core functionality
Training | Training Materials | Custom quick start guides video tutorials and FAQ documentation | EO Engineer | 24 |  |  | 110 |  | End-User Training | Deliverable: Self-service training resources and help documentation
Closeout | Knowledge Transfer | Operations handoff and support procedures documentation | EO Engineer | 8 |  |  | 140 |  | Training Materials | Transfer operational ownership to IT team
Closeout | Hypercare Support | Post-migration support and issue resolution (4 weeks) | EO Engineer | 80 |  |  | 110 |  | Knowledge Transfer | Daily monitoring rapid issue resolution optimization support
Management | Project Management | Project coordination status reporting stakeholder management | EO Project Manager |  |  |  | 150 |  |  | 20% of engineering effort for project management
Management | Technical Leadership | Quarterback oversight migration strategy technical governance | EO Quarterback |  |  |  | 180 |  |  | 25% of engineering effort for technical leadership
|  | TOTAL |  | $E19+$E20+$E21+$E22+$E23+$E24+$E25+$E26+$E27+$E28+$E29+$E30+$E31+$E32+$E33+$E34+$E35+$E36+$E37+$E38+$E39 | [5 empty] | Total Workspace migration implementation

## Credits
Credits
Category | Credit Type | Credit Amount | Credit Comments
Professional Services | Partner Migration Credit | -3000 | Google Workspace partner migration services discount
Software Licenses | New Customer Promotion | -10000 | First 3 months free for new Google Workspace customers (500 users)
Cloud Infrastructure | Infrastructure Credit | 0 | No infrastructure credits available
Support & Maintenance | Support Credit | 0 | No support credits available