# Statement of Work

Google Workspace - Google Workspace Deployment

| Client: | [Client Name] |
| --- | --- |
| Date: | November 22, 2025 |
| Consulting Company: | Your Consulting Company |
| Submitted By: | [Consultant Name ¦ Email ¦ Phone] |
| Opportunity No: | OPP-2025-001 |
| Version: | 1.0 |

# Table of Contents

1 Introduction
    1.1 Purpose
        1.1.1 Scope
2 Table Content
3 Image Section
4 Additional Content
5 Sign-Off

# List of Figures

Figure 1: Sample Architecture Diagram

# List of Tables

Table 1: Sample Deliverables Table

# 1 Executive Summary

This Statement of Work (SOW) defines the scope, deliverables, roles, and terms for deploying Google Workspace for [Client Name]. This engagement will migrate 500 users from Microsoft Exchange and on-premises file servers to Google Workspace Business Plus, enabling cloud-based email, collaboration, and productivity with Gmail, Drive, Docs, and Meet.

Project Duration: 12 weeks

# 2 Background & Objectives

## 2.1 Current State

[Client Name] currently operates Microsoft Exchange 2016 on-premises infrastructure and Windows file servers for document storage. Key challenges include:

• Aging Infrastructure: Exchange servers requiring $180K hardware refresh in next 12 months

• Limited Collaboration: Email attachments and file locking prevent real-time collaboration across remote workforce

• High IT Overhead: 2 FTE dedicated to Exchange and file server maintenance, patching, and backup management

• Poor Mobile Experience: VPN required for remote file access creating productivity barriers for 85% remote workforce

• Storage Limitations: Running out of capacity with $50K annual storage expansion costs

• No Disaster Recovery: Single datacenter with 48-hour RTO exposing business continuity risk

## 2.2 Business Objectives

• Modernize Productivity Suite: Migrate 500 users from Exchange and file servers to Google Workspace (Gmail, Drive, Docs, Meet) eliminating on-premises infrastructure

• Enable Real-Time Collaboration: Replace email attachments and file locking with Google Docs real-time co-editing supporting remote-first workforce

• Reduce IT Costs: Eliminate $180K hardware refresh, reduce ongoing support costs by 40% ($120K annually), and redirect 2 FTE to higher-value projects

• Improve Mobile Experience: Provide seamless mobile access to email, files, and collaboration tools without VPN complexity

• Enhance Business Continuity: Achieve 99.9% uptime SLA with Google's infrastructure eliminating single-point-of-failure risks

• Foundation for AI: Enable future AI capabilities with Gemini for Workspace (post-migration add-on)

## 2.3 Success Metrics

• 95%+ user adoption within 90 days measured by daily active usage

• Zero data loss during email (2.5 TB) and file (3 TB) migration

• 40% reduction in IT support costs ($120K annually) within 12 months

• 10x improvement in document collaboration (10+ simultaneous editors vs. email attachments)

• 99.9% email and file availability (vs. current 95% uptime)

• User satisfaction score 4.5/5 within 60 days post-migration

# 3 Scope of Work

## 3.1 In Scope

The following services and deliverables are included in this SOW:

• Migration planning and environment assessment

• Google Workspace account setup and configuration

• Email migration from Exchange (500 mailboxes, 2.5 TB)

• File migration from file servers to Google Drive (3 TB)

• Calendar and contacts migration

• Distribution list migration to Google Groups (150 groups)

• SAML SSO integration with Azure AD

• Directory sync setup (GCDS) for automated user provisioning

• Data Loss Prevention (DLP) policy configuration

• Google Vault setup for 7-year retention

• Mobile device management configuration

• Administrator and end-user training

• Phased migration support and hypercare

### 3.1.1 Scope Parameters

This engagement is sized based on the following parameters:

| Category | Parameter | Scope |
| --- | --- | --- |
| User Base | User Count | 500 licensed users |
| User Base | Workspace Edition | Business Plus |
| Migration | Email Migration | 500 mailboxes (2.5 TB) |
| Migration | File Migration | File servers to Drive (3 TB) |
| Integration | Identity Integration | SAML SSO with Azure AD |
| Integration | Distribution Lists | 150 groups |
| Security | DLP Policies | Sensitive content detection |
| Security | Mobile Management | Advanced mobile device management |
| Compliance | Retention Policy | 7-year retention (Vault) |
| Deployment | Deployment Approach | Phased by department (5 waves) |
| Training | Training Approach | Virtual + self-service |
| Technical Environment | Coexistence Period | 4 weeks with Exchange |
| Technical Environment | Directory Sync | GCDS for automated provisioning |

Table 1: Engagement Scope Parameters

Table: Engagement Scope Parameters

Note: Changes to these parameters may require scope adjustment and additional investment.

## 3.2 Activities

### 3.2.1 Phase 1 – Discovery & Migration Planning

During this initial phase, the Vendor will perform a comprehensive assessment of the Client's current Exchange environment, file server infrastructure, and migration readiness. This includes analyzing mailbox sizes, file volumes, distribution lists, and designing the optimal migration approach.

Key activities:

• Exchange environment assessment (mailbox count, sizes, public folders)

• File server inventory and permission mapping analysis

• Distribution list and security group documentation

• User training needs assessment and change management planning

• Identity provider integration planning (Azure AD SAML SSO, GCDS)

• Data Loss Prevention (DLP) requirements analysis

• Mobile device management policy definition

• Migration wave planning and user communication strategy

• Google Workspace account provisioning and domain verification

This phase concludes with a Migration Plan that outlines the phased approach, technical migration strategy, training plan, communication templates, and project timeline.

### 3.2.2 Phase 2 – Google Workspace Setup & Configuration

In this phase, the Google Workspace tenant is configured based on security best practices and the Client's compliance requirements. This includes identity integration, security policies, organizational units, and migration tool preparation.

Key activities:

• Google Workspace Business Plus subscription activation

• Domain verification and MX record planning

• Organizational unit structure creation for department-based access

• SAML SSO integration with Azure AD for seamless authentication

• Google Cloud Directory Sync (GCDS) deployment and testing

• Data Loss Prevention (DLP) policy configuration for sensitive data

• Google Vault setup for 7-year email and file retention

• Advanced mobile device management policy deployment

• Admin roles and permissions configuration

• Migration tool setup (Google Workspace Migration Tool - GWMT)

• Pilot user group creation (25 users from IT and early adopters)

By the end of this phase, the Client will have a production-ready Google Workspace environment configured and ready for migration.

### 3.2.3 Phase 3 – Pilot Migration & Validation

A small pilot group (25 users) will be migrated first to validate migration tools, workflows, and training materials before full-scale deployment.

Key activities:

• Pilot user notification and preparation (25 IT and early adopters)

• Mailbox migration for pilot users (Exchange to Gmail)

• File migration for pilot users (file server to Google Drive)

• Calendar and contacts migration

• Distribution list migration to Google Groups

• Google Meet and collaboration tool validation

• Pilot user training sessions (hands-on with Gmail, Drive, Docs, Meet)

• Feedback collection and workflow validation

• Migration tool performance tuning

• Issue identification and resolution before full rollout

Pilot success criteria must be met before proceeding to full migration.

### 3.2.4 Phase 4 – Phased User Migration

Following successful pilot validation, the remaining 475 users will be migrated in 5 waves (approximately 95 users per week) to manage risk and support burden.

Key activities:

• Week 1: Wave 1 - Sales department (95 users)

• Week 2: Wave 2 - Marketing department (95 users)

• Week 3: Wave 3 - Operations department (95 users)

• Week 4: Wave 4 - Finance department (95 users)

• Week 5: Wave 5 - Executive and remaining users (95 users)

• Pre-migration user communication for each wave

• Mailbox migration (Exchange to Gmail) per wave

• File migration (file server to Drive) per wave

• Calendar, contacts, and group migration per wave

• Post-migration validation and issue resolution per wave

• MX record cutover coordination (gradual or big-bang per wave)

• User training sessions (2 sessions per wave)

Cutover will be coordinated with IT team to minimize business disruption, with rollback procedures available if critical issues arise.

### 3.2.5 Phase 5 – Training, Adoption & Hypercare

Following migration completion, the focus shifts to user adoption, training reinforcement, and operational support. The Vendor will provide intensive support during the critical first 30 days to ensure smooth transition.

Activities include:

• End-user training (virtual sessions covering Gmail, Drive, Docs, Meet)

• Administrator training (Google Admin Console, GAM scripting, troubleshooting)

• Self-service training materials (quick start guides, video tutorials)

• Change champion enablement for department support

• User adoption monitoring and reporting

• Issue triage and resolution during hypercare period

• MX record final cutover and Exchange decommissioning planning

• Exchange coexistence period management (4 weeks parallel operation)

• Google Workspace optimization recommendations

• 30-day warranty support for migration-related issues

## 3.3 Out of Scope

These items are not in scope unless added via change control:

• Exchange server decommissioning or hardware disposal

• File server decommissioning or data archiving

• Historical email archiving or PST file migration beyond active mailboxes

• Custom application migration or third-party integration development

• Advanced Gemini for Workspace AI features (available as post-migration add-on)

• Ongoing operational support beyond 30-day warranty period

• Desktop operating system upgrades or hardware provisioning

• Network infrastructure changes or bandwidth upgrades

• Google Workspace licensing costs (billed directly by Google to client)

# 4 Deliverables & Timeline

## 4.1 Deliverables

| # | Deliverable | Type | Due Date | Acceptance By |
| --- | --- | --- | --- | --- |
| 1 | Migration Assessment Report | Document | Week 2 | [Client Lead] |
| 2 | Migration Plan & Communication Templates | Document | Week 3 | [Project Sponsor] |
| 3 | Google Workspace Tenant Configuration | System | Week 4 | [IT Lead] |
| 4 | SSO and Directory Sync Setup | System | Week 4 | [IT Lead] |
| 5 | DLP and Security Policies | System | Week 4 | [Security Lead] |
| 6 | Pilot Migration (25 users) | System | Week 5 | [Pilot Lead] |
| 7 | Pilot Training Materials | Document/Video | Week 5 | [Training Lead] |
| 8 | Wave 1-5 Migrations (475 users) | System | Week 6-10 | [Department Leads] |
| 9 | End-User Training Sessions | Training | Week 5-11 | [User Community] |
| 10 | Administrator Training | Training | Week 11 | [IT Team] |
| 11 | Migration Completion Report | Document | Week 11 | [Client Lead] |
| 12 | Operations Runbook | Document | Week 12 | [IT Lead] |
| 13 | Post-Migration Optimization Guide | Document | Week 12 | [Client Lead] |

Table 2: Project Deliverables and Acceptance Criteria

## 4.2 Project Milestones

| Milestone | Description | Target Date |
| --- | --- | --- |
| M1 | Migration Assessment Complete | Week 2 |
| M2 | Workspace Configured | Week 4 |
| M3 | Pilot Migration Complete | Week 5 |
| M4 | All Waves Migrated | Week 10 |
| M5 | Training Complete | Week 11 |
| Go-Live | MX Record Cutover | Week 10 |
| Hypercare End | Support Period Complete | Week 14 |

Table 3: Project Milestones and Timeline

# 5 Roles & Responsibilities

## 5.1 RACI Matrix

| Task/Role | EO PM | EO Quarterback | EO Sales Eng | EO Eng (Migration) | Client IT | Client Business | SME |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Discovery & Assessment | A | R | R | C | C | R | C |
| Migration Planning | C | A | R | I | I | C | I |
| Workspace Configuration | C | C | R | A | C | I | I |
| Email Migration | C | R | C | A | C | I | I |
| File Migration | C | R | C | A | C | I | I |
| SSO Integration | C | R | I | A | C | I | I |
| Testing & Validation | R | C | R | R | A | A | I |
| End-User Training | A | R | R | C | C | C | I |
| Hypercare Support | A | R | R | R | C | I | I |

Table 4: Roles And Responsibilities

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

## 5.2 Key Personnel

Vendor Team:

• EO Project Manager: Overall delivery accountability

• EO Quarterback: Technical design and migration oversight

• EO Sales Engineer: Solution architecture and pre-sales support

• EO Engineer (Migration): Email and file migration execution

Client Team:

• IT Lead: Primary technical contact and infrastructure access

• Business Lead: User communication and change management

• Department Leads: Wave migration coordination and user support

• Training Lead: Training schedule and materials review

• Operations Team: Knowledge transfer recipients

# 6 Architecture & Design

## 6.1 Architecture Overview

The Google Workspace deployment follows a cloud-first migration architecture replacing on-premises Exchange and file servers with Google's cloud productivity suite. The architecture provides 99.9% uptime SLA, unlimited storage (5 TB per user), and seamless mobile access.

This architecture is designed for 500 users migrating from Exchange 2016 and Windows file servers. The design prioritizes:

• Zero data loss: Validated migration tools with rollback capabilities

• Minimal disruption: Phased migration allowing 4-week coexistence period

• User adoption: Comprehensive training and self-service resources

Figure 1: Solution Architecture Diagram

Figure 1: Solution Architecture Diagram - High-level overview of the Google Workspace migration architecture

## 6.2 Architecture Type

The deployment follows a phased migration approach with temporary coexistence:

• Gradual user migration minimizing disruption

• 4-week coexistence period with Exchange for rollback safety

• Automated directory sync for seamless authentication

• Cloud-based productivity eliminating on-premises infrastructure

Key architectural components include:

• Identity Layer (Cloud Identity Premium, Azure AD SSO, Directory Sync)

• Migration Layer (GWMT for email, Drive File Stream for files)

• Core Applications (Gmail, Drive, Docs, Sheets, Slides, Meet)

• Security Layer (DLP, Vault, Mobile Management)

• Administration Layer (Admin Console, Audit Logs, Reports)

## 6.3 Scope Specifications

User Base:

• 500 Google Workspace Business Plus licenses ($18/user/month)

• 5 TB storage per user (unlimited for orgs 500+ users)

• 300 mobile devices managed via Advanced Mobile Management

Migration Volumes:

• Email: 500 mailboxes totaling 2.5 TB (average 5 GB per mailbox)

• Files: 3 TB from Windows file servers to Google Drive

• Calendar: 500 user calendars with historical appointments

• Contacts: 500 user contact lists

• Distribution Lists: 150 groups migrated to Google Groups

Security & Compliance:

• Data Loss Prevention (DLP) for PII, PHI, payment card data

• Google Vault with 7-year retention for email and files

• Advanced Mobile Management for BYOD and corporate devices

• 2-Step Verification (2SV) enforced for all users

Identity Integration:

• SAML SSO with Azure AD for seamless authentication

• Google Cloud Directory Sync (GCDS) for automated user provisioning

• Password sync disabled (SSO only for security)

Scalability Path:

• Medium scope: Expand to 1,000 users with same architecture

• Large scope: Scale to 5,000+ users (Enterprise edition recommended)

• No architectural changes required - only license count increase

## 6.4 Application Hosting

All productivity applications are cloud-hosted by Google:

• Gmail for business email (99.9% uptime SLA)

• Google Drive for file storage and sync

• Google Docs, Sheets, Slides for real-time collaboration

• Google Meet for video conferencing (up to 500 participants)

• Google Calendar for scheduling

• Google Chat for team messaging

## 6.5 Networking

Workspace is accessed via internet with no VPN required:

• Browser-based access for desktop users

• Mobile apps for iOS and Android devices

• Drive File Stream for file sync and offline access

• Google Workspace Sync for Outlook (optional during coexistence)

## 6.6 Observability

Comprehensive visibility into workspace usage and security:

• Admin Console reports for user adoption and activity

• Audit logs for administrator and user actions

• Security investigation tool for threat detection

• BigQuery exports for advanced analytics (optional)

• Alert center for security and compliance notifications

## 6.7 Backup & Disaster Recovery

Data protection through Google's infrastructure:

• Google's 99.9% uptime SLA with automatic failover

• Data replication across multiple datacenters

• Google Vault for retention and legal hold

• Third-party backup (Spanning, Backupify) optional

• RTO: <1 hour | RPO: Near-zero with cloud sync

## 6.8 Technical Implementation Strategy

The implementation approach follows Google Workspace migration best practices and proven methodologies.

## 6.9 Example Implementation Patterns

• Phased rollout: Pilot with 25 users, then 5 waves of 95 users each

• Coexistence period: 4 weeks parallel operation with Exchange before decommissioning

• Just-in-time training: Train users 1 week before their migration wave

## 6.10 Tooling Overview

| Category | Primary Tools | Purpose |
| --- | --- | --- |
| Email Migration | Google Workspace Migration Tool (GWMT) | Exchange to Gmail migration |
| File Migration | Drive File Stream, Migration for Drive | File server to Drive migration |
| Identity | Cloud Identity Premium, GCDS | SSO and directory sync |
| Security | DLP, Vault, Advanced Mobile Management | Data protection and compliance |
| Administration | Google Admin Console | User and policy management |
| Training | Google Workspace Learning Center | Self-service training resources |
| Monitoring | Admin Console Reports, Audit Logs | Usage and security monitoring |

Table 5: Implementation Tools and Technologies

## 6.11 Data Management

### 6.11.1 Data Strategy

• Email migration via GWMT with label preservation

• File migration with permission mapping (file server ACLs to Drive sharing)

• Calendar migration preserving all appointments and recurring events

• Contact migration with deduplication

• Distribution list migration to Google Groups with membership preservation

### 6.11.2 Data Security & Compliance

• Encryption in transit (TLS 1.2+) and at rest (AES-256)

• Data Loss Prevention (DLP) for sensitive content detection and blocking

• Google Vault for 7-year retention and legal hold capabilities

• Audit trail for all data access via Cloud Audit Logs

• Secure deletion capabilities for GDPR compliance

# 7 Security & Compliance

The implementation and target environment will be architected and validated to meet the Client's security, compliance, and governance requirements. Vendor will adhere to Google Workspace security frameworks and industry best practices.

## 7.1 Identity & Access Management

• Cloud Identity Premium with SAML SSO integration with Azure AD

• 2-Step Verification (2SV) enforced for all user accounts

• Security keys for high-value accounts (executives, admins)

• Password policies aligned with NIST guidelines

• Context-aware access based on device, location, and user attributes

• Admin roles with least-privilege access

## 7.2 Monitoring & Threat Detection

• Security investigation tool for threat detection and response

• Alert center for security and compliance notifications

• Audit logs for all administrative and data access events

• Login challenge for suspicious activity (impossible travel, unusual location)

• Integration with SIEM for centralized security operations (optional)

## 7.3 Compliance & Auditing

• SOC 2 certified Google Workspace infrastructure

• GDPR compliance: Data residency controls, right-to-deletion, audit trail

• HIPAA compliance (if applicable): BAA with Google, encryption, access controls

• Google Vault for eDiscovery and legal hold capabilities

• Continuous compliance monitoring via Admin Console reports

## 7.4 Encryption & Key Management

• All data encrypted at rest using Google-managed encryption keys

• All data encrypted in transit using TLS 1.2+

• Customer-managed encryption keys (CMEK) available via Enterprise Plus edition

• Drive Client-Side Encryption for sensitive files (optional)

## 7.5 Governance

• Data Loss Prevention (DLP) policies for sensitive content

• Mobile device management policies (require passcode, remote wipe)

• External sharing controls (allow with warnings, block, or allow freely)

• Google Drive audit and investigation for file access tracking

• Retention policies via Google Vault (7-year minimum)

• Quarterly access reviews and policy updates

## 7.6 Environments & Access

### 7.6.1 Environment Strategy

| Environment | Purpose | Access |
| --- | --- | --- |
| Production | Live Google Workspace tenant | All users |
| Pilot | Initial 25-user validation group | IT and early adopters |

Table 6: Security And Compliance

### 7.6.2 Access Policies

• 2-Step Verification (2SV) required for all users

• SAML SSO via Azure AD for seamless authentication

• Administrator Access: Super Admin for IT team (MFA required)

• User Access: Standard user roles with Gmail, Drive, Docs, Meet

• Mobile Access: Managed devices only for BYOD policy enforcement

# 8 Testing & Validation

Comprehensive testing and validation will take place throughout the migration lifecycle to ensure functionality, data integrity, security, and user readiness.

## 8.1 Functional Validation

• Email migration accuracy (100% of mailboxes migrated with folder structure)

• File migration accuracy (100% of files migrated with permissions)

• Calendar and contacts migration validation

• Google Groups functionality (distribution list equivalency)

• SSO authentication flow testing

• Mobile app functionality on iOS and Android

## 8.2 Performance & Load Testing

• Email delivery performance validation

• File sync performance (Drive File Stream)

• Google Meet video quality and capacity testing (500 participants)

• Concurrent user load testing (500 users logging in simultaneously)

## 8.3 Security Testing

• DLP policy enforcement validation

• Mobile device management policy testing

• External sharing control validation

• Google Vault retention and legal hold testing

• 2SV enforcement validation

## 8.4 Disaster Recovery & Resilience Tests

• Backup and restore validation (third-party backup if implemented)

• Data recovery from Google Vault

• Account recovery procedures

## 8.5 User Acceptance Testing (UAT)

• Performed with pilot group (25 users)

• Email, calendar, file access validation

• Collaboration workflow testing (Docs real-time editing)

• Mobile experience validation

• Training materials validation

## 8.6 Go-Live Readiness

A Go-Live Readiness Checklist will be delivered including:

• Pilot migration successful (25 users)

• Data integrity validation (100% data migrated)

• Security policies active (DLP, Vault, mobile management)

• SSO authentication working

• Training materials complete

• Helpdesk prepared with runbook

• Communication templates approved

## 8.7 Cutover Plan

The cutover to Google Workspace will be executed using a controlled, phased approach to minimize business disruption and ensure seamless transition from Exchange and file servers.

Cutover Approach:

The implementation follows a phased migration strategy with 5 waves of approximately 95 users each:

1. Pilot Phase (Week 5): Migrate 25 IT and early adopters

• Validate migration tools and workflows

• Test SSO, email, file access, and collaboration

• Collect feedback and refine processes

• No MX record change (mail continues flowing to Exchange)

2. Wave 1 - Sales (Week 6): Migrate 95 sales team users

• Pre-migration communication sent 1 week prior

• Mailbox and file migration over weekend

• MX record updated for sales domain (optional per-department cutover)

• Training session Monday following migration

• Monitor for issues and provide intensive support

3. Waves 2-5 (Weeks 7-10): Marketing, Operations, Finance, Executive

• Repeat process for each department (95 users per week)

• Gradual MX record cutover per wave or final cutover after all waves

• Training sessions scheduled per wave

• Continuous monitoring and support

4. Coexistence Period (4 weeks): Exchange and Workspace run in parallel

• Mail flow to both systems during transition

• Users can access old Exchange emails if needed

• Gradual decommissioning of Exchange after all migrations complete

5. Hypercare Period (4 weeks post-final-cutover): Daily monitoring and intensive support

The cutover will be executed during approved maintenance windows (weekends recommended) with documented rollback procedures available if critical issues arise.

## 8.8 Cutover Checklist

• Pre-cutover validation: Pilot success, data integrity confirmed

• Workspace environment validated and security policies active

• Rollback procedures documented (revert MX records, maintain Exchange)

• Stakeholder communication completed (email templates, FAQ, training invites)

• Execute migration wave (mailbox, files, calendar, contacts)

• Verify migration completion and data integrity

• Update MX records for email flow cutover

• Monitor email delivery and user access

• Daily health checks during hypercare (4 weeks)

## 8.9 Rollback Strategy

• Documented rollback triggers (>10% mailbox failures, critical data loss, authentication failures)

• Rollback procedures: Revert MX records to Exchange, maintain coexistence

• Root cause analysis and fix validation before retry

• Communication plan for stakeholders

• Preserve all logs and migration reports for analysis

# 9 Handover & Support

## 9.1 Handover Artifacts

• Migration completion report with statistics (mailboxes, files, users migrated)

• Google Workspace configuration documentation (SSO, DLP, Vault, mobile policies)

• Operations runbook with troubleshooting procedures

• User training materials (quick start guides, video tutorials)

• Admin training materials (Google Admin Console, GAM scripting)

• Change management and communication templates

• Post-migration optimization recommendations

## 9.2 Knowledge Transfer

• Live knowledge transfer sessions for IT administrators

• Google Admin Console management training

• Google Vault and eDiscovery training

• Mobile device management policy administration

• End-user support and helpdesk training

• Recorded training materials hosted in shared portal

• Documentation portal with searchable content

## 9.3 Hypercare Support

Post-implementation support to ensure smooth transition to Google Workspace:

Duration: 4 weeks post-final-cutover (30 days)

Coverage:

• Business hours support (8 AM - 6 PM local time)

• 4-hour response time for critical issues

• Daily health check calls (first 2 weeks)

• Weekly status meetings

Scope:

• Migration issue resolution (missing emails, file permissions)

• User access and authentication troubleshooting

• Google Workspace feature questions

• Training reinforcement and tips

• Performance optimization

• Exchange coexistence support

## 9.4 Managed Services Transition (Optional)

Post-hypercare, Client may transition to ongoing managed services:

Managed Services Options:

• 24/7 helpdesk support for Google Workspace users

• Proactive optimization and feature enablement

• User onboarding and offboarding automation

• Security policy updates and compliance monitoring

• Monthly usage and adoption reporting

• Google Workspace license management

Transition Approach:

• Evaluation of managed services requirements during hypercare

• Service Level Agreement (SLA) definition for support

• Separate managed services contract and pricing

• Seamless transition from hypercare to managed services

## 9.5 Assumptions

### 9.5.1 General Assumptions

• Client will provide Exchange admin access and file server access for migration assessment

• Network bandwidth sufficient for 2.5 TB email + 3 TB file migration over 8-week period

• Azure AD tenant available for SAML SSO integration with metadata provided

• Client technical team available for requirements validation, testing, and approvals

• Google Workspace Business Plus licenses provisioned within 1 week of project start

• Pilot users (25) identified and available for pilot migration in Week 5

• Department leads available for wave migration coordination and user communication

• Users have modern web browsers (Chrome, Firefox, Safari, Edge) and internet access

• Mobile devices supported by Google Workspace (iOS 14+, Android 8+)

• Client will handle Google Workspace licensing costs directly with Google

• Exchange and file servers remain operational throughout migration period (4 weeks coexistence minimum)

## 9.6 Dependencies

### 9.6.1 Project Dependencies

• Google Workspace Account: Client provides billing information for Google Workspace subscription

• Exchange Access: Client provides Exchange admin credentials and mailbox access for migration

• File Server Access: Client provides file server admin access and migration source paths

• Azure AD Integration: Client provides Azure AD tenant and SAML metadata for SSO configuration

• Network Bandwidth: Adequate bandwidth for 5.5 TB migration over 8-week period (estimated 100 Mbps sustained)

• Pilot Users: 25 IT and early adopter users identified and available for pilot in Week 5

• Department Leads: Business leaders available for wave migration planning and user communication

• MX Record Changes: Client DNS admin available for MX record updates during cutover

• User Communication: Client approvals for migration communication templates and training schedules

• Go-Live Approval: Business and technical approval authority available for production cutover decision

# 10 Investment Summary

500 User Deployment: This pricing reflects a migration for 500 users from Exchange and file servers to Google Workspace Business Plus. For larger enterprise deployments (1,000+ users), please request revised pricing.

## 10.1 Total Investment

| Cost Category | Year 1 List | AWS/Partner Credits | Year 1 Net | Year 2 | Year 3 | 3-Year Total |
| --- | --- | --- | --- | --- | --- | --- |
| Professional Services | $38,400 | ($3,000) | $35,400 | $0 | $0 | $35,400 |
| Software Licenses | $115,200 | ($10,000) | $105,200 | $115,200 | $115,200 | $335,600 |
| TOTAL INVESTMENT | $153,600 | ($13,000) | $140,600 | $115,200 | $115,200 | $371,000 |

Table 7: Total Investment Summary

## 10.2 Partner Credits

Year 1 Credits Applied: $13,000 (8% reduction)

• Google Workspace New Customer Promotion: $10,000 (first 3 months free for 500 users)

• Partner Migration Services Credit: $3,000 applied to professional services

• Credits are real account credits, automatically applied to subscription

• Credits are Year 1 only; Years 2-3 reflect standard Google Workspace pricing

Investment Comparison:

• Year 1 Net Investment: $140,600 (after credits) vs. $153,600 list price

• 3-Year Total Cost of Ownership: $371,000

• Expected ROI: 24 month payback based on $180K infrastructure avoidance and $120K annual IT cost reduction

## 10.3 Cost Components

Professional Services ($38,400 - 192 hours): Labor costs for migration planning, execution, training, and support. Breakdown:

• Migration Planning & Assessment (40 hours): Exchange/file server analysis, migration design

• Workspace Configuration (32 hours): Tenant setup, SSO, DLP, Vault, mobile management

• Email & File Migration (80 hours): 500 mailbox migration, 3 TB file migration, validation

• Training & Support (40 hours): Admin training, end-user training, hypercare support

Software Licenses ($115,200/year): Google Workspace Business Plus for 500 users

• 500 users × $18/user/month × 12 months = $108,000

• Cloud Identity Premium for 100 admins: $600/year

• Third-party backup (optional): $6,600/year (Spanning Backup at $1.10/user/month)

Support & Maintenance ($0/year): Google Workspace includes support

• Business Plus includes Google support

• No additional support costs

## 10.4 Payment Terms

### 10.4.1 Pricing Model

• Fixed price for professional services

• Milestone-based payments per Deliverables table

### 10.4.2 Payment Schedule

• 25% upon SOW execution and project kickoff

• 30% upon pilot migration completion (Week 5)

• 30% upon all waves migrated (Week 10)

• 15% upon training completion and project acceptance (Week 12)

## 10.5 Invoicing & Expenses

### 10.5.1 Invoicing

• Milestone-based invoicing per Payment Terms above

• Net 30 payment terms

• Invoices submitted upon milestone completion and acceptance

### 10.5.2 Expenses

• Google Workspace licensing costs are included in Software Licenses pricing ($115,200/year = $9,600/month for 500 users)

• Costs scale with user count - can increase/decrease based on hiring/attrition

• Travel and on-site expenses reimbursable at cost with prior approval (remote-first delivery model)

# 11 Terms & Conditions

## 11.1 General Terms

All services will be delivered in accordance with the executed Master Services Agreement (MSA) or equivalent contractual document between Vendor and Client.

## 11.2 Scope Changes

• Changes to user count, migration volumes, or timeline require formal change requests

• Change requests may impact project timeline and budget

## 11.3 Intellectual Property

• Client retains ownership of all business data (emails, files, contacts)

• Vendor retains ownership of proprietary methodologies and migration tools

• Google Workspace configurations become Client property upon final payment

## 11.4 Service Levels

• Migration data integrity: 100% of emails and files migrated with zero data loss

• Google Workspace uptime: 99.9% SLA (guaranteed by Google)

• 30-day warranty on all migration deliverables from go-live date

• Post-warranty support available under separate managed services agreement

## 11.5 Liability

• Migration follows Google Workspace best practices and proven methodologies

• Performance may vary based on network bandwidth and Exchange server performance

• Ongoing user training recommended as Google Workspace features evolve

• Liability caps as agreed in MSA

## 11.6 Confidentiality

• Both parties agree to maintain strict confidentiality of business data and proprietary techniques

• All exchanged artifacts under NDA protection

## 11.7 Termination

• Mutually terminable per MSA terms, subject to payment for completed work

## 11.8 Governing Law

• Agreement governed under the laws of [State/Region]

# 12 Sign-Off

By signing below, both parties agree to the scope, approach, and terms outlined in this Statement of Work.

| CLIENT | CONSULTING COMPANY |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Title: ___________________________ | Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

eoframework.org