## Cover
Test Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Disaster Recovery Web Application
Customer Name: | Data table for test plan
Version: | 1.0

## Test Plan
Test ID | Test Category | Test Type | Test Name | Description | Pre-conditions | Test Steps | Expected Results | Priority | Environment | Assigned Tester | Status | Execution Date | Actual Results | Pass/Fail | Notes | Requirements Traced
DR-001 | Network | Unit | VPN Connectivity | Validate VPN connection between regions | VPN configured, test endpoints available | 1. Ping primary region endpoint 2. Test traceroute to DR region 3. Verify bandwidth with iperf3 4. Check latency measurements | VPN connectivity stable with <100ms latency | Critical | Unit Test | Network Engineer | Not Started | [DATE] |  |  | Network infrastructure validated | REQ-NET-001
DR-002 | Network | Unit | Direct Connect Testing | Validate Direct Connect performance and failover | Direct Connect configured | 1. Test primary DX connection 2. Monitor bandwidth utilization 3. Simulate DX failure 4. Verify backup connectivity | Direct Connect maintains SLA with backup failover | Critical | Unit Test | Network Engineer | Not Started | [DATE] |  |  | DX redundancy configured | REQ-NET-002
DR-003 | DNS | Integration | Route 53 Health Checks | Validate DNS health check functionality | Route 53 configured with health checks | 1. Monitor primary endpoint health 2. Simulate endpoint failure 3. Verify health check detection 4. Confirm DNS failover timing | Health checks detect failure within 30 seconds | Critical | Integration Test | DNS Engineer | Not Started | [DATE] |  |  | DNS failover configured | REQ-DNS-001
DR-004 | DNS | Integration | DNS Failover Testing | Validate automatic DNS failover behavior | Primary and DR endpoints configured | 1. Query DNS resolution for primary 2. Simulate primary failure 3. Monitor DNS resolution changes 4. Verify traffic routing to DR | DNS fails over to DR region within RTO target | Critical | Integration Test | DNS Engineer | Not Started | [DATE] |  |  | Failover timing meets RTO | REQ-DNS-002
DR-005 | Database | Integration | RDS Replication Setup | Validate cross-region read replica functionality | Primary RDS instance running | 1. Create cross-region read replica 2. Monitor replication lag 3. Verify data consistency 4. Test read operations on replica | Read replica lag consistently <60 seconds | Critical | Integration Test | Database Engineer | Not Started | [DATE] |  |  | Replication meets RPO target | REQ-DB-001
DR-006 | Database | System | Data Consistency Validation | Validate data consistency between primary and replica | RDS replication active | 1. Insert test data in primary 2. Wait for replication 3. Compare checksums between regions 4. Verify row counts match | 100% data consistency between primary and replica | Critical | System Test | Database Engineer | Not Started | [DATE] |  |  | Data integrity maintained | REQ-DB-002
DR-007 | Database | System | Database Promotion Testing | Validate read replica promotion to primary | Read replica configured | 1. Stop writes to primary 2. Promote read replica to primary 3. Test write operations on promoted instance 4. Verify application connectivity | Replica promotes successfully with <5 minute downtime | Critical | System Test | Database Engineer | Not Started | [DATE] |  |  | Database promotion automated | REQ-DB-003
DR-008 | Storage | Integration | S3 Cross-Region Replication | Validate S3 replication between regions | S3 buckets configured with CRR | 1. Upload test files to primary bucket 2. Monitor replication status 3. Verify files in DR bucket 4. Compare file integrity | Files replicate within 15 minutes with 100% integrity | High | Integration Test | Storage Engineer | Not Started | [DATE] |  |  | S3 replication meets RPO | REQ-S3-001
DR-009 | Storage | System | S3 Versioning and Lifecycle | Validate S3 versioning and lifecycle policies | S3 versioning enabled | 1. Upload file versions 2. Verify version management 3. Test lifecycle transitions 4. Validate deletion protection | Versioning works correctly with lifecycle policies | Medium | System Test | Storage Engineer | Not Started | [DATE] |  |  | Data protection implemented | REQ-S3-002
DR-010 | Application | Integration | Health Check Endpoints | Validate application health check functionality | Applications deployed in both regions | 1. Test /health endpoint in primary 2. Test /health endpoint in DR 3. Simulate application failure 4. Verify health check response | Health checks accurately reflect application status | Critical | Integration Test | Application Engineer | Not Started | [DATE] |  |  | Health monitoring configured | REQ-APP-001
DR-011 | Application | System | Cross-Region Load Testing | Validate application performance across regions | Load testing tools configured | 1. Execute load test on primary 2. Execute load test on DR 3. Compare response times 4. Analyze throughput metrics | DR region performance within 20% of primary | High | System Test | Performance Engineer | Not Started | [DATE] |  |  | Performance parity achieved | REQ-APP-002
DR-012 | Application | UAT | Application Functionality Testing | Validate core application features in DR region | Application deployed in DR region | 1. Test user authentication 2. Test core business functions 3. Test API endpoints 4. Verify database operations | All critical functions work correctly in DR region | Critical | UAT | QA Engineer | Not Started | [DATE] |  |  | Full functionality validated | REQ-APP-003
DR-013 | Compute | System | Auto Scaling Testing | Validate auto scaling in DR region | ASG configured in DR region | 1. Scale up DR instances 2. Monitor scaling metrics 3. Test application availability 4. Verify load distribution | Auto scaling responds to demand within 5 minutes | High | System Test | Infrastructure Engineer | Not Started | [DATE] |  |  | Auto scaling configured | REQ-COMPUTE-001
DR-014 | Compute | Integration | Instance Health Monitoring | Validate EC2 instance health checks | Instances running in both regions | 1. Monitor instance health 2. Simulate instance failure 3. Verify replacement behavior 4. Test application resilience | Failed instances replaced within target time | High | Integration Test | Infrastructure Engineer | Not Started | [DATE] |  |  | Instance management automated | REQ-COMPUTE-002
DR-015 | Security | System | Cross-Region Security Validation | Validate security controls in DR region | Security groups and NACLs configured | 1. Test security group rules 2. Verify encryption in transit 3. Test encryption at rest 4. Validate access controls | Security controls consistent across regions | Critical | System Test | Security Engineer | Not Started | [DATE] |  |  | Security parity maintained | REQ-SEC-001
DR-016 | Security | Integration | SSL Certificate Validation | Validate SSL certificates for DR endpoints | SSL certificates configured | 1. Test primary region SSL 2. Test DR region SSL 3. Verify certificate chain 4. Check expiration dates | SSL certificates valid and properly configured | Critical | Integration Test | Security Engineer | Not Started | [DATE] |  |  | SSL coverage complete | REQ-SEC-002
DR-017 | Monitoring | Integration | CloudWatch Alarms Testing | Validate monitoring and alerting in DR scenario | CloudWatch alarms configured | 1. Trigger test alarm conditions 2. Verify alarm notifications 3. Test escalation procedures 4. Validate metric collection | Alarms trigger correctly with proper notifications | High | Integration Test | Operations Engineer | Not Started | [DATE] |  |  | Monitoring coverage complete | REQ-MON-001
DR-018 | Monitoring | System | Cross-Region Metrics Collection | Validate metrics collection across regions | Monitoring tools deployed | 1. Monitor primary region metrics 2. Monitor DR region metrics 3. Compare metric accuracy 4. Test dashboard functionality | Metrics collected accurately from both regions | High | System Test | Operations Engineer | Not Started | [DATE] |  |  | Monitoring parity achieved | REQ-MON-002
DR-019 | DR Process | System | Planned Failover Test | Execute complete planned failover procedure | All components deployed and tested | 1. Scale up DR region 2. Promote database replica 3. Update DNS to point to DR 4. Validate application availability | Complete failover within 15-minute RTO target | Critical | System Test | DR Team Lead | Not Started | [DATE] |  |  | RTO target achieved | REQ-DR-001
DR-020 | DR Process | System | Automated Failover Test | Test automated failover using Lambda function | Failover automation deployed | 1. Trigger Lambda failover function 2. Monitor automation progress 3. Verify all components fail over 4. Test application accessibility | Automated failover completes within RTO | Critical | System Test | DR Team Lead | Not Started | [DATE] |  |  | Automation functioning correctly | REQ-DR-002
DR-021 | DR Process | System | Failback Testing | Validate failback procedure to primary region | DR region active and stable | 1. Prepare primary region 2. Reverse DNS to primary 3. Demote DR database 4. Scale down DR infrastructure | Failback completes successfully without data loss | Critical | System Test | DR Team Lead | Not Started | [DATE] |  |  | Failback procedure validated | REQ-DR-003
DR-022 | Performance | System | RTO Measurement | Measure actual Recovery Time Objective | Monitoring tools configured for timing | 1. Record start of outage 2. Execute failover procedure 3. Measure time to application availability 4. Document actual vs target RTO | Actual RTO meets or exceeds 15-minute target | Critical | System Test | Performance Engineer | Not Started | [DATE] |  |  | RTO compliance verified | REQ-PERF-001
DR-023 | Performance | System | RPO Measurement | Measure actual Recovery Point Objective | Data generation tools configured | 1. Generate continuous test data 2. Simulate failure scenario 3. Measure data loss window 4. Compare to 60-minute RPO target | Actual RPO meets or exceeds 60-minute target | Critical | System Test | Data Engineer | Not Started | [DATE] |  |  | RPO compliance verified | REQ-PERF-002
DR-024 | Performance | System | Load Testing During DR | Validate performance during DR scenario | Load testing tools and DR environment ready | 1. Execute baseline load test 2. Trigger DR scenario 3. Continue load testing 4. Compare performance metrics | Performance degradation <20% during DR operation | High | System Test | Performance Engineer | Not Started | [DATE] |  |  | DR performance acceptable | REQ-PERF-003
DR-025 | Compliance | System | Data Encryption Validation | Validate encryption compliance in DR scenario | Encryption keys and policies configured | 1. Verify encryption at rest in DR 2. Validate encryption in transit 3. Test key management 4. Check compliance with standards | All data encrypted per compliance requirements | Critical | System Test | Compliance Officer | Not Started | [DATE] |  |  | Encryption compliance maintained | REQ-COMP-001
DR-026 | Compliance | System | Audit Trail Validation | Validate audit logging during DR operations | Audit logging configured | 1. Execute DR procedures 2. Review generated audit logs 3. Verify log completeness 4. Test log integrity | Complete audit trail maintained during DR | Critical | System Test | Compliance Officer | Not Started | [DATE] |  |  | Audit compliance maintained | REQ-COMP-002
DR-027 | Operational | System | Backup Verification | Validate backup integrity and restore capability | Backup systems configured | 1. Verify automated backup completion 2. Test backup integrity checks 3. Execute test restore procedure 4. Validate restored data accuracy | Backups complete and restorable within SLA | High | System Test | Backup Engineer | Not Started | [DATE] |  |  | Backup reliability confirmed | REQ-OPS-001
DR-028 | Operational | Integration | Runbook Validation | Validate DR procedure documentation and execution | DR runbooks documented | 1. Follow documented procedures 2. Note any deviations or issues 3. Verify procedure completeness 4. Update documentation as needed | Runbooks accurate and enable successful DR execution | High | Integration Test | Operations Manager | Not Started | [DATE] |  |  | Documentation accuracy verified | REQ-OPS-002
DR-029 | Operational | System | Team Coordination Testing | Validate team communication and coordination during DR | DR team members identified and trained | 1. Execute DR simulation exercise 2. Test communication channels 3. Verify role clarity 4. Assess decision-making process | Teams coordinate effectively during DR scenarios | Medium | System Test | DR Manager | Not Started | [DATE] |  |  | Team readiness validated | REQ-OPS-003
DR-030 | End-to-End | System | Complete DR Scenario Test | Execute full end-to-end DR test including all components | All systems deployed and individual tests passed | 1. Simulate complete regional failure 2. Execute all failover procedures 3. Validate all systems and applications 4. Measure complete recovery time | Complete DR capability validated within all targets | Critical | System Test | DR Program Manager | Not Started | [DATE] |  |  | Full DR capability proven | REQ-E2E-001