## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Document Intelligence
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Stakeholder_Group | Communication_Type | Frequency | Method | Content_Focus | Responsible_Party | Audience_Size | Timing | Template_Used | Success_Metrics | Escalation_Required
Executive Sponsors | Status Reports | Weekly | Email + Dashboard | High-level progress budget risks and decisions | EO Project Manager | 3-5 | Friday EOD | Executive Status Template | Executive engagement and decision speed | Yes - for budget or scope issues
Executive Sponsors | Milestone Reviews | At Milestones | Presentation | Major milestone completion next phase planning | EO Quarterback | 5-8 | End of each phase | Milestone Review Template | Milestone approval and continued sponsorship | Yes - for major issues
Project Steering Committee | Steering Committee Meetings | Bi-weekly | Video Conference | Detailed progress issues risks and resource needs | EO Project Manager | 8-12 | Every other Tuesday 2pm | Steering Committee Agenda | Issue resolution and resource allocation | No - unless strategic decisions needed
Project Team | Team Standup Meetings | Daily | Video Conference | Daily progress blockers and coordination | EO Engineer | 10-15 | Daily 9am | Standup Meeting Format | Team coordination and productivity | No - escalate through project manager
Project Team | Sprint Planning | Bi-weekly | Workshop | Sprint goals task assignment and capacity planning | EO Engineer | 8-12 | Every other Wednesday | Sprint Planning Template | Sprint commitment and delivery | No - unless capacity issues
Project Team | Sprint Reviews | Bi-weekly | Demonstration | Sprint deliverable demo feedback and next steps | EO Quarterback | 8-15 | Every other Friday | Sprint Review Template | Stakeholder satisfaction and feedback quality | No - unless delivery issues
Technical Teams | Architecture Reviews | Weekly | Technical Session | Architecture decisions technical blockers and solutions | EO Quarterback | 5-8 | Thursday 10am | Architecture Review Template | Technical decisions and issue resolution | Yes - for architectural conflicts
Technical Teams | Technical Deep Dives | As Needed | Workshop | Deep technical discussions problem solving | EO Quarterback | 3-6 | Scheduled as needed | Technical Deep Dive Template | Technical problem resolution | No - unless impacts timeline
Business Stakeholders | Business Update Meetings | Monthly | Presentation | Business value progress user readiness and change impact | EO Sales Engineer | 10-20 | First Tuesday of month | Business Update Template | Business alignment and support | Yes - for scope or requirement changes
Business Stakeholders | User Readiness Updates | Bi-weekly | Email + Meeting | Training progress change management and go-live preparation | EO Engineer | 15-25 | Every other Thursday | User Readiness Template | User adoption metrics and readiness score | Yes - for low adoption scores
End Users | Town Hall Meetings | Monthly | All-hands Meeting | Solution progress upcoming changes and training opportunities | EO Project Manager | 50-100 | Third Friday of month | Town Hall Template | User awareness and engagement level | No - address concerns in Q&A
End Users | Training Announcements | As Needed | Email + Intranet | Training schedule registration information and preparation | EO Engineer | All end users | 2 weeks before training | Training Announcement Template | Training registration and attendance rates | No - follow up individually
IT Operations | Operations Readiness Meetings | Weekly | Technical Meeting | Infrastructure readiness monitoring setup and support preparation | EO Engineer | 8-12 | Wednesday 3pm | Operations Readiness Template | Operational readiness score and issue resolution | Yes - for infrastructure issues
IT Operations | Go-Live Preparation | Daily (final 2 weeks) | Daily Standup | Go-live preparation issue resolution and readiness validation | EO Project Manager | 10-15 | Daily 8am (final 2 weeks) | Go-Live Prep Template | Go-live readiness and issue count | Yes - for blocking issues
Security Team | Security Reviews | Bi-weekly | Security Assessment | Security implementation compliance validation and risk assessment | EO Quarterback | 5-8 | Every other Monday | Security Review Template | Security compliance and risk mitigation | Yes - for security vulnerabilities
Compliance Team | Compliance Updates | Monthly | Compliance Review | Compliance status audit readiness and regulatory alignment | EO Engineer | 3-5 | Second Monday of month | Compliance Update Template | Compliance score and audit readiness | Yes - for compliance gaps
Vendor Partners | Vendor Coordination Calls | Weekly | Conference Call | Vendor support escalations and technical coordination | EO Engineer | 5-10 | Tuesday 11am | Vendor Coordination Template | Issue resolution and support quality | Yes - for vendor performance issues
Quality Assurance | QA Status Meetings | Weekly | Technical Meeting | Test progress defect status and quality metrics | EO Engineer | 6-10 | Monday 2pm | QA Status Template | Quality metrics and defect resolution rate | Yes - for quality gate failures
Training Team | Training Coordination | Weekly | Planning Meeting | Training schedule content development and delivery planning | EO Engineer | 4-8 | Friday 10am | Training Coordination Template | Training readiness and user competency | No - unless training delays
External Stakeholders | Client Updates | Monthly | Formal Presentation | Project progress business benefits and upcoming milestones | EO Project Manager | 10-15 | Last Friday of month | Client Update Template | Client satisfaction and continued support | Yes - for relationship issues
Regulatory Bodies | Compliance Reporting | Quarterly | Formal Report | Compliance status audit results and regulatory alignment | EO Engineer | 2-3 | End of each quarter | Compliance Report Template | Regulatory approval and compliance score | Yes - for regulatory concerns
Board of Directors | Board Updates | Quarterly | Executive Briefing | Strategic progress ROI realization and business impact | EO Engineer | 8-12 | Board meeting schedule | Board Update Template | Board support and strategic alignment | Yes - for strategic issues
Emergency Communications | Crisis Communications | As Needed | Multiple Channels | Critical issues immediate actions and impact communication | EO Project Manager | All stakeholders | Within 2 hours of crisis | Crisis Communication Template | Speed of communication and issue resolution | Automatic - for all crisis situations
Project Closure | Lessons Learned Session | At Project End | Workshop | Project retrospective lessons learned and improvement recommendations | EO Project Manager | All team members | Within 1 week of closure | Lessons Learned Template | Quality of insights and improvement adoption | No - unless organizational learning issues
Knowledge Transfer | Documentation Handover | At Phase Completion | Document Review | Technical documentation operational procedures and knowledge transfer | EO Quarterback | 5-10 | End of each major phase | Knowledge Transfer Template | Documentation completeness and team readiness | No - unless knowledge gaps identified