## Cover
Test Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Enterprise Landing Zone
Customer Name: | Data table for test plan
Version: | 1.0

## Test Plan
Test_Phase | Test_Category | Test_ID | Test_Name | Description | Prerequisites | Test_Steps | Expected_Result | Pass_Criteria | Priority | Estimated_Duration | Responsible_Team | Environment | Test_Data_Required
Unit Testing | Component Testing | UT001 | Form Recognizer Service Connectivity | Verify Form Recognizer service endpoint accessibility and authentication | Form Recognizer service deployed with valid credentials | 1. Initialize Form Recognizer client with endpoint and key\n2. Attempt to connect to service\n3. Verify authentication success | Service connection established successfully | HTTP 200 response and valid service metadata | High | 15 minutes | Development Team | Dev | Valid API credentials
Unit Testing | Component Testing | UT002 | Storage Account Access | Test storage account connectivity and container operations | Storage account created with required containers | 1. Connect to storage account using connection string\n2. List containers\n3. Attempt to upload test file\n4. Verify file upload success | All storage operations complete successfully | Container access successful and file upload confirmed | High | 20 minutes | Development Team | Dev | Test documents (PDF JPG)
Unit Testing | Component Testing | UT003 | Key Vault Secret Retrieval | Validate Key Vault access and secret retrieval functionality | Key Vault configured with required secrets and access policies | 1. Authenticate using managed identity\n2. Retrieve Form Recognizer endpoint secret\n3. Retrieve Form Recognizer key secret\n4. Verify secret values are valid | All secrets retrieved successfully with correct values | Secrets returned without errors and contain expected values | High | 10 minutes | Development Team | Dev | Key Vault with test secrets
Unit Testing | Function Testing | UT004 | Document Processing Function | Test core document processing logic with valid input | Function app deployed with processing function | 1. Prepare test document (invoice PDF)\n2. Call processing function with document URI\n3. Wait for processing completion\n4. Verify extracted data structure | Function returns structured data with confidence scores | Processing completes within timeout with >90% confidence | High | 30 minutes | Development Team | Dev | Sample invoice PDF files
Unit Testing | Function Testing | UT005 | Error Handling Validation | Test function error handling with invalid inputs | Processing function deployed and accessible | 1. Submit invalid document format\n2. Submit corrupted file\n3. Submit empty file\n4. Verify appropriate error responses | Function handles errors gracefully with descriptive messages | Error responses contain proper HTTP codes and error details | Medium | 25 minutes | Development Team | Dev | Invalid/corrupted test files
Integration Testing | End-to-End Testing | IT001 | Document Upload to Processing | Test complete workflow from upload to processing completion | Full solution deployed with all components | 1. Upload document to input container\n2. Trigger processing workflow\n3. Monitor processing status\n4. Verify document moves to processed container | Document successfully processed and moved to appropriate container | Document in processed container with extracted data | High | 45 minutes | QA Team | Test | Various document types
Integration Testing | End-to-End Testing | IT002 | Multi-Document Batch Processing | Test processing multiple documents simultaneously | Solution configured for batch processing | 1. Upload 10 different documents\n2. Trigger batch processing\n3. Monitor all document processing\n4. Verify all documents processed correctly | All documents processed successfully within expected timeframe | 90% success rate within 5 minutes | High | 60 minutes | QA Team | Test | Batch of 10-20 test documents
Integration Testing | End-to-End Testing | IT003 | ERP System Integration | Test integration with enterprise ERP system | ERP system available and integration configured | 1. Process invoice document\n2. Extract vendor and amount data\n3. Send data to ERP system\n4. Verify data appears in ERP correctly | Extracted data successfully integrated into ERP system | Data accuracy >95% and ERP records created | High | 90 minutes | Integration Team | Test | ERP test environment access
Integration Testing | Error Scenarios | IT004 | Failed Document Handling | Test handling of documents that fail processing | Solution with error handling workflows configured | 1. Submit unreadable document\n2. Monitor processing attempt\n3. Verify document moves to failed container\n4. Check error logging and notifications | Failed documents properly isolated and logged | Documents in failed container with error details logged | Medium | 30 minutes | QA Team | Test | Intentionally corrupted documents
Integration Testing | Security Testing | IT005 | Authentication and Authorization | Verify security controls and access restrictions | Solution deployed with security configurations | 1. Test API access without credentials\n2. Test with invalid credentials\n3. Test with valid credentials\n4. Verify role-based access controls | Unauthorized access blocked and authorized access granted | 401/403 for invalid access 200 for valid access | High | 40 minutes | Security Team | Test | Valid and invalid credentials
Performance Testing | Load Testing | PT001 | Concurrent Document Processing | Test system performance under concurrent load | Performance test environment deployed | 1. Configure 50 concurrent users\n2. Each user submits document for processing\n3. Monitor response times and success rates\n4. Measure system resource utilization | System maintains performance under concurrent load | Response time <5 seconds 95% success rate | High | 120 minutes | Performance Team | Test | 50 diverse test documents
Performance Testing | Load Testing | PT002 | Volume Processing Test | Test high-volume document processing capability | Solution scaled for high volume testing | 1. Submit 1000 documents over 2 hours\n2. Monitor processing throughput\n3. Track system performance metrics\n4. Verify all documents processed | System processes high volume without degradation | Throughput >500 docs/hour no system failures | High | 180 minutes | Performance Team | Test | 1000 test documents various types
Performance Testing | Stress Testing | PT003 | Peak Load Stress Test | Test system behavior under extreme load conditions | Performance environment with monitoring | 1. Gradually increase load to 200% capacity\n2. Monitor system response and failures\n3. Test auto-scaling behavior\n4. Verify graceful degradation | System handles stress with graceful degradation | Auto-scaling triggers error rate <10% | Medium | 90 minutes | Performance Team | Test | Large volume of test documents
Performance Testing | Scalability Testing | PT004 | Auto-Scaling Validation | Verify automatic scaling based on demand | Auto-scaling configured and enabled | 1. Start with baseline load\n2. Increase to trigger scale-out\n3. Monitor scaling behavior\n4. Decrease load to test scale-in | Auto-scaling responds appropriately to demand changes | Scale-out within 5 minutes scale-in within 10 minutes | Medium | 75 minutes | Performance Team | Test | Variable load test scripts
Security Testing | Authentication Testing | ST001 | API Authentication Security | Test API security and authentication mechanisms | APIs deployed with authentication enabled | 1. Test API access without authentication\n2. Test with expired tokens\n3. Test with invalid tokens\n4. Test with valid authentication | Authentication properly enforced for all API endpoints | Unauthorized requests rejected valid requests accepted | High | 45 minutes | Security Team | Test | Authentication tokens and credentials
Security Testing | Authorization Testing | ST002 | Role-Based Access Control | Verify RBAC implementation and enforcement | RBAC configured with different user roles | 1. Test admin user access\n2. Test standard user access\n3. Test restricted user access\n4. Verify permission boundaries | Users can only access resources according to their roles | Proper access control based on assigned roles | High | 60 minutes | Security Team | Test | Test users with different roles
Security Testing | Data Protection | ST003 | Data Encryption Validation | Verify data encryption at rest and in transit | Solution deployed with encryption enabled | 1. Check storage encryption status\n2. Monitor network traffic for TLS\n3. Verify Key Vault key usage\n4. Test data access without proper keys | All data properly encrypted using specified keys | Encryption enabled and keys properly managed | High | 30 minutes | Security Team | Test | Encrypted test data
Security Testing | Network Security | ST004 | Network Access Controls | Test network security and access restrictions | Network security groups and firewall configured | 1. Test access from allowed networks\n2. Test access from blocked networks\n3. Verify firewall rules\n4. Test private endpoint connectivity | Network access properly controlled and restricted | Blocked networks rejected allowed networks accepted | Medium | 40 minutes | Security Team | Test | Different network locations
User Acceptance Testing | Business Process | UAT001 | Invoice Processing Workflow | Validate invoice processing meets business requirements | Production-like environment with test data | 1. Upload sample invoices\n2. Review extracted data accuracy\n3. Validate business rules application\n4. Confirm integration with accounting system | Invoice processing meets accuracy and speed requirements | >98% accuracy <30 seconds processing time | High | 120 minutes | Business Users | UAT | Real invoice samples (anonymized)
User Acceptance Testing | Business Process | UAT002 | Receipt Processing for Expenses | Test receipt processing for expense management workflows | Expense management system integrated | 1. Process various receipt types\n2. Validate data extraction accuracy\n3. Test expense categorization\n4. Verify expense system integration | Receipt processing supports expense management workflows | Proper categorization and system integration | Medium | 90 minutes | Finance Team | UAT | Employee expense receipts
User Acceptance Testing | Business Process | UAT003 | Contract Document Analysis | Validate contract processing and key term extraction | Contract analysis workflows configured | 1. Process various contract types\n2. Review extracted key terms\n3. Validate date and party extraction\n4. Test compliance checking | Contract processing extracts required business data | Key terms dates and parties extracted accurately | Medium | 105 minutes | Legal Team | UAT | Sample contracts (redacted)
User Acceptance Testing | Usability Testing | UAT004 | User Interface and Experience | Test user interface usability and workflow efficiency | Web interface deployed and accessible | 1. Navigate upload interface\n2. Monitor processing status\n3. Review results and reports\n4. Test administrative functions | Interface is intuitive and meets usability standards | Users can complete tasks without extensive training | Medium | 75 minutes | End Users | UAT | Training materials and user guides
User Acceptance Testing | Reporting and Analytics | UAT005 | Processing Reports and Analytics | Validate reporting capabilities and data visualization | Reporting system configured with sample data | 1. Generate processing statistics\n2. Review accuracy reports\n3. Test custom report creation\n4. Validate data export functionality | Reporting provides required business insights | Reports accurate and support business decisions | Low | 60 minutes | Business Analysts | UAT | Historical processing data
Regression Testing | Automated Testing | RT001 | Automated Regression Suite | Execute automated tests to verify no functionality regression | Automated test suite configured and executable | 1. Execute full automated test suite\n2. Review test results and coverage\n3. Investigate any failures\n4. Validate all critical functions | All automated tests pass without regression issues | >95% test pass rate no critical failures | High | 90 minutes | QA Team | Test | Automated test data sets
Regression Testing | Configuration Testing | RT002 | Environment Configuration Validation | Verify all environments properly configured | All environments deployed with standard configuration | 1. Validate configuration consistency\n2. Test environment-specific settings\n3. Verify security configurations\n4. Check integration endpoints | All environments configured correctly and consistently | Configuration matches specifications no environment issues | Medium | 45 minutes | DevOps Team | All | Environment configuration baselines
Disaster Recovery | Backup and Recovery | DR001 | Backup and Restore Procedures | Test backup and recovery capabilities | Backup systems configured and operational | 1. Perform full system backup\n2. Simulate system failure\n3. Execute recovery procedures\n4. Verify data integrity post-recovery | System can be recovered within RTO with no data loss | RTO <4 hours RPO <1 hour data integrity verified | High | 240 minutes | Operations Team | Prod | Production backup procedures
Disaster Recovery | Failover Testing | DR002 | Multi-Region Failover | Test failover to secondary region | Multi-region deployment configured | 1. Simulate primary region outage\n2. Execute failover procedures\n3. Verify service availability in secondary region\n4. Test failback procedures | Service continues in secondary region with minimal downtime | Failover <30 minutes service fully functional | Medium | 180 minutes | Operations Team | Prod | Multi-region configuration