## Cover
Roles
Delivery Document
Generated: | November 15, 2025
Solution: | Enterprise Platform
Customer Name: | Data table for roles
Version: | 1.0

## Roles
Role_ID | Role_Name | Level | Department | Primary_Responsibilities | Required_Skills | Experience_Required | Certification_Preferred | Estimated_Hours | Phase | Status
ROLE-001 | DevOps Engineering Lead | Senior | Engineering | Lead DevOps transformation initiative, architect CI/CD solutions, mentor team members | Azure DevOps, Kubernetes, Terraform, Python, PowerShell | 5+ years | Microsoft Certified: DevOps Engineer Expert | 160 | All Phases | Required
ROLE-002 | Senior DevOps Engineer | Senior | Engineering | Design and implement CI/CD pipelines, automate deployment processes, troubleshoot issues | Azure DevOps, Docker, Kubernetes, YAML, Git | 3-5 years | Azure DevOps Engineer Expert | 120 | Implementation | Required
ROLE-003 | DevOps Engineer | Mid-Level | Engineering | Develop build and release pipelines, maintain infrastructure as code, support deployments | Azure DevOps, Git, PowerShell, YAML, Basic scripting | 2-3 years | Azure Fundamentals | 100 | Implementation | Required
ROLE-004 | Site Reliability Engineer (SRE) | Senior | Operations | Ensure platform reliability and performance, implement monitoring and alerting, incident response | Monitoring tools, Kubernetes, Azure Monitor, Python, Linux | 3-5 years | Azure Solutions Architect | 100 | Operations | Recommended
ROLE-005 | Platform Architect | Principal | Architecture | Design enterprise DevOps platform architecture, define standards and best practices | Enterprise architecture, Azure services, Security, Governance | 7+ years | Azure Solutions Architect Expert | 80 | Planning | Required
ROLE-006 | Security Engineer | Senior | Security | Implement DevSecOps practices, security scanning integration, compliance validation | Security tools, SAST/DAST, Azure Security Center, Compliance | 3-5 years | Azure Security Engineer Associate | 60 | Security | Required
ROLE-007 | Infrastructure Engineer | Mid-Level | Infrastructure | Manage Azure infrastructure, implement IaC, network configuration and security | Azure IaaS, Terraform, ARM templates, Networking, PowerShell | 2-4 years | Azure Infrastructure Associate | 80 | Infrastructure | Required
ROLE-008 | Application Development Lead | Senior | Development | Lead application modernization, establish development standards, code review processes | Application development, Architecture patterns, Code quality | 5+ years | Technology-specific certifications | 40 | Development | Recommended
ROLE-009 | Senior Developer | Senior | Development | Implement application changes for DevOps adoption, mentor junior developers | Programming languages, Git workflows, Testing frameworks | 3-5 years | Technology-specific certifications | 60 | Development | Required
ROLE-010 | QA Automation Engineer | Mid-Level | Quality Assurance | Develop automated test suites, integrate testing into CI/CD pipelines | Test automation tools, Selenium, API testing, Scripting | 2-4 years | Test automation certifications | 80 | Testing | Required
ROLE-011 | Cloud Solutions Architect | Principal | Architecture | Design cloud-native solutions, migration planning, technology selection | Azure architecture, Migration patterns, Enterprise integration | 7+ years | Azure Solutions Architect Expert | 60 | Planning | Required
ROLE-012 | Project Manager | Senior | Project Management | Coordinate DevOps transformation project, stakeholder management, timeline tracking | Project management, Agile methodologies, Risk management | 5+ years | PMP or Agile certifications | 120 | All Phases | Required
ROLE-013 | Scrum Master / Agile Coach | Mid-Level | Process | Facilitate agile ceremonies, coach teams on DevOps practices, process improvement | Agile frameworks, Coaching, Process improvement | 3-5 years | Scrum Master or Agile Coach | 40 | Cultural Change | Recommended
ROLE-014 | Technical Writer | Mid-Level | Documentation | Create technical documentation, runbooks, training materials, process documentation | Technical writing, Documentation tools, Process mapping | 2-3 years | Technical writing certifications | 60 | Documentation | Recommended
ROLE-015 | Database Administrator | Senior | Data Management | Manage database deployments, implement database DevOps practices, performance tuning | Database technologies, Backup/recovery, Performance tuning | 3-5 years | Database-specific certifications | 40 | Data Management | Recommended
ROLE-016 | Network Engineer | Senior | Infrastructure | Configure network security, implement connectivity solutions, troubleshoot network issues | Azure networking, VPN, Security groups, DNS | 3-5 years | Azure Network Engineer Associate | 40 | Infrastructure | Recommended
ROLE-017 | Monitoring Specialist | Mid-Level | Operations | Implement monitoring solutions, create dashboards, configure alerting systems | Azure Monitor, Log Analytics, Grafana, KQL | 2-4 years | Azure monitoring certifications | 60 | Operations | Recommended
ROLE-018 | Compliance Officer | Senior | Compliance | Ensure regulatory compliance, audit trail implementation, policy enforcement | Compliance frameworks, Risk assessment, Audit processes | 5+ years | Compliance certifications | 30 | Compliance | Required
ROLE-019 | Change Management Specialist | Senior | Organizational Development | Manage organizational change, training coordination, adoption metrics | Change management, Training development, Communication | 5+ years | Change management certifications | 80 | Cultural Change | Required
ROLE-020 | Business Analyst | Mid-Level | Business Analysis | Requirements gathering, process mapping, stakeholder communication, ROI tracking | Requirements analysis, Process modeling, Stakeholder management | 2-4 years | Business analysis certifications | 60 | Analysis | Recommended
ROLE-021 | Container Platform Engineer | Senior | Platform | Manage Kubernetes clusters, container orchestration, platform operations | Kubernetes, Docker, Container security, GitOps | 3-5 years | Certified Kubernetes Administrator | 80 | Platform | Recommended
ROLE-022 | Integration Engineer | Senior | Integration | Design and implement system integrations, API management, data synchronization | Integration patterns, API design, Middleware, ETL | 3-5 years | Integration platform certifications | 60 | Integration | Recommended
ROLE-023 | Performance Engineer | Senior | Performance | Conduct performance testing, optimization, capacity planning, bottleneck analysis | Performance testing tools, APM, Capacity planning | 3-5 years | Performance testing certifications | 40 | Performance | Recommended
ROLE-024 | Backup and Recovery Specialist | Mid-Level | Operations | Implement backup strategies, disaster recovery planning, data protection | Backup technologies, Disaster recovery, Azure Backup | 2-4 years | Backup and recovery certifications | 30 | Operations | Recommended
ROLE-025 | DevOps Tools Administrator | Mid-Level | Administration | Administer DevOps tools, user management, plugin maintenance, system updates | Azure DevOps administration, User management, System administration | 2-3 years | Azure DevOps administration | 60 | Administration | Required
ROLE-026 | Enterprise Integration Architect | Principal | Integration | Design enterprise integration architecture, API governance, microservices strategy | Enterprise integration, SOA, Microservices, API management | 7+ years | Enterprise architecture certifications | 40 | Architecture | Recommended
ROLE-027 | Data Engineer | Senior | Data | Implement data pipelines, data governance, analytics integration with DevOps processes | Data pipelines, ETL/ELT, Data governance, Analytics | 3-5 years | Data engineering certifications | 40 | Data | Recommended
ROLE-028 | Mobile DevOps Engineer | Senior | Development | Implement mobile CI/CD pipelines, app store integration, mobile testing automation | Mobile development, App distribution, Mobile testing | 3-5 years | Mobile platform certifications | 40 | Mobile | Optional
ROLE-029 | Cost Management Specialist | Mid-Level | Finance | Monitor and optimize cloud costs, implement cost controls, financial reporting | Cost management, Financial analysis, Azure cost optimization | 2-4 years | FinOps certifications | 30 | Financial | Recommended
ROLE-030 | Training Coordinator | Mid-Level | Training | Coordinate training programs, schedule sessions, track certifications, knowledge management | Training coordination, Learning management systems, Knowledge management | 2-3 years | Training and development certifications | 60 | Training | Required
ROLE-031 | User Experience (UX) Developer | Mid-Level | Development | Implement UX improvements, user interface optimization, usability testing | UX/UI design, Frontend development, Usability testing | 2-4 years | UX design certifications | 20 | User Experience | Optional
ROLE-032 | Technical Support Specialist | Mid-Level | Support | Provide technical support for DevOps platform, troubleshoot issues, user assistance | Technical support, Troubleshooting, Customer service | 2-3 years | Technical support certifications | 40 | Support | Recommended
ROLE-033 | Release Manager | Senior | Release Management | Coordinate releases across teams, manage release calendar, risk assessment | Release management, Risk assessment, Coordination | 3-5 years | Release management certifications | 60 | Release | Required
ROLE-034 | Configuration Manager | Mid-Level | Configuration | Manage configuration baselines, change control, configuration auditing | Configuration management, Change control, Auditing | 2-4 years | Configuration management certifications | 40 | Configuration | Recommended
ROLE-035 | DevOps Consultant | Principal | Consulting | Provide expert guidance, best practices consultation, transformation advisory | DevOps expertise, Consulting, Transformation leadership | 8+ years | Multiple DevOps certifications | 40 | Advisory | Optional