## Cover
Test Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Enterprise Platform
Customer Name: | Data table for test plan
Version: | 1.0

## Test Plan
Test_ID | Test_Suite | Test_Case | Test_Type | Priority | Phase | Owner | Prerequisites | Test_Steps | Expected_Results | Status | Environment | Automation_Level
TEST-001 | Platform Setup | Azure DevOps Organization Creation | Functional | Critical | Infrastructure | Platform Team | Azure subscription active, admin access available | 1. Navigate to dev.azure.com, 2. Create new organization, 3. Configure initial settings, 4. Verify access | Organization created successfully with proper configuration | Not Started | Development | Manual
TEST-002 | Platform Setup | Azure AD Integration | Integration | Critical | Security | Security Engineer | Azure AD tenant configured, SSO requirements defined | 1. Configure Azure AD connection, 2. Test SSO login, 3. Verify user provisioning, 4. Test group mappings | Users can authenticate via SSO with appropriate permissions | Not Started | Development | Semi-Automated
TEST-003 | Platform Setup | Key Vault Configuration | Security | Critical | Security | Security Engineer | Azure subscription active, Key Vault service available | 1. Deploy Key Vault, 2. Configure access policies, 3. Store test secrets, 4. Verify secret retrieval | Secrets stored and retrieved securely with proper access control | Not Started | Development | Automated
TEST-004 | Platform Setup | Container Registry Setup | Functional | High | Platform | DevOps Engineer | Azure subscription active, ACR service available | 1. Create ACR instance, 2. Configure security scanning, 3. Push test image, 4. Verify scan results | ACR operational with vulnerability scanning enabled | Not Started | Development | Semi-Automated
TEST-005 | Platform Setup | Kubernetes Cluster Deployment | Infrastructure | High | Platform | Container Engineer | Network configured, RBAC requirements defined | 1. Deploy AKS cluster, 2. Configure RBAC, 3. Install required addons, 4. Test pod deployment | AKS cluster operational with proper security configuration | Not Started | Development | Automated
TEST-006 | CI/CD Pipelines | Build Pipeline Creation | Functional | Critical | Development | DevOps Engineer | Repository configured, build requirements defined | 1. Create YAML pipeline, 2. Configure triggers, 3. Run test build, 4. Verify artifacts | Build pipeline executes successfully and produces artifacts | Not Started | Development | Automated
TEST-007 | CI/CD Pipelines | Multi-stage Release Pipeline | Functional | Critical | Development | DevOps Engineer | Build pipeline functional, environments configured | 1. Create release pipeline, 2. Configure approval gates, 3. Test deployment, 4. Verify rollback | Multi-stage deployment works with proper approvals | Not Started | Development | Semi-Automated
TEST-008 | CI/CD Pipelines | Parallel Job Execution | Performance | High | Development | DevOps Engineer | Multiple pipelines configured, agents available | 1. Trigger multiple builds, 2. Monitor execution, 3. Verify parallel processing, 4. Check resource utilization | Pipelines execute in parallel without resource conflicts | Not Started | Development | Automated
TEST-009 | Security Testing | Static Code Analysis | Security | High | Security | Security Engineer | SonarCloud configured, code quality gates defined | 1. Trigger code analysis, 2. Review quality gates, 3. Verify blocking behavior, 4. Test exception handling | Code analysis identifies issues and blocks poor quality code | Not Started | Development | Automated
TEST-010 | Security Testing | Dependency Vulnerability Scanning | Security | High | Security | Security Engineer | WhiteSource configured, policies defined | 1. Scan dependencies, 2. Review vulnerability report, 3. Test policy enforcement, 4. Verify remediation tracking | Vulnerabilities detected and remediation tracked properly | Not Started | Development | Automated
TEST-011 | Security Testing | Container Image Scanning | Security | High | Security | Security Engineer | Container registry configured, scanning enabled | 1. Push test images, 2. Review scan results, 3. Test policy enforcement, 4. Verify quarantine behavior | Container images scanned with vulnerabilities properly handled | Not Started | Development | Automated
TEST-012 | Performance Testing | Build Performance Baseline | Performance | Medium | Performance | Performance Engineer | Build pipelines configured, performance tools ready | 1. Execute baseline builds, 2. Measure execution times, 3. Identify bottlenecks, 4. Document baselines | Build performance baseline established with identified optimization areas | Not Started | Development | Automated
TEST-013 | Performance Testing | Deployment Speed Testing | Performance | Medium | Performance | Performance Engineer | Deployment pipelines configured, target environments ready | 1. Execute deployments, 2. Measure deployment times, 3. Test parallel deployments, 4. Verify SLA compliance | Deployment times meet SLA requirements across environments | Not Started | Development | Automated
TEST-014 | Performance Testing | Scale Testing | Performance | High | Performance | Performance Engineer | Multiple agents configured, load generation tools ready | 1. Generate high pipeline load, 2. Monitor system performance, 3. Test auto-scaling, 4. Verify stability | Platform handles expected load with proper auto-scaling behavior | Not Started | Test | Automated
TEST-015 | Integration Testing | Third-party Tool Integration | Integration | Medium | Integration | Integration Engineer | External tools configured, API connections established | 1. Test tool integrations, 2. Verify data synchronization, 3. Test notification flows, 4. Verify error handling | External tools integrate properly with data flow working correctly | Not Started | Development | Semi-Automated
TEST-016 | Integration Testing | API Gateway Testing | Integration | Medium | Integration | Integration Engineer | API Management configured, APIs deployed | 1. Test API routing, 2. Verify authentication, 3. Test rate limiting, 4. Verify documentation | API Gateway functions properly with security controls working | Not Started | Development | Semi-Automated
TEST-017 | Disaster Recovery | Backup and Recovery Testing | DR | High | Operations | Backup Specialist | Backup policies configured, recovery procedures documented | 1. Execute backup procedures, 2. Simulate disaster scenario, 3. Execute recovery, 4. Verify data integrity | Backup and recovery procedures work within RTO/RPO targets | Not Started | Test | Manual
TEST-018 | Disaster Recovery | Cross-region Failover Testing | DR | High | Operations | Platform Architect | Multi-region setup configured, failover procedures documented | 1. Simulate region failure, 2. Execute failover procedures, 3. Verify service continuity, 4. Test failback | Failover procedures work with minimal service disruption | Not Started | Test | Semi-Automated
TEST-019 | User Acceptance | Developer Workflow Testing | UAT | High | User Experience | Senior Developer | Training completed, access provisioned | 1. Complete typical workflow, 2. Test collaboration features, 3. Verify notification system, 4. Test mobile access | Developer workflows are intuitive and efficient | Not Started | Development | Manual
TEST-020 | User Acceptance | Admin Interface Testing | UAT | High | User Experience | Platform Admin | Admin training completed, admin access provisioned | 1. Test user management, 2. Configure permissions, 3. Generate reports, 4. Test system monitoring | Admin interfaces provide necessary functionality and visibility | Not Started | Development | Manual
TEST-021 | Compliance Testing | Audit Trail Verification | Compliance | High | Compliance | Compliance Officer | Audit logging configured, compliance requirements defined | 1. Generate audit events, 2. Verify log capture, 3. Test log integrity, 4. Verify retention policies | All required audit events are captured and retained properly | Not Started | Development | Semi-Automated
TEST-022 | Compliance Testing | Data Encryption Validation | Compliance | Critical | Security | Security Engineer | Encryption configured, compliance requirements defined | 1. Verify encryption at rest, 2. Test encryption in transit, 3. Verify key management, 4. Test access controls | Data encryption meets compliance requirements | Not Started | Development | Automated
TEST-023 | Load Testing | Concurrent User Testing | Load | High | Performance | Performance Engineer | Load testing tools configured, user scenarios defined | 1. Simulate concurrent users, 2. Monitor system performance, 3. Identify breaking points, 4. Verify graceful degradation | System handles expected concurrent user load gracefully | Not Started | Test | Automated
TEST-024 | Load Testing | Repository Scale Testing | Load | Medium | Performance | Performance Engineer | Large repositories prepared, performance monitoring enabled | 1. Test large repository operations, 2. Monitor Git performance, 3. Test build times, 4. Verify storage impact | System handles large repositories without performance degradation | Not Started | Test | Automated
TEST-025 | Migration Testing | Repository Migration Validation | Migration | Critical | Migration | DevOps Lead | Source repositories identified, migration tools configured | 1. Migrate test repository, 2. Verify history preservation, 3. Test branch structure, 4. Validate permissions | Repository migration preserves all data and relationships correctly | Not Started | Test | Semi-Automated
TEST-026 | Migration Testing | Work Item Migration Testing | Migration | High | Migration | Business Analyst | Work items identified, mapping configured | 1. Migrate work items, 2. Verify field mapping, 3. Test relationships, 4. Validate history | Work items migrate with complete history and relationships intact | Not Started | Test | Semi-Automated
TEST-027 | Monitoring Testing | Alert Configuration Testing | Monitoring | High | Operations | Monitoring Specialist | Monitoring configured, alert rules defined | 1. Trigger alert conditions, 2. Verify alert generation, 3. Test escalation procedures, 4. Verify resolution tracking | Alerts fire correctly and escalation procedures work properly | Not Started | Development | Semi-Automated
TEST-028 | Monitoring Testing | Dashboard Functionality Testing | Monitoring | Medium | Operations | Monitoring Specialist | Dashboards configured, data sources connected | 1. Verify data visualization, 2. Test drill-down capabilities, 3. Validate real-time updates, 4. Test export functionality | Dashboards provide accurate real-time visibility into system health | Not Started | Development | Manual
TEST-029 | Network Testing | Connectivity and Security Testing | Network | High | Infrastructure | Network Engineer | Network configured, security policies defined | 1. Test network connectivity, 2. Verify firewall rules, 3. Test VPN connections, 4. Validate security groups | Network connectivity works properly with security controls enforced | Not Started | Development | Semi-Automated
TEST-030 | End-to-End | Complete DevOps Workflow Testing | E2E | Critical | Integration | Project Manager | All components configured, end-to-end scenarios defined | 1. Execute complete workflow, 2. Test all integrations, 3. Verify data flow, 4. Test exception handling | Complete DevOps workflow functions end-to-end without issues | Not Started | Test | Semi-Automated