## Cover
Training Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Enterprise Platform
Customer Name: | Data table for training plan
Version: | 1.0

## Training Plan
Training_ID | Course_Name | Target_Audience | Learning_Objectives | Duration_Hours | Delivery_Method | Prerequisites | Trainer | Schedule | Max_Participants | Materials_Required | Assessment_Method | Certification | Priority
TRN-001 | Azure DevOps Fundamentals | All Team Members | Understand Azure DevOps services, navigation, basic concepts | 4 | Virtual Classroom | Basic Azure knowledge | Azure Trainer | Week 1 | 30 | Azure DevOps access, presentation slides | Quiz + Practical Exercise | Azure DevOps Fundamentals Certificate | Critical
TRN-002 | Git Version Control Best Practices | Developers | Master Git workflows, branching strategies, collaboration | 6 | Virtual Classroom | Basic Git knowledge | DevOps Lead | Week 1 | 20 | Git client, sample repository | Hands-on Exercise | Git Proficiency Certificate | Critical
TRN-003 | YAML Pipeline Development | DevOps Engineers | Create and maintain YAML-based CI/CD pipelines | 8 | Hands-on Workshop | Azure DevOps Fundamentals | Senior DevOps Engineer | Week 2 | 15 | Azure DevOps access, code editor | Pipeline Creation Project | Pipeline Development Certificate | Critical
TRN-004 | Infrastructure as Code with Terraform | Infrastructure Team | Develop and manage infrastructure using Terraform | 12 | Hands-on Workshop | Basic scripting knowledge | Infrastructure Architect | Week 2 | 12 | Terraform installed, Azure access | Infrastructure Deployment Project | Terraform Associate Certification | High
TRN-005 | Container Technologies and Kubernetes | Platform Team | Understand containerization, Kubernetes orchestration | 16 | Multi-day Workshop | Basic Linux knowledge | Container Specialist | Week 3 | 10 | Docker installed, Kubernetes access | Container Deployment Project | Kubernetes Certification | High
TRN-006 | Security Integration in DevOps | Security Team | Implement DevSecOps practices, security scanning | 6 | Virtual Classroom | Security fundamentals | Security Architect | Week 2 | 15 | Security tools access, sample code | Security Assessment Project | DevSecOps Certificate | High
TRN-007 | Azure Monitor and Application Insights | Operations Team | Configure monitoring, create dashboards, set up alerts | 8 | Hands-on Workshop | Azure fundamentals | Monitoring Specialist | Week 3 | 15 | Azure access, sample applications | Monitoring Configuration Project | Azure Monitoring Certificate | High
TRN-008 | Agile and DevOps Culture | All Team Members | Understand cultural aspects, collaboration, continuous improvement | 4 | Interactive Workshop |  | Agile Coach | Week 1 | 40 | Workshop materials, collaboration tools | Group Discussion + Reflection | Cultural Transformation Certificate | Medium
TRN-009 | Test Automation in CI/CD | QA Team | Integrate automated testing into pipelines | 10 | Hands-on Workshop | Basic testing knowledge | QA Automation Lead | Week 4 | 12 | Testing tools, sample applications | Test Automation Project | Test Automation Certificate | High
TRN-010 | Azure DevOps Administration | Administrators | Manage users, permissions, organizations, billing | 6 | Virtual Classroom | Azure DevOps Fundamentals | Platform Admin | Week 2 | 10 | Admin access, administration guides | Administrative Tasks Project | Azure DevOps Admin Certificate | High
TRN-011 | Database DevOps Practices | Database Team | Implement database CI/CD, migration strategies | 8 | Virtual Classroom | Database fundamentals | Database Specialist | Week 4 | 10 | Database access, migration tools | Database Pipeline Project | Database DevOps Certificate | Medium
TRN-012 | API Management and Integration | Integration Team | Design APIs, implement API management, integration patterns | 8 | Hands-on Workshop | API fundamentals | Integration Architect | Week 5 | 12 | API tools, development environment | API Integration Project | API Management Certificate | Medium
TRN-013 | Performance Testing and Optimization | Performance Team | Conduct performance testing, analyze results, optimize | 10 | Hands-on Workshop | Testing fundamentals | Performance Engineer | Week 5 | 8 | Performance tools, test applications | Performance Test Project | Performance Testing Certificate | Medium
TRN-014 | Compliance and Audit in DevOps | Compliance Team | Implement compliance controls, audit trails, reporting | 6 | Virtual Classroom | Compliance fundamentals | Compliance Officer | Week 3 | 15 | Compliance tools, audit templates | Compliance Assessment Project | Compliance Certificate | Medium
TRN-015 | Cost Management and FinOps | Financial Team | Monitor and optimize cloud costs, implement cost controls | 4 | Virtual Classroom | Financial fundamentals | Cost Specialist | Week 4 | 12 | Cost management tools, financial reports | Cost Optimization Project | FinOps Certificate | Medium
TRN-016 | Disaster Recovery and Business Continuity | Operations Team | Implement backup strategies, disaster recovery procedures | 6 | Virtual Classroom | Operations fundamentals | DR Specialist | Week 5 | 10 | Backup tools, recovery procedures | DR Test Exercise | Business Continuity Certificate | Medium
TRN-017 | Advanced Pipeline Patterns | Senior DevOps Engineers | Implement complex deployment strategies, advanced patterns | 12 | Advanced Workshop | YAML Pipeline Development | Principal DevOps Architect | Week 6 | 8 | Advanced tooling, complex scenarios | Advanced Pipeline Project | Advanced DevOps Certificate | Medium
TRN-018 | Microservices and DevOps | Architecture Team | Design microservices, implement distributed DevOps | 10 | Architecture Workshop | Container fundamentals | Solution Architect | Week 6 | 10 | Microservices platform, design tools | Microservices Design Project | Microservices Architecture Certificate | Medium
TRN-019 | Mobile DevOps Practices | Mobile Team | Implement mobile CI/CD, app store deployment | 8 | Specialized Workshop | Mobile development | Mobile DevOps Specialist | Week 7 | 6 | Mobile development tools, app stores | Mobile Pipeline Project | Mobile DevOps Certificate | Low
TRN-020 | Azure DevOps Extensions Development | Platform Team | Develop custom extensions, marketplace publishing | 12 | Developer Workshop | JavaScript/TypeScript | Extension Developer | Week 8 | 6 | Development environment, SDK access | Custom Extension Project | Extension Developer Certificate | Low
TRN-021 | Change Management for DevOps | Management Team | Lead organizational change, adoption strategies | 4 | Leadership Workshop | Management experience | Change Management Expert | Week 1 | 20 | Change management materials, case studies | Change Strategy Project | Change Management Certificate | High
TRN-022 | Project Management for DevOps | Project Managers | Manage DevOps projects, agile methodologies, risk management | 6 | Virtual Classroom | Project management experience | Agile PM Expert | Week 2 | 15 | PM tools, project templates | Project Plan Exercise | Agile PM Certificate | Medium
TRN-023 | Technical Writing for DevOps | Documentation Team | Create technical documentation, runbooks, user guides | 6 | Writing Workshop | Technical background | Technical Writer | Week 7 | 8 | Documentation tools, templates | Documentation Project | Technical Writing Certificate | Low
TRN-024 | User Experience for DevOps Tools | UX Team | Design user-friendly interfaces, usability testing | 8 | Design Workshop | UX fundamentals | UX Designer | Week 8 | 6 | Design tools, prototyping software | UX Design Project | UX Design Certificate | Low
TRN-025 | Support and Troubleshooting | Support Team | Provide technical support, troubleshoot issues, escalate problems | 8 | Hands-on Workshop | Technical fundamentals | Support Specialist | Week 6 | 12 | Support tools, troubleshooting guides | Support Scenario Exercise | Technical Support Certificate | Medium
TRN-026 | Data Engineering in DevOps | Data Team | Implement data pipelines, data governance, analytics integration | 10 | Technical Workshop | Data fundamentals | Data Architect | Week 7 | 8 | Data tools, analytics platforms | Data Pipeline Project | Data Engineering Certificate | Low
TRN-027 | Network Security in DevOps | Network Team | Implement network security, VPN configuration, firewall management | 8 | Technical Workshop | Networking fundamentals | Network Security Expert | Week 4 | 10 | Network tools, security appliances | Network Security Project | Network Security Certificate | Medium
TRN-028 | Release Management Best Practices | Release Team | Coordinate releases, manage dependencies, risk assessment | 6 | Virtual Classroom | Release experience | Release Manager | Week 5 | 12 | Release tools, coordination templates | Release Plan Exercise | Release Management Certificate | Medium
TRN-029 | Configuration Management | Configuration Team | Manage configurations, version control, change tracking | 6 | Technical Workshop | Systems administration | Configuration Specialist | Week 6 | 10 | Configuration tools, version control | Configuration Project | Configuration Management Certificate | Medium
TRN-030 | DevOps Metrics and KPIs | Analytics Team | Define and track DevOps metrics, create dashboards, report insights | 4 | Analytics Workshop | Analytics fundamentals | Business Analyst | Week 7 | 15 | Analytics tools, dashboard platforms | Metrics Dashboard Project | DevOps Analytics Certificate | Medium
TRN-031 | Continuous Improvement Practices | Process Team | Implement continuous improvement, retrospectives, optimization | 4 | Process Workshop | Process improvement experience | Process Improvement Expert | Week 8 | 20 | Process tools, improvement frameworks | Improvement Plan Project | Process Improvement Certificate | Low
TRN-032 | Vendor Management for DevOps | Procurement Team | Manage vendor relationships, contract negotiation, SLA management | 4 | Business Workshop | Procurement experience | Vendor Management Expert | Week 3 | 8 | Contract templates, SLA frameworks | Vendor Assessment Project | Vendor Management Certificate | Low
TRN-033 | Risk Management in DevOps | Risk Team | Identify and mitigate risks, create risk registers, contingency planning | 6 | Risk Workshop | Risk management fundamentals | Risk Management Expert | Week 4 | 12 | Risk tools, assessment templates | Risk Assessment Project | Risk Management Certificate | Medium
TRN-034 | Innovation and Emerging Technologies | Innovation Team | Explore new technologies, innovation processes, technology evaluation | 6 | Innovation Workshop | Technology background | Innovation Specialist | Week 9 | 10 | Technology demos, evaluation frameworks | Innovation Project | Innovation Certificate | Low
TRN-035 | Executive Briefing on DevOps ROI | Executive Team | Understand DevOps value, ROI measurement, strategic alignment | 2 | Executive Briefing | Executive experience | Executive Consultant | Week 1 | 10 | Executive summary, ROI models | Strategic Discussion | Executive Understanding Certificate | Critical