## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Virtual Desktop
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Executive Status Report | Executive Sponsors | AVD project status and modern workplace transformation progress | Weekly | Email Report | EO Project Manager | Email distribution list |  | "Virtual desktop deployment progress, user adoption metrics, key decisions needed" | EO Quarterback and IT Director | Executive | Report delivered on time and strategic decisions made | Active | [DATE] | Include user satisfaction metrics and ROI tracking
COMM-002 | AVD Steering Committee | Project Steering Committee | Strategic direction and scope decisions for virtual desktop implementation | Bi-weekly | In-Person Meeting | EO Project Manager | Meeting invitation | 60 minutes | "Modern workplace strategy, user experience, budget, timeline, scope changes" | EO Quarterback and Department Heads | Strategic | Meeting attendance >80% and critical decisions documented | Active | [DATE] | Decision authority for user requirements and technology choices
COMM-003 | Development Team Standup | Core AVD Development Team | Daily coordination for Azure infrastructure and application deployment | Daily | Virtual Meeting | EO Quarterback | Video conference | 15 minutes | "Host pool deployment, application packaging, user profile configuration" | Development Team and Cloud Engineers | Operational | Daily attendance >90% and technical blockers resolved | Active | [DATE] | Focus on Azure services coordination and impediments
COMM-004 | Azure Architecture Review | Technical and Infrastructure Teams | AVD architecture optimization and performance tuning | Weekly | Technical Meeting | EO Quarterback | Meeting invitation | 90 minutes | "Host pool configuration, network performance, storage optimization" | EO Sales Engineer (Solution Architecture) and Cloud Architects | Technical | Architecture decisions documented and performance targets achieved | Active | [DATE] | Include Azure resource optimization and cost management
COMM-005 | Virtual Desktop Risk Review | Risk Management Team | User adoption risks and technology performance monitoring | Bi-weekly | Risk Meeting | EO Quarterback | Meeting invitation | 45 minutes | "User adoption risks, performance degradation, network connectivity issues" | EO Project Manager and EO Delivery Engineer (Technical Leadership) | Management | Risk register updated and virtual desktop specific mitigations tracked | Active | [DATE] | Focus on user experience risks and performance monitoring
COMM-006 | Business User Feedback | Desktop Users and Managers | Requirements validation and user experience feedback | Weekly | Workshop Session | EO Sales Engineer | Workshop invitation | 120 minutes | "Application requirements, desktop performance feedback, workflow validation" | Business Stakeholders and End Users | Business | User sign-off on desktop experience and application access | Active | [DATE] | Include hands-on testing of virtual desktop workflows
COMM-007 | AVD Sprint Review | AVD Development Team | Infrastructure progress and user experience demonstrations | Bi-weekly | Demo Meeting | EO Quarterback | Video conference | 60 minutes | "Host pool status, application deployment, user experience demonstrations" | Infrastructure Team and Product Owner | Team | User experience goals achieved and feedback incorporated | Active | [DATE] | Live demonstration of virtual desktop login and application access
COMM-008 | Microsoft Support Coordination | Microsoft Technical Teams | Azure AVD service optimization and best practices coordination | Weekly | Technical Call | EO Engineer | Conference call | 45 minutes | "AVD service performance, host pool optimization, troubleshooting" | Microsoft Technical Team and EO Sales Engineer (Solution Architecture) | Technical | Microsoft service performance targets met and issues resolved | Active | [DATE] | Track AVD SLAs and optimization opportunities
COMM-009 | User Experience Review | Quality Assurance and User Representatives | Virtual desktop performance and user satisfaction validation | Weekly | UX Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Login performance testing, application responsiveness, user satisfaction" | QA Team and User Representatives | Quality | User experience goals met and performance within tolerance | Active | [DATE] | Include user experience metrics and satisfaction analysis
COMM-010 | Change Control Board | Change Control Board | AVD configuration changes and user environment modifications | As Needed | Change Meeting | EO Engineer | Meeting invitation | 60 minutes | "Host pool changes, application updates, user profile modifications" | Change Control Board Members | Governance | Change requests processed within SLA and impact assessed | Active | [DATE] | Include user impact assessment and rollback procedures
COMM-011 | User Training Update | Training and Change Management Teams | AVD user training progress and adoption readiness | Bi-weekly | Training Call | EO Engineer | Conference call | 30 minutes | "Training material development, user competency, change readiness" | Training Team and Change Management | Operational | Training materials ready and user adoption validated | Active | [DATE] | Include hands-on virtual desktop training sessions
COMM-012 | Security and Compliance Review | Security and Compliance Teams | Virtual desktop security posture and compliance validation | Monthly | Security Meeting | EO Quarterback | Meeting invitation | 60 minutes | "Access controls, data protection, compliance validation, conditional access" | Security Team and Compliance Officer | Security | Security requirements met and compliance validated | Active | [DATE] | Include Azure AD integration and zero trust implementation
COMM-013 | Azure Infrastructure Update | Infrastructure and DevOps Teams | Azure resource performance and capacity planning | Weekly | Infrastructure Call | EO Engineer | Conference call | 30 minutes | "Azure resource utilization, cost optimization, capacity planning" | Infrastructure Team and Cloud Architect | Technical | Infrastructure performance targets met and costs optimized | Active | [DATE] | Include Azure cost monitoring and resource optimization
COMM-014 | Business Readiness Assessment | Business Stakeholders | Virtual desktop workflow readiness and change management | Bi-weekly | Business Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Workflow transition readiness, user adoption, process changes" | Business Managers and Department Heads | Business | Business readiness criteria met and users prepared for transition | Active | [DATE] | Include user acceptance of virtual desktop workflows
COMM-015 | Go-Live Preparation | Go-Live Coordination Team | Production deployment and AVD go-live readiness | Daily (2 weeks before) | Go-Live Meeting | EO Project Manager | Video conference | 30 minutes | "Deployment checklist, production readiness, user migration procedures" | All Team Leads and Operations Manager | Critical | Go-live criteria met and AVD deployment ready | Planned | [DATE] | Intensive coordination for virtual desktop production migration
COMM-016 | Post-Implementation Review | Project and Operations Teams | AVD performance review and optimization opportunities | Monthly (3 months) | Review Meeting | EO Quarterback | Meeting invitation | 90 minutes | "User satisfaction trends, performance efficiency, optimization opportunities" | Core Project Team and Business Stakeholders | Review | Performance improvements identified and optimization roadmap created | Planned | [DATE] | Include user adoption analysis and continuous improvement planning
COMM-017 | Critical Issue Escalation | Emergency Response Team | Critical AVD system failures and user access issues | As Needed | Emergency Call | EO Sales Engineer | Emergency notification | Variable | "System outages, authentication failures, performance degradation, resolution actions" | Incident Response Team and Management | Emergency | Critical issues resolved within SLA and service restored | Active | [DATE] | Include emergency user communication and service restoration
COMM-018 | Stakeholder Briefing | All Project Stakeholders | General AVD project updates and modern workplace progress | Monthly | All-Hands Meeting | EO Project Manager | Town hall meeting | 45 minutes | "Virtual desktop progress, user adoption success, productivity improvements" | All Project Stakeholders | Informational | Stakeholder engagement maintained and progress communicated | Active | [DATE] | Include modern workplace achievements and user success stories
COMM-019 | Technical Deep Dive | Technical and Infrastructure Teams | AVD technical knowledge sharing and problem-solving | As Needed | Technical Session | EO Quarterback | Meeting invitation | 90 minutes | "Architecture challenges, performance optimization, integration solutions" | Technical Team Members and Cloud Engineers | Technical | Technical challenges resolved and AVD knowledge shared | Active | [DATE] | Include Azure best practices and troubleshooting guides
COMM-020 | Client Update Call | External Client | Client AVD progress and virtual desktop value updates | Bi-weekly | Client Call | EO Project Manager | Client meeting | 45 minutes | "Virtual desktop progress, user satisfaction, business productivity improvements" | Client Stakeholders and Account Manager | Client | Client satisfaction maintained and virtual desktop value communicated | Active | [DATE] | Professional communication with clear business value and ROI
COMM-021 | Performance Monitoring Review | Operations and Infrastructure Teams | AVD performance monitoring and capacity planning | Weekly | Performance Meeting | EO Quarterback | Video conference | 45 minutes | "Performance trends, capacity utilization, scaling requirements" | Operations Team and Cloud Architects | Technical | Performance maintained above thresholds and capacity planned | Active | [DATE] | Include performance dashboards and capacity forecasting
COMM-022 | Application Compatibility Review | Application and Business Teams | Application performance and compatibility validation | Bi-weekly | Application Meeting | EO Quarterback | Meeting invitation | 60 minutes | "Application performance, compatibility issues, optimization needs" | Application SMEs and Technical Team | Business | Application performance maintained and compatibility validated | Active | [DATE] | Include application optimization and user experience improvements
COMM-023 | Network Performance Review | Network and Infrastructure Teams | Network connectivity and performance optimization | Weekly | Network Meeting | EO Engineer | Meeting invitation | 45 minutes | "Network latency, bandwidth utilization, connectivity optimization" | Network Team and Infrastructure Engineers | Technical | Network performance targets met and connectivity optimized | Active | [DATE] | Include ExpressRoute performance and WAN optimization
COMM-024 | User Adoption Tracking | Change Management and Business Teams | User adoption progress and resistance identification | Weekly | Adoption Meeting | EO Project Manager | Meeting invitation | 30 minutes | "Adoption metrics, resistance points, training effectiveness" | Change Management Team and Business Managers | Business | Adoption targets met and resistance issues addressed | Active | [DATE] | Include user feedback analysis and adoption strategy refinement