## Cover
Test Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Virtual Desktop
Customer Name: | Data table for test plan
Version: | 1.0

## Test Plan
Test ID | Test Phase | Test Type | Test Category | Test Description | Test Objective | Test Data Requirements | Expected Result | Pass Criteria | Priority | Owner | Dependencies | Duration | Automation Level | Tools Required | Status | Notes
TST-001 | Unit Testing | Functional | Infrastructure Testing | Test Azure Virtual Network connectivity | Validate VNet setup and subnet configuration | Network configuration parameters | Successful VNet creation with proper subnets | VNet accessible and subnets properly configured | Critical | EO Delivery Engineer (Infrastructure) | Azure infrastructure access | 1 day | Manual | Azure Portal Azure CLI | Not Started | Test connectivity between subnets
TST-002 | Unit Testing | Functional | Infrastructure Testing | Test Azure AD domain join | Validate session hosts can join Azure AD | Test Azure AD tenant and credentials | Session hosts successfully joined to Azure AD | Hosts appear in Azure AD with computer accounts | Critical | EO Engineer (Identity) | Azure AD configuration | 2 days | Semi-automated | Azure AD PowerShell | Not Started | Test both Azure AD and hybrid scenarios
TST-003 | Unit Testing | Functional | AVD Core Testing | Test host pool creation | Validate AVD host pool configuration | Host pool configuration parameters | Host pool created with correct settings | Host pool accessible with proper load balancing | Critical | EO Delivery Engineer (Technical Leadership) | Azure subscription and permissions | 1 day | Manual | Azure Portal AVD PowerShell | Not Started | Test both pooled and personal host pools
TST-004 | Unit Testing | Functional | AVD Core Testing | Test session host deployment | Validate session host VM deployment | VM configuration and image specifications | Session hosts deployed and registered | VMs running and registered to host pool | Critical | EO Delivery Engineer (Technical Leadership) | TST-002 TST-003 | 3 days | Semi-automated | Azure Resource Manager templates | Not Started | Test multiple VM sizes and configurations
TST-005 | Unit Testing | Functional | Image Testing | Test custom image deployment | Validate custom session host image | Custom image with installed applications | Session hosts deployed with custom image | Applications available and functional in sessions | High | EO Engineer (Image Management) | Custom image creation | 2 days | Manual | Azure Portal session testing | Not Started | Test application compatibility and performance
TST-006 | Unit Testing | Functional | Profile Testing | Test FSLogix profile containers | Validate user profile management | Test user accounts and profile data | User profiles created and accessible | Profiles persist across session disconnections | Critical | EO Engineer (User Profile) | FSLogix configuration | 3 days | Manual | Session testing profile validation | Not Started | Test profile container performance and roaming
TST-007 | Integration Testing | Functional | User Experience Testing | Test user session connectivity | Validate end-to-end user session experience | Test user accounts and RDP clients | Users can connect and access desktop | Successful session establishment within 30 seconds | Critical | EO Engineer (QA) | All unit tests complete | 2 days | Manual | RDP clients session monitoring | Not Started | Test from various client platforms
TST-008 | Integration Testing | Functional | Application Testing | Test application compatibility | Validate installed applications work correctly | Business applications and test scenarios | Applications launch and function correctly | All critical applications accessible and functional | High | EO Engineer (Application) | TST-005 TST-007 | 4 days | Manual | Application testing scripts | Not Started | Test application performance and resource usage
TST-009 | Integration Testing | Functional | Peripheral Testing | Test device redirection | Validate printer clipboard and USB redirection | Various peripheral devices | Redirected devices accessible in sessions | Device redirection works according to policy | Medium | EO Engineer (QA) | TST-007 | 2 days | Manual | Test devices and peripherals | Not Started | Test security policies for device access
TST-010 | Integration Testing | Functional | Network Testing | Test network connectivity from sessions | Validate network access from session hosts | Internal and external network resources | Network resources accessible from sessions | Proper network connectivity and DNS resolution | High | EO Delivery Engineer (Infrastructure) | TST-001 TST-007 | 1 day | Manual | Network testing tools | Not Started | Test firewall rules and NSG configuration
TST-011 | Performance Testing | Non-Functional | Load Testing | Test concurrent user sessions | Validate system performance under normal user load | 50-100 concurrent test users | System maintains performance with expected load | Session response time <3 seconds average | High | EO Delivery Engineer (Monitoring) | TST-007 | 3 days | Automated | Load testing tools Azure Monitor | Not Started | Monitor resource utilization and auto-scaling
TST-012 | Performance Testing | Non-Functional | Stress Testing | Test maximum user capacity | Validate system scalability limits | 200+ concurrent test users | System handles peak load or scales appropriately | Auto-scaling functions correctly under stress | High | EO Delivery Engineer (Monitoring) | TST-011 | 2 days | Automated | Performance testing tools | Not Started | Test scale-out and scale-in behavior
TST-013 | Performance Testing | Non-Functional | Network Performance Testing | Test bandwidth and latency | Validate network performance for remote users | Various network conditions and locations | Acceptable performance across network conditions | Session quality maintained with minimum bandwidth | Medium | EO Delivery Engineer (Infrastructure) | TST-010 | 2 days | Manual | Network simulation tools | Not Started | Test from different geographic locations
TST-014 | Security Testing | Security | Authentication Testing | Test user authentication mechanisms | Validate multi-factor authentication and SSO | Test user accounts with MFA enabled | Users authenticate successfully with MFA | Authentication complies with security policies | Critical | EO Engineer (Security) | Azure AD configuration | 2 days | Manual | Authentication testing tools | Not Started | Test various MFA methods and scenarios
TST-015 | Security Testing | Security | Access Control Testing | Test Conditional Access policies | Validate device compliance and access controls | Compliant and non-compliant test devices | Access granted only to compliant devices | Conditional Access policies enforced correctly | Critical | EO Engineer (Security) | Conditional Access configuration | 3 days | Manual | Device compliance testing | Not Started | Test various device compliance scenarios
TST-016 | Security Testing | Security | Data Protection Testing | Test data encryption and isolation | Validate data security measures | Sensitive test data and documents | Data encrypted and properly isolated | All data security requirements met | Critical | EO Engineer (Security) | Encryption implementation | 2 days | Manual | Security audit tools | Not Started | Verify encryption in transit and at rest
TST-017 | Security Testing | Security | Session Security Testing | Test session isolation and security | Validate session-level security controls | Multiple concurrent user sessions | Sessions properly isolated and secured | No data leakage between user sessions | Critical | EO Engineer (Security) | TST-007 | 2 days | Manual | Session security testing tools | Not Started | Test session hijacking and privilege escalation
TST-018 | Disaster Recovery Testing | Non-Functional | Backup Testing | Test backup and recovery procedures | Validate data protection and recovery capabilities | Production-like data and configurations | Successful backup and recovery operations | Recovery time within RTO requirements | High | EO Engineer (Support) | Backup configuration | 1 day | Manual | Azure Backup tools | Not Started | Test both automated and manual recovery scenarios
TST-019 | User Acceptance Testing | Functional | Business Process Testing | Test business workflow integration | Validate AVD meets business requirements | Real business processes and workflows | Business processes work effectively in AVD | Business requirements satisfied and validated | High | EO Sales Engineer (Business Analysis) | TST-008 | 5 days | Manual | Business application testing | Not Started | Involve actual business users in testing
TST-020 | User Acceptance Testing | Functional | Training Validation Testing | Test user training effectiveness | Validate user training and adoption materials | Trained and untrained test users | Users can effectively use AVD after training | Training materials enable successful adoption | Medium | EO Engineer (Training) | Training materials completion | 3 days | Manual | User feedback collection | Not Started | Test training effectiveness with real users
TST-021 | Monitoring Testing | Functional | Alerting Testing | Test monitoring and alerting systems | Validate monitoring alerts and dashboards | Simulated failure scenarios | Alerts trigger correctly for defined conditions | Monitoring system detects and alerts on issues | High | EO Delivery Engineer (Monitoring) | Monitoring configuration | 2 days | Semi-automated | Azure Monitor alert testing | Not Started | Test alert accuracy and response time
TST-022 | Compliance Testing | Security | Audit Testing | Test compliance and audit capabilities | Validate logging and audit trail completeness | User activities and system events | Complete audit trail captured and accessible | Audit logs meet compliance requirements | High | EO Engineer (Security) | Logging configuration | 2 days | Manual | Audit log analysis tools | Not Started | Verify compliance with organizational policies
TST-023 | Migration Testing | Functional | Data Migration Testing | Test user data migration | Validate migration of existing user data | Legacy user profiles and data | User data successfully migrated to AVD | Data integrity maintained during migration | High | EO Engineer (User Profile) | Migration tools and scripts | 3 days | Semi-automated | Migration validation scripts | Not Started | Test data integrity and user experience post-migration
TST-024 | Performance Testing | Non-Functional | Scalability Testing | Test auto-scaling functionality | Validate automatic scaling based on demand | Variable user load patterns | System scales up and down based on demand | Auto-scaling responds appropriately to load changes | Medium | EO Delivery Engineer (Monitoring) | Auto-scaling configuration | 2 days | Automated | Auto-scaling testing tools | Not Started | Test scaling policies and thresholds
TST-025 | Integration Testing | Functional | External Integration Testing | Test line-of-business application integration | Validate integration with existing business applications | Production business applications | Applications integrate seamlessly with AVD | Business applications work correctly in AVD environment | High | EO Engineer (Application) | Business application access | 4 days | Manual | Application integration testing | Not Started | Test SSO and data access from AVD sessions