## Cover
Training Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Virtual Desktop
Customer Name: | Data table for training plan
Version: | 1.0

## Training Plan
Training ID | Training Category | Training Type | Target Audience | Training Title | Learning Objectives | Duration | Delivery Method | Prerequisites | Materials Required | Trainer | Schedule | Maximum Participants | Assessment Method | Certification | Status | Notes
TRN-001 | Technical | Administrator | System Administrators | Azure Virtual Desktop Administration Fundamentals | Understand AVD architecture Azure services management and basic troubleshooting | 2 days | Instructor-led with hands-on labs | Basic Azure knowledge | Azure portal access training materials | EO Delivery Engineer (Technical Leadership) | Week 15 | 8 | Hands-on lab completion | AVD Administrator Certificate | Planned | Focus on operational aspects and host pool management
TRN-002 | Technical | Administrator | System Administrators | AVD Host Pool and Session Host Management | Learn to manage host pools session hosts and user sessions | 1 day | Virtual instructor-led | TRN-001 completion | Azure portal access AVD PowerShell | EO Delivery Engineer (Technical Leadership) | Week 15 | 8 | Service configuration assessment | AVD Management Certificate | Planned | Deep dive into session host lifecycle management
TRN-003 | Technical | Infrastructure | Infrastructure Team | Azure Networking for AVD | Learn networking requirements VNet configuration and connectivity | 1 day | Hands-on workshop | Azure networking experience | Azure portal access network diagrams | EO Delivery Engineer (Infrastructure) | Week 14 | 6 | Network configuration exercise | Azure Networking Certificate | Planned | Include ExpressRoute and VPN scenarios
TRN-004 | Technical | Identity | Identity Team | Azure AD and AVD Integration | Learn Azure AD integration conditional access and MFA setup | 1 day | Technical workshop | Azure AD administration experience | Azure AD portal access test accounts | EO Engineer (Identity) | Week 14 | 6 | Identity configuration assessment | Identity Integration Certificate | Planned | Focus on modern authentication methods
TRN-005 | Technical | Image Management | Technical Team | Custom Image Creation and Management | Learn to create maintain and deploy custom AVD images | 1 day | Hands-on workshop | Windows administration experience | Azure portal access VM access | EO Engineer (Image Management) | Week 14 | 4 | Image creation exercise | Image Management Certificate | Planned | Include application packaging with MSIX
TRN-006 | Technical | Profile Management | Technical Team | FSLogix Profile Container Management | Learn FSLogix setup configuration and troubleshooting | 4 hours | Technical workshop | Windows profiles knowledge | Azure Files access FSLogix tools | EO Engineer (User Profile) | Week 15 | 6 | Profile configuration assessment | FSLogix Specialist Certificate | Planned | Include performance optimization techniques
TRN-007 | Business | End User | Remote Workers | AVD User Experience and Best Practices | Learn to connect use applications and optimize session experience | 2 hours | Virtual demonstration | Basic computer skills | RDP client access sample applications | EO Engineer (Training) | Week 16 | 25 | User task completion assessment | AVD User Certificate | Planned | Include tips for optimal performance
TRN-008 | Business | End User | Business Users | Application Access and Data Management | Learn to access business applications and manage files in AVD | 2 hours | Hands-on training | Application knowledge | AVD session access business applications | EO Engineer (Training) | Week 16 | 20 | Application workflow assessment | Business User Certificate | Planned | Focus on daily business tasks
TRN-009 | Business | Power User | Power Users | Advanced AVD Features and Customization | Learn advanced features customization and productivity tips | 3 hours | Interactive workshop | TRN-007 completion | AVD session access productivity tools | EO Engineer (Training) | Week 16 | 12 | Advanced task exercise | Power User Certificate | Planned | Include automation and scripting basics
TRN-010 | Business | Management | IT Managers | AVD Monitoring and Performance Management | Learn to monitor performance costs and user experience metrics | 2 hours | Executive briefing | IT management background | Azure Monitor access performance dashboards | EO Delivery Engineer (Monitoring) | Week 16 | 10 | Dashboard interpretation assessment | AVD Management Overview Certificate | Planned | Focus on KPIs and cost optimization
TRN-011 | Technical | Support | Help Desk Staff | AVD Troubleshooting and User Support | Learn common issues troubleshooting and user assistance procedures | 4 hours | Problem-solving workshop | Technical support experience | Support documentation troubleshooting tools | EO Engineer (Support) | Week 15 | 12 | Troubleshooting scenario assessment | AVD Support Specialist Certificate | Planned | Include escalation procedures and ticket management
TRN-012 | Technical | Support | Operations Team | AVD Monitoring and Alerting | Learn system monitoring alert configuration and performance optimization | 3 hours | Technical workshop | TRN-011 completion | Azure Monitor Log Analytics access | EO Delivery Engineer (Monitoring) | Week 15 | 8 | Monitoring configuration exercise | AVD Operations Certificate | Planned | Include capacity planning and scaling
TRN-013 | Security | Compliance | Security Team | AVD Security and Compliance Management | Learn security controls compliance monitoring and audit procedures | 3 hours | Security briefing | Security background | Security documentation compliance frameworks | EO Engineer (Security) | Week 15 | 6 | Security assessment review | AVD Security Certificate | Planned | Include conditional access and data protection
TRN-014 | Business | Change Management | All Users | AVD Adoption and Change Management | Understand migration benefits and adoption strategies | 1 hour | All-hands presentation |  | Presentation materials migration guides | EO Engineer (Training) | Week 14 | 75 | Participation and feedback | Change Readiness Certificate | Planned | Focus on user adoption and communication
TRN-015 | Technical | Advanced | Technical Leads | AVD Architecture and Design Principles | Advanced understanding of AVD architecture and design best practices | 4 hours | Technical deep dive | Senior technical experience | Architecture documentation design specifications | EO Sales Engineer (Solution Architecture) | Week 14 | 6 | Architecture review exercise | AVD Technical Leadership Certificate | Planned | Include future roadmap and advanced scenarios
TRN-016 | Technical | Automation | DevOps Team | AVD Infrastructure as Code and Automation | Learn to automate AVD deployment and management with ARM templates | 1 day | Hands-on workshop | Infrastructure as Code experience | Azure DevOps access ARM templates | EO Delivery Engineer (Infrastructure) | Week 15 | 6 | Automation exercise | IaC Automation Certificate | Planned | Include CI/CD pipeline integration
TRN-017 | Business | Migration | Migration Team | User Data and Application Migration | Learn migration planning user communication and data transfer | 4 hours | Planning workshop | Migration experience | Migration tools user data samples | EO Engineer (User Profile) | Week 14 | 8 | Migration plan assessment | Migration Specialist Certificate | Planned | Include timeline and communication planning
TRN-018 | Technical | Networking | Network Team | AVD Network Optimization and Troubleshooting | Learn network optimization connectivity troubleshooting and performance tuning | 3 hours | Technical workshop | Network troubleshooting experience | Network monitoring tools connectivity tests | EO Delivery Engineer (Infrastructure) | Week 15 | 6 | Network troubleshooting exercise | Network Optimization Certificate | Planned | Include WAN optimization and QoS
TRN-019 | Business | Training | IT Trainers | Train-the-Trainer for AVD User Education | Learn to deliver effective AVD training to end users | 4 hours | Trainer development workshop | Training experience | Training materials presentation tools | EO Engineer (Training) | Week 15 | 4 | Training delivery assessment | AVD Trainer Certification | Planned | Include adult learning principles and change management
TRN-020 | Technical | Application | Application Team | Application Compatibility and Optimization for AVD | Learn application testing virtualization and optimization techniques | 1 day | Technical workshop | Application management experience | Test applications compatibility tools | EO Engineer (Application) | Week 14 | 8 | Application assessment exercise | Application Optimization Certificate | Planned | Include MSIX app attach and performance tuning