## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Virtual Wan Global
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Executive Status Report | Executive Sponsors | Virtual WAN project status and global network transformation progress | Weekly | Email Report | EO Project Manager | Email distribution list |  | "Network deployment progress, performance metrics, cost savings, key decisions needed" | EO Quarterback and IT Director | Executive | Report delivered on time and strategic decisions made | Active | [DATE] | Include network performance metrics and ROI tracking
COMM-002 | Virtual WAN Steering Committee | Project Steering Committee | Strategic direction and scope decisions for global network implementation | Bi-weekly | In-Person Meeting | EO Project Manager | Meeting invitation | 60 minutes | "Global network strategy, site connectivity, budget, timeline, scope changes" | EO Quarterback and Department Heads | Strategic | Meeting attendance >80% and critical decisions documented | Active | [DATE] | Decision authority for network requirements and vendor selection
COMM-003 | Network Team Standup | Core Virtual WAN Team | Daily coordination for Azure infrastructure and site connectivity | Daily | Virtual Meeting | EO Quarterback | Video conference | 15 minutes | "Hub deployment progress, site connectivity status, technical blockers" | Network Team and Azure Engineers | Operational | Daily attendance >90% and technical blockers resolved | Active | [DATE] | Focus on Azure services coordination and site deployment
COMM-004 | Azure Architecture Review | Technical and Network Teams | Virtual WAN architecture optimization and performance tuning | Weekly | Technical Meeting | EO Quarterback | Meeting invitation | 90 minutes | "Hub configuration, routing optimization, security integration" | EO Sales Engineer (Solution Architecture) and Network Architects | Technical | Architecture decisions documented and performance targets achieved | Active | [DATE] | Include Azure networking optimization and cost management
COMM-005 | Network Infrastructure Risk Review | Risk Management Team | Connectivity risks and network performance monitoring | Bi-weekly | Risk Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Connectivity risks, performance degradation, vendor dependencies" | EO Project Manager and EO Delivery Engineer (Technical Leadership) | Management | Risk register updated and network-specific mitigations tracked | Active | [DATE] | Focus on global connectivity risks and vendor coordination
COMM-006 | Site Connectivity Feedback | Site Managers and Network Users | Site requirements validation and connectivity experience feedback | Weekly | Workshop Session | EO Sales Engineer | Workshop invitation | 120 minutes | "Site connectivity requirements, performance feedback, application access" | Site Managers and Network Users | Business | Site sign-off on connectivity and application performance | Active | [DATE] | Include hands-on testing of site-to-site connectivity
COMM-007 | Virtual WAN Sprint Review | Network Development Team | Infrastructure progress and connectivity demonstrations | Bi-weekly | Demo Meeting | EO Quarterback | Video conference | 60 minutes | "Hub deployment status, site connectivity, performance demonstrations" | Network Team and Product Owner | Team | Connectivity goals achieved and feedback incorporated | Active | [DATE] | Live demonstration of hub-to-spoke connectivity and routing
COMM-008 | Microsoft Support Coordination | Microsoft Technical Teams | Azure Virtual WAN service optimization and best practices | Weekly | Technical Call | EO Engineer | Conference call | 45 minutes | "Virtual WAN service performance, hub optimization, troubleshooting" | Microsoft Technical Team and EO Sales Engineer (Solution Architecture) | Technical | Microsoft service performance targets met and issues resolved | Active | [DATE] | Track Virtual WAN SLAs and optimization opportunities
COMM-009 | Network Performance Review | Network Operations and Monitoring Teams | Network performance validation and optimization requirements | Weekly | Performance Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Latency metrics, throughput analysis, connectivity quality" | Network Operations Team and Performance Engineers | Quality | Performance goals met and network quality within tolerance | Active | [DATE] | Include network performance baselines and optimization analysis
COMM-010 | Change Control Board | Change Control Board | Network configuration changes and routing modifications | As Needed | Change Meeting | EO Engineer | Meeting invitation | 60 minutes | "Routing changes, security policy updates, hub configurations" | Change Control Board Members | Governance | Change requests processed within SLA and impact assessed | Active | [DATE] | Include network impact assessment and rollback procedures
COMM-011 | Site Deployment Update | Field Operations and Site Teams | Site deployment progress and readiness assessment | Bi-weekly | Deployment Call | EO Engineer | Conference call | 30 minutes | "Site preparation status, equipment deployment, connectivity testing" | Field Operations Team and Site Coordinators | Operational | Deployment milestones met and site readiness validated | Active | [DATE] | Include hands-on site connectivity validation
COMM-012 | Security and Compliance Review | Security and Network Teams | Network security posture and compliance validation | Monthly | Security Meeting | EO Quarterback | Meeting invitation | 60 minutes | "Firewall policies, traffic inspection, compliance validation" | Security Team and Network Security Engineer | Security | Security requirements met and compliance validated | Active | [DATE] | Include Azure Firewall integration and threat protection
COMM-013 | Azure Infrastructure Update | Infrastructure and Cloud Teams | Azure resource performance and cost optimization | Weekly | Infrastructure Call | EO Engineer | Conference call | 30 minutes | "Azure resource utilization, Virtual WAN costs, capacity planning" | Infrastructure Team and Cloud Architect | Technical | Infrastructure performance targets met and costs optimized | Active | [DATE] | Include Azure cost monitoring and resource optimization
COMM-014 | Business Readiness Assessment | Business Stakeholders | Network transition readiness and application performance | Bi-weekly | Business Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Application performance readiness, business continuity, process changes" | Business Managers and Application Owners | Business | Business readiness criteria met and applications validated | Active | [DATE] | Include application performance validation over new network
COMM-015 | Go-Live Preparation | Go-Live Coordination Team | Production cutover and network go-live readiness | Daily (2 weeks before) | Go-Live Meeting | EO Project Manager | Video conference | 30 minutes | "Cutover checklist, production readiness, rollback procedures" | All Team Leads and Operations Manager | Critical | Go-live criteria met and network cutover ready | Planned | [DATE] | Intensive coordination for network production cutover
COMM-016 | Post-Implementation Review | Project and Operations Teams | Network performance review and optimization opportunities | Monthly (3 months) | Review Meeting | EO Quarterback | Meeting invitation | 90 minutes | "Performance trends, cost optimization, enhancement opportunities" | Core Project Team and Business Stakeholders | Review | Performance improvements identified and optimization roadmap created | Planned | [DATE] | Include network utilization analysis and capacity planning
COMM-017 | Critical Issue Escalation | Emergency Response Team | Critical network failures and connectivity issues | As Needed | Emergency Call | EO Sales Engineer | Emergency notification | Variable | "Network outages, routing failures, security incidents, resolution actions" | Incident Response Team and Management | Emergency | Critical issues resolved within SLA and service restored | Active | [DATE] | Include emergency communication and service restoration
COMM-018 | Stakeholder Briefing | All Project Stakeholders | General Virtual WAN project updates and network transformation progress | Monthly | All-Hands Meeting | EO Project Manager | Town hall meeting | 45 minutes | "Network modernization progress, performance improvements, cost savings" | All Project Stakeholders | Informational | Stakeholder engagement maintained and progress communicated | Active | [DATE] | Include network transformation achievements and business benefits
COMM-019 | Technical Deep Dive | Technical and Network Teams | Virtual WAN technical knowledge sharing and problem-solving | As Needed | Technical Session | EO Quarterback | Meeting invitation | 90 minutes | "Architecture challenges, routing optimization, integration solutions" | Technical Team Members and Network Engineers | Technical | Technical challenges resolved and Virtual WAN knowledge shared | Active | [DATE] | Include Azure networking best practices and troubleshooting
COMM-020 | Client Update Call | External Client | Client Virtual WAN progress and network performance updates | Bi-weekly | Client Call | EO Project Manager | Client meeting | 45 minutes | "Network transformation progress, performance metrics, business value" | Client Stakeholders and Account Manager | Client | Client satisfaction maintained and network value communicated | Active | [DATE] | Professional communication with clear business value and ROI
COMM-021 | Network Monitoring Review | Operations and NOC Teams | Network monitoring and alerting effectiveness | Weekly | Monitoring Meeting | EO Quarterback | Video conference | 45 minutes | "Monitoring coverage, alert effectiveness, performance baselines" | NOC Team and Monitoring Engineers | Technical | Monitoring effectiveness maintained and issues detected proactively | Active | [DATE] | Include monitoring dashboards and alert tuning
COMM-022 | Vendor Coordination | Vendor Management and Technical Teams | ISP and vendor performance and service delivery | Bi-weekly | Vendor Meeting | EO Quarterback | Meeting invitation | 60 minutes | "Service delivery status, performance issues, contract compliance" | Vendor Managers and Technical Leads | Business | Vendor performance targets met and service delivery validated | Active | [DATE] | Include SLA tracking and vendor performance metrics
COMM-023 | Capacity Planning Review | Network Planning and Operations Teams | Network capacity and growth planning | Monthly | Planning Meeting | EO Engineer | Meeting invitation | 45 minutes | "Traffic growth analysis, capacity utilization, expansion planning" | Network Planning Team and Operations | Technical | Capacity planning targets met and growth accommodated | Active | [DATE] | Include traffic analysis and capacity forecasting
COMM-024 | Cost Optimization Review | Finance and Technical Teams | Network cost management and optimization | Monthly | Cost Meeting | EO Project Manager | Meeting invitation | 30 minutes | "Azure costs, circuit costs, optimization opportunities" | Finance Team and Technical Leads | Financial | Cost targets met and optimization opportunities identified | Active | [DATE] | Include detailed cost analysis and optimization recommendations