## Slide 1
Project Closeout
Microsoft CMMC GCC High Enclave
Project Manager | November 27, 2025

## Slide 2
Executive Summary
Project Duration: 6 months, on schedule
Budget: $153,240 Year 1 delivered on budget
Go-Live Date: Week 15 as planned
Certification: CMMC Level 2 achieved Week 26
NIST 800-171: All 110 controls implemented
User Migration: 50 CUI users onboarded
Security Posture: Zero incidents during migration
Microsoft CMMC GCC High Enclave
Notes: *Opening Statement:*
Good [morning/afternoon]. Today we celebrate the successful completion of the Microsoft CMMC GCC High Enclave implementation. This project has transformed [Client Name]'s compliance posture, enabling pursuit of DoD contracts requiring CMMC Level 2 certification.
*Key Talking Points - Expand on Each Bullet:*
**Project Duration - 6 Months:**
- Executed exactly as planned in Statement of Work
- Phase 1 (Gap Assessment & Design): Months 1-2 - NIST 800-171 gap assessment completed
- Phase 2 (GCC High Deployment): Months 3-4 - M365 GCC High tenant and Azure Government deployed
- Phase 3 (CMMC Preparation): Months 5-6 - C3PAO assessment completed, certification achieved
- No schedule slippage despite complexity of CAC/PIV integration
**Budget - $153,240 Year 1:**
- Cloud Services: $47,640 (Azure Government, ExpressRoute)
- Software Licenses: $87,600 (M365 GCC High E5 for 50 users)
- Support & Maintenance: $18,000 (30-day hypercare + monitoring)
- Actual spend: $152,890 - $350 under budget
**Go-Live - Week 15:**
- Pilot-then-production migration strategy executed flawlessly
- Week 1: 10 pilot users migrated to GCC High
- Week 2: Validation period with CAC/PIV authentication testing
- Weeks 3-4: Remaining 40 users migrated in departmental waves
- Zero data loss during migration
**CMMC Level 2 Certification - Week 26:**
- C3PAO assessment completed with zero open findings
- All 110 NIST 800-171 controls validated
- DoD CMMC Marketplace registration complete
- Organization now eligible for CUI-handling DoD contracts
*Transition to Next Slide:*
"Let me walk you through exactly what we built together..."

## Slide 3
Solution Architecture
Microsoft 365 GCC High
  Exchange Online with 10-year archive
  SharePoint, Teams, OneDrive
  Microsoft Purview DLP policies
Azure Government Cloud
  5 VMs for CUI workloads
  2TB encrypted storage
  VNet with ExpressRoute
Security & Monitoring
  Sentinel SIEM (100GB/month)
  Defender for Cloud posture mgmt
  CAC/PIV authentication
Microsoft CMMC GCC High Enclave
Notes: *Architecture Overview - Walk Through the Diagram:*
"This diagram shows the FedRAMP High authorized architecture we deployed. Let me walk through each component..."
**Microsoft 365 GCC High Layer:**
- Deployed FedRAMP High authorized M365 tenant
- Exchange Online: 50 mailboxes with 100GB total data migrated
- SharePoint Online: 500GB CUI document storage with DLP
- Teams: Secure collaboration with external sharing disabled
- OneDrive: Known Folder Move configured for file sync
- Microsoft Purview: Sensitivity labels for CUI classification
**Azure Government Cloud Layer:**
- Subscription provisioned in us-gov-virginia region
- Virtual Network with network segmentation:
- Management subnet for administrative access
- CUI workload subnet for protected resources
- 5 Standard_D4s_v3 VMs for CUI workload hosting
- 2TB premium SSD storage with FIPS 140-2 encryption
- ExpressRoute for private, dedicated connectivity
**Identity & Access Management:**
- Azure AD GCC High tenant with DoD integration
- CAC/PIV smart card authentication for all 50 users
- Conditional Access policies enforcing:
- MFA on all access
- Device compliance checks
- Location-based restrictions
- 3 roles configured: CUI processor, admin, reviewer
**Security Monitoring:**
- Sentinel SIEM: 100GB/month log ingestion
- All M365 and Azure logs centralized
- 5 incident response playbooks configured
- 90-day log retention for NIST 800-171 compliance
- Defender for Cloud:
- CMMC compliance dashboard operational
- Vulnerability assessment enabled
- Real-time security alerts (<15 min response)
**Key Architecture Decisions:**
1. Single region deployment (us-gov-virginia) per SOW scope
2. GCC High selected for FedRAMP High compliance
3. Sentinel SIEM for centralized security monitoring
4. CAC/PIV integration via Azure AD GCC High
*Transition:*
"Now let me show you the complete deliverables package we're handing over..."

## Slide 4
Deliverables Inventory
Deliverable | Purpose | Location
NIST 800-171 Gap Assessment | Compliance baseline and remediation roadmap | `/delivery/gap-assessment.docx`
GCC High Architecture Document | M365 and Azure Government design | `/delivery/detailed-design.docx`
System Security Plan (SSP) | CMMC control narratives and evidence | `/delivery/ssp.docx`
Implementation Guide | Step-by-step deployment procedures | `/delivery/implementation-guide.docx`
Project Plan | Timeline, RACI, communications plan | `/delivery/project-plan.xlsx`
ARM/Terraform Templates | Infrastructure as Code for Azure Gov | `/delivery/scripts/terraform/`
Operations Runbook | Incident response and compliance monitoring | `/delivery/docs/runbook.md`
Training Materials | ISSO/ISSM and security operations guides | `/delivery/training/`
Microsoft CMMC GCC High Enclave
Notes: *Deliverables Deep Dive - Review Each Item:*
**1. NIST 800-171 Gap Assessment Report:**
- 45-page comprehensive assessment
- Evaluated all 14 control families
- Initial SPRS score documented
- Remediation roadmap with prioritized actions
- Approved by ISSO/ISSM
**2. GCC High Architecture Document (detailed-design.docx):**
- Complete technical architecture
- M365 GCC High tenant configuration
- Azure Government infrastructure design
- CAC/PIV authentication flow diagrams
- Network architecture with security controls
- Data flow and encryption specifications
**3. System Security Plan (SSP):**
- 110 NIST 800-171 control narratives
- Evidence artifacts for each control
- Control implementation descriptions
- Continuous monitoring procedures
- Used successfully for C3PAO assessment
**4. Implementation Guide:**
- Step-by-step deployment procedures
- GCC High tenant provisioning
- Azure Government resource deployment
- CAC/PIV integration configuration
- Sentinel SIEM setup and tuning
- Migration procedures for email and files
**5. Project Plan:**
- Four worksheets:
1. Project Timeline - 26-week implementation
2. Milestones - 7 key milestones tracked
3. RACI Matrix - Clear accountability
4. Communications Plan - Stakeholder engagement
- All milestones achieved on schedule
**6. Infrastructure as Code:**
- ARM templates for Azure Government resources
- Terraform modules for repeatable deployment
- Sentinel workbook configurations
- Compliance policy definitions
**7. Operations Runbook:**
- Daily security monitoring procedures
- Sentinel alert response playbooks
- Vulnerability management process
- C3PAO assessment preparation checklist
- NIST 800-171 continuous monitoring
**8. Training Materials:**
- ISSO/ISSM compliance management guide
- Security operations procedures
- CAC/PIV user troubleshooting
- Video recordings (4 sessions, 6 hours total)
*Transition:*
"Let's look at how we're performing against our targets..."

## Slide 5
Quality & Performance
Compliance Metrics
  NIST 800-171 Controls: 110/110 (100%)
  CMMC Level 2: Certified Week 26
  C3PAO Findings: 0 open findings
  SPRS Score: +110 (maximum)
  Compliance Dashboard: 98.5% score
Security Metrics
  Sentinel Alert Response: <12 min avg
  Vulnerability Remediation: 100% on SLA
  MFA Enforcement: 100% coverage
  Data Encryption: FIPS 140-2 validated
  Zero security incidents recorded
Microsoft CMMC GCC High Enclave
Notes: *Quality & Performance Deep Dive:*
**Compliance Metrics - Detailed Breakdown:**
*NIST 800-171 Controls: 110/110 Implemented*
- All 14 control families addressed:
- Access Control (AC): 22 controls
- Awareness and Training (AT): 3 controls
- Audit and Accountability (AU): 9 controls
- Configuration Management (CM): 9 controls
- Identification and Authentication (IA): 11 controls
- Incident Response (IR): 3 controls
- Maintenance (MA): 6 controls
- Media Protection (MP): 9 controls
- Personnel Security (PS): 2 controls
- Physical Protection (PE): 6 controls
- Risk Assessment (RA): 3 controls
- Security Assessment (CA): 4 controls
- System and Communications Protection (SC): 16 controls
- System and Information Integrity (SI): 7 controls
*CMMC Level 2 Certification:*
- C3PAO: [Assessment Organization Name]
- Assessment dates: Weeks 24-25
- Final certification: Week 26
- Zero open POA&Ms
- DoD CMMC Marketplace registration complete
*SPRS Score: +110*
- Maximum achievable score
- All controls implemented and validated
- Documented evidence for each control
- Ready for DoD contract submissions
**Security Metrics - Detailed Analysis:**
*Sentinel Alert Response: <12 Minutes Average*
- SOW target: <15 minutes
- Achieved: 12 minutes average response
- 5 automated playbooks reduce MTTR
- Critical alerts: 8 minutes average
- High alerts: 15 minutes average
*Vulnerability Remediation: 100% SLA Compliance*
- Critical vulnerabilities: 24-hour SLA
- High vulnerabilities: 7-day SLA
- Monthly vulnerability scans operational
- Zero outstanding critical/high findings
*MFA Enforcement: 100%*
- All 50 CUI users require CAC/PIV
- Conditional Access policies enforced
- No password-only access permitted
- Emergency access procedures documented
*Data Encryption: FIPS 140-2 Validated*
- All data at rest: AES-256 encryption
- All data in transit: TLS 1.2+
- Azure Key Vault for key management
- Email encryption with S/MIME
*Transition:*
"These capabilities translate directly into business value. Let me show you the benefits we're already seeing..."

## Slide 6
Benefits Realized
Benefit Category | Target | Achieved | Business Impact
CMMC Certification | Level 2 | Level 2 | DoD contract eligibility enabled
Time to Certification | 6 months | 6 months | 66% faster than on-premises
Compliance Automation | 90% | 95% | Reduced manual audit effort
Security Posture | NIST 800-171 | 100% compliant | Contract requirement met
User Productivity | Minimal disruption | <2 hr downtime | Seamless migration
Cost Avoidance | $500K capex | $0 capex | Cloud vs on-premises savings
Microsoft CMMC GCC High Enclave
Notes: *Benefits Analysis - Detailed ROI Discussion:*
**CMMC Level 2 Certification - Contract Eligibility:**
*Before Implementation:*
- Could not pursue DoD contracts requiring CMMC Level 2
- Estimated $8M+ annual contract opportunity at risk
- Self-assessment only - not sufficient for contract awards
*After Implementation:*
- CMMC Level 2 certified by C3PAO
- Eligible for all CUI-handling DoD contracts
- Competitive advantage over non-certified competitors
- Foundation for CMMC Level 3 if needed
**Time to Certification - 6 Months:**
*Traditional On-Premises Approach:*
- Typical timeline: 18+ months
- Capital expenditure: $500K+ for CMMC enclave
- Physical datacenter buildout required
- On-premises PKI infrastructure needed
*GCC High Cloud Approach:*
- Timeline: 6 months (66% faster)
- No capital expenditure - operational expense model
- FedRAMP High controls inherited
- Microsoft manages underlying infrastructure
**Compliance Automation - 95% Automated:**
*Manual Compliance (Before):*
- Quarterly manual control assessments
- Manual evidence collection for audits
- Spreadsheet-based compliance tracking
- 40+ hours per month compliance effort
*Automated Compliance (After):*
- Defender for Cloud continuous monitoring
- Sentinel automated compliance dashboards
- Real-time NIST 800-171 control validation
- <5 hours per month compliance effort
- 95% reduction in manual compliance work
**Cost Comparison:**
| Category | On-Premises | GCC High | Savings |
|----------|-------------|----------|---------|
| Infrastructure Capex | $500K+ | $0 | $500K |
| Year 1 Total | $680K | $153K | $527K |
| 3-Year TCO | $1.2M | $460K | $740K |
| Time to Certification | 18 months | 6 months | 12 months |
**ROI Summary:**
- Year 1 investment: $153,240
- DoD contract opportunity: $8M+ annually
- Payback period: <3 months (if contract awarded)
- 3-year ROI: 1,600%+ based on contract enablement
*Transition:*
"We learned valuable lessons during this implementation that will help with future initiatives..."

## Slide 7
Lessons Learned & Recommendations
What Worked Well
  Phased migration reduced risk
  C3PAO engaged early (Month 4)
  CAC/PIV pilot validated approach
  Sentinel playbooks accelerated response
  Weekly stakeholder demos
Challenges Overcome
  ExpressRoute provisioning delay
  CAC certificate expiration issues
  DLP policy false positives
  User adoption of new workflows
  GCC High tenant provisioning lead time
Recommendations
  Expand to additional doc types
  Implement advanced threat hunting
  Plan for CMMC Level 3 if needed
  Quarterly compliance reviews
  Annual C3PAO reassessment prep
Microsoft CMMC GCC High Enclave
Notes: *Lessons Learned - Comprehensive Review:*
**What Worked Well - Details:**
*1. Phased Migration Strategy:*
- Pilot group (10 users) validated CAC/PIV workflow
- Issues identified before full migration
- User feedback incorporated into training
- Zero data loss across all migration waves
*2. Early C3PAO Engagement (Month 4):*
- Selected C3PAO during Phase 2
- Pre-assessment readiness review in Month 5
- Assessment timeline confirmed
- No delays due to C3PAO availability
*3. CAC/PIV Pilot Validation:*
- Tested with 5 users before full rollout
- Identified certificate synchronization issues
- Conditional Access policies refined
- User experience optimized
*4. Sentinel Playbooks:*
- 5 automated response playbooks deployed
- Reduced mean time to response by 60%
- Consistent incident handling
- Reduced analyst workload
**Challenges Overcome - Details:**
*1. ExpressRoute Provisioning:*
- Challenge: 4-week lead time not anticipated
- Impact: Azure Government connectivity delayed
- Resolution: Started provisioning in Week 1
- Lesson: Plan ExpressRoute 6 weeks ahead
*2. CAC Certificate Expiration:*
- Challenge: 5 users had expired certificates
- Impact: Could not authenticate to GCC High
- Resolution: Coordinated with DoD PKI team
- Lesson: Verify all CAC certificates before migration
*3. DLP Policy False Positives:*
- Challenge: Initial DLP rules too aggressive
- Impact: Legitimate documents blocked
- Resolution: Tuned sensitivity labels and policies
- Lesson: Start with monitoring mode, then enforce
**Recommendations for Future Enhancement:**
*1. Expand Document Types:*
- Current: Invoices, POs, contracts
- Recommended: Add technical drawings, CAD files
- Estimated effort: 2-3 weeks per document type
*2. Advanced Threat Hunting:*
- Implement Sentinel hunting queries
- Schedule weekly threat hunting sessions
- Integrate threat intelligence feeds
*3. CMMC Level 3 Preparation:*
- If pursuing IL5/IL6 contracts
- Requires additional 58 controls
- Estimated 6-month effort
*Transition:*
"Let me walk you through how we're transitioning support to your team..."

## Slide 8
Support Transition
Hypercare Complete (30 days)
  Daily health checks completed
  2 minor issues resolved
  Knowledge transfer sessions done
  Runbook procedures validated
  ISSO/ISSM fully trained
Steady State Support
  Monthly compliance reviews
  Quarterly security assessments
  Sentinel monitoring 24/7
  Vulnerability scan weekly
  C3PAO reassessment annual
Escalation Path
  L1: Internal IT Help Desk
  L2: ISSO/Security Team
  L3: Microsoft GCC High Support
  Emergency: Security Operations
  Executive: Account Manager
Microsoft CMMC GCC High Enclave
Notes: *Support Transition - Complete Details:*
**Hypercare Period Summary (30 Days Post-Certification):**
*Daily Activities Completed:*
- Morning health check (9am) - Sentinel dashboard review
- Compliance posture monitoring
- CAC/PIV authentication verification
- Azure Government resource status
- M365 GCC High service health
*Issues Resolved During Hypercare:*
Issue #1 (Minor) - Day 5:
- Problem: Sentinel alert noise from scheduled tasks
- Root cause: Windows Update triggering false positives
- Resolution: Added exclusion rules to detection
- Prevention: Documented in runbook
Issue #2 (Minor) - Day 12:
- Problem: OneDrive sync paused for 3 users
- Root cause: Known Folder Move conflict
- Resolution: Reset sync relationship
- Prevention: Added to troubleshooting guide
*Knowledge Transfer Sessions Delivered:*
| Session | Date | Attendees | Duration |
|---------|------|-----------|----------|
| Sentinel SIEM Operations | Week 1 | 4 SOC staff | 3 hours |
| CMMC Compliance Monitoring | Week 2 | ISSO/ISSM | 2 hours |
| CAC/PIV Troubleshooting | Week 2 | IT Support | 1.5 hours |
| Defender for Cloud | Week 3 | Security team | 2 hours |
| C3PAO Reassessment Prep | Week 4 | ISSO/ISSM | 2 hours |
**Steady State Support Model:**
*What Client Team Handles (L1/L2):*
- Daily Sentinel monitoring via dashboards
- User CAC/PIV authentication support
- Basic DLP policy exceptions
- Monthly compliance reporting
- Vulnerability remediation coordination
*When to Escalate (L3):*
- Sentinel detection rule changes
- Conditional Access policy modifications
- Azure Government infrastructure changes
- C3PAO assessment preparation
- Security incidents requiring forensics
**Monthly Operational Tasks:**
- Week 1: NIST 800-171 compliance review
- Week 2: Vulnerability scan analysis
- Week 3: Security metrics reporting
- Week 4: Continuous monitoring validation
**Quarterly Tasks:**
- Security posture assessment
- Compliance evidence collection
- SSP updates if controls changed
- Tabletop incident response exercise
**Annual Tasks:**
- C3PAO reassessment preparation
- CMMC certification renewal
- Security architecture review
- Training refresh for all users
*Transition:*
"Let me acknowledge the team that made this possible and outline next steps..."

## Slide 9
Acknowledgments & Next Steps
Executive sponsors for securing budget and CMMC program commitment
ISSO/ISSM for System Security Plan development and C3PAO coordination
IT team for GCC High migration execution and user support
Security team for Sentinel operations and incident response
This Week: Final documentation handover, archive project artifacts
Next 30 Days: First monthly compliance review, SPRS score submission
Next Quarter: C3PAO annual reassessment planning, CMMC Level 3 evaluation
Microsoft CMMC GCC High Enclave
Notes: *Acknowledgments - Recognize Key Contributors:*
**Client Team Recognition:**
*Executive Sponsor - [Name]:*
- Championed CMMC compliance program
- Secured budget approval for GCC High migration
- Cleared organizational blockers
- Demonstrated commitment to DoD contract pursuit
*ISSO/ISSM - [Name]:*
- Led System Security Plan development
- Coordinated C3PAO assessment activities
- Provided control implementation evidence
- Will own ongoing compliance operations
*IT Lead - [Name]:*
- Managed GCC High tenant provisioning
- Coordinated CAC/PIV integration
- Supported user migration waves
- Knowledge transfer recipient
*Security Team:*
- Configured Sentinel SIEM playbooks
- Established security monitoring procedures
- Conducted incident response training
- Ongoing security operations owners
**Immediate Next Steps (This Week):**
| Task | Owner | Due Date |
|------|-------|----------|
| Final documentation handover | PM | [Date] |
| Archive project SharePoint | PM | [Date] |
| SPRS score submission | ISSO | [Date] |
| DoD contract pursuit | Business Dev | Ongoing |
**30-Day Next Steps:**
| Task | Owner | Due Date |
|------|-------|----------|
| First monthly compliance review | ISSO | [Date+30] |
| Sentinel tuning recommendations | Security | [Date+30] |
| User satisfaction survey | PM | [Date+30] |
| Identify expansion opportunities | Business | [Date+30] |
**Quarterly Planning:**
*CMMC Level 3 Evaluation:*
- Assess need based on contract requirements
- 58 additional controls required
- Estimated 6-month implementation
- Budget planning for FY25
*C3PAO Annual Reassessment:*
- Schedule 3 months before expiration
- Continuous monitoring evidence ready
- SSP updates documented
- No assessment gaps expected
*Transition:*
"Thank you for your partnership on this project. Let me open the floor for questions..."

## Slide 10
Thank You
Notes: *Closing and Q&A Preparation:*
**Closing Statement:**
"Thank you for your partnership throughout this CMMC compliance journey. We've successfully achieved CMMC Level 2 certification, enabling [Client Name] to pursue DoD contracts requiring CUI handling. The GCC High environment is operational, your team is trained, and you're ready for ongoing compliance operations.
I want to open the floor for questions. We have [time] remaining."
**Anticipated Questions and Prepared Answers:**
*Q: What if we need CMMC Level 3?*
A: Level 3 requires 58 additional controls focused on protecting CUI from advanced persistent threats. If you're pursuing contracts with Level 3 requirements, we can conduct a gap assessment and provide a 6-month implementation roadmap. Estimated investment: $100-150K additional.
*Q: How do we maintain certification?*
A: CMMC certification requires annual reassessment by a C3PAO. Your ISSO/ISSM should maintain continuous monitoring evidence via Defender for Cloud and Sentinel dashboards. We recommend scheduling reassessment 3 months before expiration to allow remediation time if needed.
*Q: What are the ongoing costs?*
A: Annual run rate is approximately $153,240:
- M365 GCC High E5 (50 users): $87,600/year
- Azure Government services: $47,640/year
- Support and maintenance: $18,000/year
Costs scale with user count and Azure resource usage.
*Q: Can we add more users?*
A: Yes. Additional GCC High licenses are $146/user/month. Onboarding includes CAC/PIV enrollment, Conditional Access configuration, and security awareness training. Budget 2-3 hours per user for onboarding.
*Q: What if CAC/PIV authentication fails?*
A: The runbook includes troubleshooting procedures for common CAC issues: certificate expiration, middleware conflicts, and Azure AD sync delays. Emergency break-glass accounts are available for critical business continuity scenarios.
*Q: How do we handle a security incident?*
A: Sentinel playbooks automate initial response. The runbook includes escalation procedures: L1 (IT Help Desk), L2 (ISSO/Security Team), L3 (Microsoft Support). For critical incidents, contact security operations immediately.
**Demo Offer:**
"Would anyone like to see the Sentinel SIEM dashboard or Defender for Cloud compliance view? I can show you real-time security monitoring in action."
**Follow-Up Commitments:**
- [ ] Send final presentation to all attendees
- [ ] Distribute CMMC compliance quick reference guide
- [ ] Schedule first monthly compliance review
- [ ] Provide C3PAO reassessment planning template
- [ ] Share CMMC Level 3 gap assessment proposal (if requested)
**Final Closing:**
"Thank you again for trusting our team with your CMMC compliance program. This certification positions [Client Name] for significant DoD contract opportunities. We look forward to supporting your continued compliance success.
Please don't hesitate to reach out to me or [Account Manager] if any questions arise. Have a great [rest of your day/afternoon]."