## Cover
Project Plan
Generated: | November 27, 2025
Solution: | Cmmc Enclave
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Phase 1 Gap Assessment & Design
Phase 1: Gap Assessment & Design
Milestone ID | Target Date | Milestone | Deliverables | Owner | Status
MS-1.1 | [DATE+2w] | NIST 800-171 Gap Assessment Complete | Gap assessment report; Initial SPRS score | Security Architect | Not Started
MS-1.2 | [DATE+4w] | System Security Plan Draft Complete | SSP with 110 control narratives; Evidence mapping | ISSO/ISSM | Not Started
MS-1.3 | [DATE+6w] | GCC High Architecture Finalized | Detailed design document; Network diagrams; Cost model | Solution Architect | Not Started
MS-1.4 | [DATE+8w] | Phase 1 Design Approval | Signed design approval; ExpressRoute ordered | Project Manager | Not Started

## Phase 2 GCC High Deployment
Phase 2: GCC High Deployment
Milestone ID | Target Date | Milestone | Deliverables | Owner | Status
MS-2.1 | [DATE+10w] | M365 GCC High Tenant Configured | Tenant configured; Conditional Access policies; DLP | M365 Engineer | Not Started
MS-2.2 | [DATE+12w] | Azure Government Resources Deployed | VNet deployed; Key Vault; Sentinel workspace | Azure Engineer | Not Started
MS-2.3 | [DATE+13w] | Pilot Migration Complete (10 Users) | 10 users migrated; CAC/PIV validated; Pilot report | Migration Lead | Not Started
MS-2.4 | [DATE+16w] | Production Migration Complete (50 Users) | All 50 users migrated; Email/files migrated; DNS cutover | Migration Lead | Not Started
MS-2.5 | [DATE+17w] | Sentinel SIEM Operational | Data connectors enabled; Playbooks deployed; Dashboards | Security Engineer | Not Started

## Phase 3 CMMC Preparation
Phase 3: CMMC Preparation
Milestone ID | Target Date | Milestone | Deliverables | Owner | Status
MS-3.1 | [DATE+20w] | Pre-Assessment Validation Complete | All 110 controls validated; Evidence package complete | ISSO/ISSM | Not Started
MS-3.2 | [DATE+21w] | C3PAO Readiness Review | Pre-assessment completed; Remediation items addressed | Security Architect | Not Started
MS-3.3 | [DATE+24w] | C3PAO Assessment Complete | Assessment completed; Findings documented | C3PAO | Not Started
MS-3.4 | [DATE+25w] | CMMC Level 2 Certification Achieved | CMMC certificate issued; SPRS score +110 submitted | Project Manager | Not Started
MS-3.5 | [DATE+26w] | Hypercare Complete and Handover | 30-day hypercare complete; Training delivered; Runbooks | Project Manager | Not Started