## Cover
Project Plan
Generated: | November 30, 2025
Solution: | Sample Solution
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Planning | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | Project Manager | Not Started
Planning | Requirements Gathering | 4 days | [START_DATE+1] | [START_DATE+5] | Project Kickoff | Business Analyst | Not Started
Planning | Solution Architecture Design | 7 days | [START_DATE+3] | [START_DATE+10] | Requirements Gathering | Solution Architect | Not Started
Planning | Infrastructure Planning | 7 days | [START_DATE+8] | [START_DATE+15] | Architecture Design | Infrastructure Architect | Not Started
Design | Detailed Design | 10 days | [START_DATE+15] | [START_DATE+25] | Infrastructure Planning | Technical Lead | Not Started
Design | Security Design | 5 days | [START_DATE+18] | [START_DATE+23] | Architecture Design | Security Architect | Not Started
Design | Integration Design | 7 days | [START_DATE+20] | [START_DATE+27] | Detailed Design | Integration Specialist | Not Started
Build | Environment Setup | 7 days | [START_DATE+25] | [START_DATE+32] | Infrastructure Planning | DevOps Engineer | Not Started
Build | Core Development | 20 days | [START_DATE+30] | [START_DATE+50] | Detailed Design | Development Team | Not Started
Build | Integration Development | 12 days | [START_DATE+35] | [START_DATE+47] | Integration Design | Integration Developer | Not Started
Build | Security Implementation | 10 days | [START_DATE+38] | [START_DATE+48] | Security Design | Security Developer | Not Started
Test | Unit Testing | 12 days | [START_DATE+40] | [START_DATE+52] | Core Development | Development Team | Not Started
Test | Integration Testing | 10 days | [START_DATE+50] | [START_DATE+60] | Integration Development | QA Engineer | Not Started
Test | System Testing | 15 days | [START_DATE+55] | [START_DATE+70] | Unit Testing | QA Team | Not Started
Test | Security Testing | 7 days | [START_DATE+60] | [START_DATE+67] | Security Implementation | Security Tester | Not Started
Test | User Acceptance Testing | 10 days | [START_DATE+70] | [START_DATE+80] | System Testing | Business Users | Not Started
Deploy | Production Environment Setup | 7 days | [START_DATE+75] | [START_DATE+82] | Environment Setup | Infrastructure Team | Not Started
Deploy | Pre-Deployment Testing | 5 days | [START_DATE+80] | [START_DATE+85] | UAT Complete | QA Lead | Not Started
Deploy | Production Deployment | 2 days | [START_DATE+85] | [START_DATE+87] | Production Env Ready | Deployment Team | Not Started
Deploy | User Training Delivery | 15 days | [START_DATE+75] | [START_DATE+90] | UAT Complete | Training Team | Not Started
Deploy | Go-Live Support | 7 days | [START_DATE+89] | [START_DATE+96] | Deployment Complete | Support Team | Not Started
Closure | Hypercare Period | 30 days | [START_DATE+96] | [START_DATE+126] | Go-Live | Support Team | Not Started
Closure | Project Documentation | 10 days | [START_DATE+90] | [START_DATE+100] | All Deliverables | Project Manager | Not Started
Closure | Project Closure | 2 days | [START_DATE+126] | [START_DATE+128] | Hypercare Complete | Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Project Kickoff | [START_DATE] | All stakeholders attended kickoff meeting; project charter approved | Project Manager | Not Started
M2 | Requirements Approved | [START_DATE+5] | Requirements document signed off by business stakeholders | Business Analyst | Not Started
M3 | Architecture Approved | [START_DATE+10] | Architecture design approved by technical governance board | Solution Architect | Not Started
M4 | Design Complete | [START_DATE+25] | All detailed design documents completed and approved | Technical Lead | Not Started
M5 | Development Complete | [START_DATE+52] | All development completed; unit tests passing with 80%+ coverage | Development Team Lead | Not Started
M6 | Testing Complete | [START_DATE+80] | All test phases completed; no critical/high defects open | QA Lead | Not Started
M7 | Go-Live | [START_DATE+87] | Solution deployed to production; validation complete | Project Manager | Not Started
M8 | Project Closure | [START_DATE+128] | Hypercare complete; project formally closed with lessons learned | Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | SA | BA | TL | QA | DevOps | SecArch | Client
Project Charter | A | C | C | I | I | I | I | C
Requirements Document | A | C | R | C | C | I | C | C
Architecture Design | A | R | C | C | I | C | C | I
Detailed Design | A | C | I | R | C | C | C | I
Development | A | C | I | R | I | C | I | I
Test Plan | A | I | C | C | R | I | C | I
Test Execution | A | I | I | C | R | I | C | I
Security Implementation | A | C | I | C | C | I | R | I
Infrastructure Setup | A | C | I | C | I | R | C | I
User Training | A | I | C | I | I | I | I | R
Go-Live Approval | A | C | C | C | C | C | C | R
Production Deployment | A | C | I | C | I | R | C | I
Post-Go-Live Support | A | I | I | C | I | R | I | I
Legend:
R | A A: Responsible - Does the work
A | A A: Accountable - Ultimate ownership
C | A A: Consulted - Provides input
I | A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch project and align on objectives | Project Manager | Day 1
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic direction and issue resolution | Project Manager | Alternate Tuesdays
Status Meeting | Weekly | Core project team | Review progress and address blockers | Project Manager | Mondays 10:00
Technical Review | Weekly | Technical leads | Technical design decisions and issues | Solution Architect | Wednesdays 14:00
Risk Review | Bi-weekly | PM and Risk Manager | Risk assessment and mitigation tracking | Risk Manager | Alternate Fridays
Sprint Review | Bi-weekly | Development team and stakeholders | Sprint demo and feedback | Technical Lead | End of Sprint
QA Review | Weekly | QA and Development teams | Test progress and quality metrics | QA Lead | Thursdays 11:00
Go-Live Readiness | Daily (2 weeks pre) | Go-live team | Go-live preparation and checklist | Project Manager | Daily 09:00