## Cover
Training Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Sample Solution
Customer Name: | Data table for training plan
Version: | 1.0

## Training Plan
Training ID | Module Name | Target Audience | Duration Hours | Format | Prerequisites | Learning Objectives | Materials Required | Trainer | Scheduled Date | Location | Max Attendees | Status | Completion Rate | Feedback Score | Notes
TRN-001 | System Overview and Architecture | Administrators | 2 | ILT | Basic system administration knowledge | Describe solution architecture, Navigate admin interface, Explain data flow | Presentation slides, System access, Architecture diagrams | System Architect | [DATE] | Conference Room A | 15 | Planned |  |  | Foundation module for all admin training
TRN-002 | User Management and Security | Administrators | 3 | ILT | TRN-001 completed | Configure user accounts, Set permissions, Manage security policies | Admin guide, Test accounts, Security checklist | Security Engineer | [DATE] | Conference Room B | 12 | Planned |  |  | Critical for system security
TRN-003 | System Configuration | Administrators | 4 | Hands-On Lab | TRN-001 and TRN-002 completed | Configure system settings, Customize workflows, Set up integrations | Configuration guide, Lab environment, Test data | Technical Lead | [DATE] | Training Lab | 8 | Planned |  |  | Hands-on practice essential
TRN-004 | Backup and Recovery | Administrators | 2 | VILT | System administration experience | Execute backup procedures, Perform recovery operations, Monitor system health | Backup procedures guide, Recovery checklist | Operations Manager | [DATE] | Virtual | 20 | Planned |  |  | Critical operational procedures
TRN-005 | Performance Monitoring | Administrators | 2 | E-Learning | Basic monitoring concepts | Set up monitoring, Interpret metrics, Configure alerts | Online modules, Monitoring tools access | Performance Engineer | [DATE] | Self-Paced | Unlimited | Planned |  |  | Self-paced with practical exercises
TRN-006 | Core Functionality | End Users | 1.5 | ILT | Basic computer skills | Navigate user interface, Perform daily tasks, Use core features | User guide, System access, Sample data | Business Analyst | [DATE] | Conference Room C | 25 | Planned |  |  | Essential for all end users
TRN-007 | Data Entry and Processing | End Users | 2 | Hands-On Lab | TRN-006 completed | Enter data accurately, Process workflows, Generate reports | Data entry guide, Practice datasets, Report templates | Subject Matter Expert | [DATE] | Training Lab | 15 | Planned |  |  | Practical skills development
TRN-008 | Reporting and Analytics | Power Users | 3 | ILT | TRN-006 completed | Create custom reports, Analyze data, Export information | Reporting guide, Analytics tools, Sample queries | Data Analyst | [DATE] | Conference Room A | 12 | Planned |  |  | Advanced reporting capabilities
TRN-009 | Advanced Features | Power Users | 4 | VILT | TRN-006 and TRN-007 completed | Use advanced functions, Customize interfaces, Automate tasks | Advanced user guide, Automation examples | Technical Lead | [DATE] | Virtual | 15 | Planned |  |  | Power user capabilities
TRN-010 | Troubleshooting | Power Users | 2 | E-Learning | Basic troubleshooting skills | Diagnose issues, Apply solutions, Escalate problems | Troubleshooting guide, Issue scenarios | Support Manager | [DATE] | Self-Paced | Unlimited | Planned |  |  | Self-service support skills
TRN-011 | Management Dashboard | Managers | 1 | ILT | Basic computer skills | Access dashboards, Interpret KPIs, Generate executive reports | Manager guide, Dashboard access, KPI definitions | Business Analyst | [DATE] | Executive Conference Room | 10 | Planned |  |  | Executive-level overview
TRN-012 | System Integration | IT Support | 3 | Hands-On Lab | Integration experience | Configure integrations, Troubleshoot connections, Monitor data flow | Integration guide, Test environments, API documentation | Integration Specialist | [DATE] | IT Lab | 8 | Planned |  |  | Technical integration skills
TRN-013 | Technical Troubleshooting | IT Support | 4 | ILT | TRN-012 completed | Diagnose technical issues, Use diagnostic tools, Resolve problems | Technical guide, Diagnostic tools, Issue database | Technical Support Lead | [DATE] | IT Training Room | 10 | Planned |  |  | Advanced technical support
TRN-014 | User Support Procedures | IT Support | 2 | VILT | Customer service experience | Handle user requests, Use ticketing system, Escalate issues | Support procedures, Ticketing system access | Support Manager | [DATE] | Virtual | 20 | Planned |  |  | Support desk procedures
TRN-015 | Quick Reference Materials | All Users | 0.5 | Job Aid |  | Access quick help, Use reference cards, Find support resources | Quick reference cards, Help system | Self-Service | [DATE] | Workplace | Unlimited | Planned |  |  | Always available resources
TRN-016 | New User Orientation | New Hires | 1 | E-Learning |  | Understand solution purpose, Know basic navigation, Identify support resources | Orientation materials, Welcome packet | Self-Service | [DATE] | Self-Paced | Unlimited | Planned |  |  | Onboarding for new employees
TRN-017 | Change Management | Change Champions | 2 | ILT | Leadership experience | Communicate changes, Support adoption, Gather feedback | Change management toolkit, Communication templates | Change Manager | [DATE] | Conference Room B | 15 | Planned |  |  | Critical for successful adoption
TRN-018 | Train-the-Trainer | Internal Trainers | 8 | ILT | Training experience | Deliver training sessions, Use training materials, Assess learning | Training materials, Presentation skills guide | Training Manager | [DATE] | Training Center | 6 | Planned |  |  | Build internal training capacity
TRN-019 | System Refresh Training | Existing Users | 1 | VILT | Previous system experience | Learn new features, Understand changes, Update workflows | Update guide, Feature demos | Product Owner | [DATE] | Virtual | 50 | Planned |  |  | For system updates and enhancements
TRN-020 | Advanced Troubleshooting Workshop | Administrators | 4 | Workshop | TRN-003 and operational experience | Solve complex issues, Use advanced tools, Document solutions | Advanced troubleshooting guide, Complex scenarios | Senior Technical Lead | [DATE] | Workshop Room | 8 | Planned |  |  | Advanced problem-solving skills