## Cover
[DOCUMENT TITLE]
Level of Effort
AWS - Ai - Intelligent Document Processing
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Document Types | 2-3 document types | 2-3 document types | 4-6 document types | 8+ document types or complex variations | Standard document types for IDP
Solution Scope | AI/ML Complexity | AWS Textract/Comprehend only | AWS Textract/Comprehend only | Custom classification models | Advanced custom models + NLP | Pre-built vs custom model development
Integration | External System Integrations | 2 REST APIs | 2 REST APIs | 4-6 systems | 8+ systems or complex protocols | Standard REST/API integrations for document flow
Integration | Data Sources | S3 and email ingestion | 2-3 data sources | 4-6 data sources | 8+ data sources or complex formats | Document input channels and storage
User Base | Total Users | 50 users | 50 users | 100-250 users | 500+ users | Users submitting and reviewing documents
User Base | User Roles | 3 roles (submitter reviewer admin) | 2-3 standard roles | 4-6 roles | 8+ roles with complex permissions | Document processors reviewers administrators
Data Volume | Document Processing Volume | 1000-5000 docs/month | 1000-5000 docs/month | 10000-50000 docs/month | 100000+ docs/month | Monthly document processing volume
Data Volume | Data Storage Requirements | 500 GB | 500 GB | 2 TB | 10+ TB | Document storage and retention
Technical Environment | Deployment Regions | Single AWS region (us-east-1) | Single AWS region | 2-3 regions | Global multi-region | Geographic distribution for IDP
Technical Environment | Availability Requirements | Standard (99.5%) | Standard (99.5%) | High availability (99.9%) | Mission critical (99.95%+) | SLA for document processing
Technical Environment | Infrastructure Complexity | Serverless (Lambda S3 Textract) | Basic serverless | Multi-tier standard | Complex distributed with custom ML | AWS Lambda S3 Textract Comprehend architecture
Security & Compliance | Security Requirements | Basic encryption IAM SSE-S3 | Basic encryption IAM | Industry standard (SOC2 HIPAA) | Advanced (FedRAMP multi-jurisdiction) | Document security and access controls
Security & Compliance | Compliance Frameworks | SOC2 | 1-2 basic standards | 2-3 industry standards | Multiple complex frameworks | Regulatory compliance for documents
Performance | Accuracy Requirements | 95%+ extraction accuracy | 95%+ standard | 98%+ enhanced | 99%+ with human review | Data extraction accuracy targets
Performance | Processing Speed | Standard batch processing | Standard batch processing | Near real-time processing | Real-time with sub-second response | Document processing speed requirements
Environment | Deployment Environments | 2 environments (dev prod) | 2 environments (dev prod) | 3 environments (dev staging prod) | 4+ environments with ML pipelines | Environment management for IDP

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Requirements Gathering, Document Analysis, AWS Assessment, Compliance Review)
Planning | PLANNING_MX | 1 | All Planning phase tasks (IDP Solution Design, Data Flow Design, Security Architecture, Project Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (AWS Infrastructure, Document Pipeline, AI/ML Integration, Custom Models, API Development)
Testing | TESTING_MX | 1 | All Testing phase tasks (Unit Testing, Document Testing, Performance Testing, Accuracy Testing, Security Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, Model Deployment, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Administrator Training, Business User Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline)
Management | MANAGEMENT_MX | 1.5 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Requirements Gathering | Conduct stakeholder interviews for IDP requirements | EO Engineer | 32 |  |  | 150 |  |  | Includes requirements documentation and document processing workflow analysis
Discovery | Document Analysis | Analyze document types volumes and data extraction requirements | EO Engineer | 24 |  |  | 200 |  |  | Customer must provide representative document samples for each document type
Discovery | AWS Environment Assessment | Evaluate AWS infrastructure and AI/ML services readiness | EO Engineer | 24 |  |  | 200 |  |  | Customer must provide AWS account access and service limits information
Discovery | Compliance Review | Assess data privacy compliance and security requirements | EO Engineer | 16 |  |  | 175 |  |  | Identifies PII/PHI handling requirements and document retention policies
Planning | IDP Solution Design | Design AWS AI/ML architecture with Textract Comprehend A2I | EO Engineer | 40 |  |  | 200 |  | Requirements Gathering | Deliverable: AWS architecture diagram with AI/ML service integration design
Planning | Data Flow Design | Design document ingestion processing and output workflows | EO Engineer | 24 |  |  | 180 |  | Document Analysis | Deliverable: Document processing workflow and data flow diagrams
Planning | Security Architecture | Design security controls encryption and access for documents | EO Engineer | 24 |  |  | 175 |  | Compliance Review | Document encryption at rest/transit IAM roles and audit logging design
Planning | Project Planning | Develop implementation timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  | IDP Solution Design | Deliverable: Project plan with phased rollout and milestone schedule
Development | AWS Infrastructure Setup | Provision Textract Comprehend S3 Lambda and supporting services | EO Engineer | 40 |  |  | 160 |  | IDP Solution Design | Includes S3 buckets Lambda functions API Gateway and CloudWatch setup
Development | Document Processing Pipeline | Build document ingestion and processing workflows | EO Engineer | 64 |  |  | 130 |  | AWS Infrastructure Setup | Serverless event-driven pipeline with error handling and retry logic
Development | AI/ML Model Integration | Integrate AWS Textract Comprehend and A2I services | EO Engineer | 48 |  |  | 170 |  | Document Processing Pipeline | Configure Textract APIs Comprehend entity recognition and A2I workflows
Development | Custom Classification Models | Develop minimal classification logic for 2-3 document types | EO Engineer | 24 |  |  | 165 |  | AI/ML Model Integration | Simple classification using AWS pre-built services - not full custom ML models
Development | Data Extraction Logic | Build structured data extraction and validation logic | EO Engineer | 32 |  |  | 130 |  | Custom Classification Models | Includes field validation business rules and confidence scoring
Development | API Development | Create REST APIs for document submission and retrieval | EO Engineer | 24 |  |  | 125 |  | Data Extraction Logic | API Gateway endpoints with authentication and rate limiting
Development | Web Interface | Build document upload and results viewing interface | EO Engineer | 32 |  |  | 125 |  | API Development | Simple upload UI with drag-drop and results dashboard - not full application
Testing | Unit Testing | Develop automated tests for all processing components | EO Engineer | 32 |  |  | 120 |  | Data Extraction Logic | Automated test suite for Lambda functions and API endpoints
Testing | Document Processing Testing | Test various document types formats and qualities | EO Engineer | 32 |  |  | 120 |  | Web Interface | Customer must provide comprehensive test document library with variations
Testing | Performance Testing | Test system performance with high document volumes | EO Engineer | 24 |  |  | 140 |  | Document Processing Testing | Load testing with realistic document volumes and concurrent processing
Testing | Accuracy Testing | Validate AI/ML model accuracy and data extraction quality | EO Engineer | 24 |  |  | 170 |  | Performance Testing | Statistical validation of extraction accuracy against labeled test dataset
Testing | Security Testing | Perform security testing on document handling pipeline | EO Engineer | 16 |  |  | 175 |  | Accuracy Testing | Includes IAM policy validation encryption testing and audit log verification
Deployment | Production Deployment | Deploy IDP solution to production AWS environment | EO Engineer | 24 |  |  | 160 |  | Security Testing | Blue-green deployment with rollback procedures and smoke testing
Deployment | Model Deployment | Deploy trained ML models to production endpoints | EO Engineer | 16 |  |  | 170 |  | Production Deployment | Deploy classification logic and configure production Textract/Comprehend
Deployment | Go-Live Support | Provide support during initial production rollout | EO Engineer | 40 |  |  | 110 |  | Model Deployment | Daily monitoring rapid issue response and accuracy validation during hypercare
Training | Administrator Training | Train system administrators on IDP solution management | EO Engineer | 16 |  |  | 130 |  | Production Deployment | Includes AWS service management CloudWatch monitoring and troubleshooting
Training | Business User Training | Train users on document submission and results review | EO Engineer | 16 |  |  | 120 |  | Administrator Training | Role-based training for document processors and quality reviewers
Training | Documentation | Create user guides technical documentation and runbooks | EO Engineer | 24 |  |  | 110 |  | Business User Training | Deliverable: Operations runbook user guides and troubleshooting procedures
Closeout | Knowledge Transfer | Transfer solution ownership to client operations team | EO Engineer | 16 |  |  | 140 |  | Documentation | Comprehensive handover including AWS architecture model details and procedures
Closeout | Performance Baseline | Establish performance metrics and monitoring baselines | EO Engineer | 8 |  |  | 130 |  | Knowledge Transfer | Establishes accuracy SLAs processing time metrics and cost monitoring
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  |  |  | 200 |  |  | AWS AI/ML architecture review and technical escalation support
Management | Project Management | Project coordination planning and management activities | EO Project Manager |  |  |  | 150 |  |  | Includes weekly status reporting risk management and stakeholder coordination
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | EO Sales Engineer: Update phase-based multipliers in Estimate Settings based on customer document processing scope

## Credits
Credits - Applied to Total Cost (Year 1 Only)
Credit Type | Credit Amount | Credit Comments
AWS Partner Services Credit | -10000 | AWS Partner Network (APN) credit for solution architecture and AI/ML integration services
Implementation Discount | 0 | No implementation discount applicable
TOTAL