## Cover
[VENDOR LOGO]
Level Of Effort Estimate
Presales Document
Generated: | November 18, 2025
Solution: | Onpremise To Cloud Migration
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Scope Assumptions
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Workloads to Migrate | 5-10 VMs/applications | 5-10 workloads | 10-25 workloads | 25+ workloads or complex apps | Number of workloads being migrated
Solution Scope | Migration Strategy | Rehost (lift-and-shift) | Rehost simple | Replatform moderate | Refactor complex | AWS 6R migration strategy
Integration | Source Environment | VMware vSphere on-premises | Single hypervisor | Multiple hypervisors | Hybrid cloud + physical servers | Current infrastructure platform
Integration | Hybrid Connectivity | AWS Direct Connect | VPN only | Direct Connect | Direct Connect + VPN redundancy | On-premises to AWS connectivity
User Base | Total Users | 100 application users | 50-100 users | 100-500 users | 500+ users | End users of migrated apps
User Base | User Roles | 3 roles (admin operator user) | 2-3 standard roles | 4-6 roles | 8+ roles with migration access | Roles for migration and operation
Data Volume | Total Data to Migrate | 500 GB | 100-500 GB | 500 GB - 2 TB | 2+ TB | Total data volume for migration
Data Volume | Database Migration | 2 databases (MySQL PostgreSQL) | 1-2 databases | 3-5 databases | 6+ databases or complex schemas | Database migration scope
Technical Environment | Target AWS Region | us-east-1 | Single region | Multi-AZ deployment | Multi-region deployment | AWS target deployment region
Technical Environment | Availability Requirements | Standard (99.5%) | Standard (99.5%) | High availability (99.9%) | Mission critical (99.95%+) | Post-migration availability SLA
Technical Environment | Infrastructure Complexity | EC2 RDS S3 standard | Basic IaaS | Standard AWS services | Advanced AWS native services | Target AWS architecture complexity
Security & Compliance | Security Requirements | VPC Security Groups IAM | Basic cloud security | Industry standard (SOC2) | Advanced (compliance frameworks) | Cloud security controls
Security & Compliance | Compliance Frameworks | SOC2 | 1-2 basic standards | 2-3 industry standards | Multiple complex frameworks | Post-migration compliance
Performance | Migration Window | Weekend maintenance windows | Single cutover | Phased migration | Zero-downtime migration | Migration execution strategy
Performance | Performance Requirements | Match on-premises baseline | Standard performance | Enhanced cloud performance | Optimized cloud-native | Post-migration performance targets
Environment | Deployment Environments | 2 environments (dev prod) | 2 environments | 3 environments | 4+ environments with automation | Target cloud environments

## Estimate Settings
INSTRUCTIONS: How to Use Estimate Settings
This sheet contains phase-based multiplier variables that control effort scaling for each project phase.
The EO Sales Engineer updates these multipliers based on customer scope compared to baseline assumptions.
How It Works:
1. Review customer requirements from Discovery Questionnaire
2. Compare customer scope to Baseline Assumptions (see 'Scope Assumptions' sheet)
3. Update YELLOW HIGHLIGHTED multiplier values below (Column C) for each phase
4. All tasks in that phase on the 'LOE' sheet automatically update their Actual Hours
5. Total cost recalculates automatically
Multiplier Guidelines:
• 1.0 = Matches baseline exactly (Small scope)
• 1.5-2.0 = Medium scope (moderately above baseline)
• 2.0-3.0 = Large scope (significantly above baseline)
• 3.0+ = Very large/complex (substantially above baseline, document rationale)
Example: Customer needs comprehensive testing due to compliance → Set TESTING_MX to 2.0
Example: Complex architecture requiring more technical oversight → Set LEADERSHIP_MX to 1.5
ESTIMATE SETTINGS - Update phase multipliers in Column C below:
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks
Planning | PLANNING_MX | 1 | All Planning phase tasks
Development | DEVELOPMENT_MX | 1 | All Development phase tasks
Testing | TESTING_MX | 1 | All Testing phase tasks
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks
Training | TRAINING_MX | 1 | All Training phase tasks
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks
Management | MANAGEMENT_MX | 1.5 | Project Management overhead
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead

## LOE
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Cloud Requirements Gathering | Conduct stakeholder interviews for cloud migration/infrastructure | EO Engineer | 40 |  |  | 150 |  |  | Focus on scalability performance and business objectives
Discovery | Infrastructure Assessment | Analyze current infrastructure workloads and dependencies | EO Engineer | 32 |  |  | 200 |  |  | Include application dependencies and performance baselines
Discovery | AWS Services Assessment | Evaluate target AWS services and architecture patterns | EO Engineer | 24 |  |  | 200 |  |  | Focus on cost optimization and best practices
Discovery | Compliance Review | Assess security governance and compliance requirements | EO Engineer | 16 |  |  | 175 |  |  | Include industry regulations and data residency
Planning | AWS Architecture Design | Design AWS cloud architecture and migration strategy | EO Engineer | 48 |  |  | 200 |  |  | Include multi-AZ design and disaster recovery
Planning | Migration Strategy | Develop detailed migration approach and timeline | EO Engineer | 32 |  |  | 180 |  |  | Include risk assessment and rollback procedures
Planning | Security Architecture | Design AWS security controls and governance framework | EO Engineer | 24 |  |  | 175 |  |  | Include IAM networking and data protection
Planning | Project Planning | Develop cloud implementation timeline and resource allocation | EO Engineer | 24 |  |  | 140 |  |  | Coordinate with infrastructure and security teams
Development | AWS Infrastructure Provisioning | Provision AWS services networking and foundational infrastructure | EO Engineer | 60 |  |  | 160 |  |  | Include VPC subnets security groups and routing
Development | Application Migration | Migrate applications and workloads to AWS | EO Engineer | 80 |  |  | 130 |  |  | Include application optimization and testing
Development | Data Migration | Migrate databases and data stores to AWS | EO Engineer | 48 |  |  | 145 |  |  | Include data validation backup and recovery testing
Development | Monitoring and Operations | Implement AWS monitoring logging and operational tools | EO Engineer | 40 |  |  | 140 |  |  | Include CloudWatch X-Ray and operational dashboards
Development | Automation and IaC | Develop infrastructure automation using CloudFormation/CDK | EO Engineer | 32 |  |  | 125 |  |  | Include CI/CD pipeline integration
Testing | Unit Testing | Develop automated tests for all solution components | EO Engineer | 32 |  |  | 120 |  |  | Include technology-specific testing frameworks
Testing | Integration Testing | Test system integrations data flows and external dependencies | EO Engineer | 40 |  |  | 120 |  |  | Include end-to-end workflow validation
Testing | Performance Testing | Conduct load performance and scalability testing | EO Engineer | 24 |  |  | 140 |  |  | Include production-like environment and stress testing
Testing | Security Testing | Perform security assessments penetration testing and compliance validation | EO Engineer | 16 |  |  | 175 |  |  | Include vulnerability scanning and compliance checks
Testing | User Acceptance Testing | Coordinate UAT with business users and stakeholders | EO Engineer | 32 |  |  | 150 |  |  | Include training feedback collection and sign-off
Deployment | Production Deployment | Deploy solution to production environment with monitoring | EO Engineer | 24 |  |  | 160 |  |  | Include blue-green deployment rollback and validation
Deployment | Go-Live Support | Provide comprehensive support during initial production rollout | EO Engineer | 48 |  |  | 110 |  |  | Include 24/7 support monitoring and issue resolution
Training | Administrator Training | Train system administrators and technical support teams | EO Engineer | 16 |  |  | 130 |  |  | Include hands-on technical training and certification
Training | End User Training | Train business users on solution functionality and workflows | EO Engineer | 24 |  |  | 120 |  |  | Include role-based training documentation and support
Training | Documentation | Create comprehensive technical and user documentation | EO Engineer | 32 |  |  | 110 |  |  | Include runbooks troubleshooting guides and best practices
Closeout | Knowledge Transfer | Transfer solution ownership to operations and support teams | EO Engineer | 16 |  |  | 140 |  |  | Include operational procedures escalation and maintenance
Closeout | Performance Baseline | Establish performance metrics monitoring baselines and SLAs | EO Engineer | 8 |  |  | 130 |  |  | Include KPI definition monitoring setup and reporting
Management | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback | 40 |  |  | 180 |  |  | 25% of engineering effort
Management | Project Management | Project coordination and management activities | EO Project Manager | 40 |  |  | 150 |  |  | 20% of engineering effort
[5 empty] | TOTAL HOURS |  | TOTAL COST |  |  | Total project cost estimate