## Cover
Project Plan
Generated: | November 27, 2025
Solution: | Onpremise To Cloud Migration
Customer: | [Customer Name]
Version: | 1.0
Status: | Draft
eoframework.org

## Project Timeline
Project Timeline
Phase | Task | Duration | Start Date | End Date | Dependencies | Owner | Status
Assessment | Project Kickoff | 1 day | [START_DATE] | [START_DATE+1] | None | EO Project Manager | Not Started
Assessment | Infrastructure Discovery | 6 days | [START_DATE+1] | [START_DATE+7] | Project Kickoff | EO Quarterback | Not Started
Assessment | Application Portfolio Analysis | 7 days | [START_DATE+3] | [START_DATE+10] | Infrastructure Discovery | EO Quarterback | Not Started
Assessment | Dependency Mapping | 7 days | [START_DATE+8] | [START_DATE+15] | Portfolio Analysis | EO Sales Engineer | Not Started
Assessment | Network Assessment | 7 days | [START_DATE+5] | [START_DATE+12] | Infrastructure Discovery | EO Engineer (Migration) | Not Started
Assessment | Security and Compliance Review | 7 days | [START_DATE+8] | [START_DATE+15] | Infrastructure Discovery | EO Quarterback | Not Started
Assessment | AWS Landing Zone Design | 10 days | [START_DATE+15] | [START_DATE+25] | Security Review | EO Quarterback | Not Started
Assessment | Migration Wave Planning | 7 days | [START_DATE+18] | [START_DATE+25] | Dependency Mapping | EO Engineer (Migration) | Not Started
Assessment | Cost Optimization Strategy | 7 days | [START_DATE+20] | [START_DATE+27] | Portfolio Analysis | EO Sales Engineer | Not Started
Implementation | Migration Factory Setup | 10 days | [START_DATE+25] | [START_DATE+35] | Landing Zone Design | EO Engineer (Migration) | Not Started
Implementation | AWS Environment Setup | 10 days | [START_DATE+35] | [START_DATE+45] | Migration Factory Setup | EO Engineer (Migration) | Not Started
Implementation | Network Connectivity | 7 days | [START_DATE+40] | [START_DATE+47] | AWS Environment Setup | EO Engineer (Migration) | Not Started
Implementation | Security Baseline Implementation | 10 days | [START_DATE+42] | [START_DATE+52] | AWS Environment Setup | EO Engineer (Migration) | Not Started
Migration | Pilot Migration (Wave 0) | 10 days | [START_DATE+50] | [START_DATE+60] | Migration Factory Setup | EO Engineer (Migration) | Not Started
Migration | Wave 1 Migration | 15 days | [START_DATE+65] | [START_DATE+80] | Pilot Migration | EO Engineer (Migration) | Not Started
Migration | Database Migration | 15 days | [START_DATE+60] | [START_DATE+75] | Network Connectivity | EO Engineer (Migration) | Not Started
Migration | Wave 2 Migration | 15 days | [START_DATE+85] | [START_DATE+100] | Wave 1 Migration | EO Engineer (Migration) | Not Started
Migration | Wave 3 Migration | 15 days | [START_DATE+105] | [START_DATE+120] | Wave 2 Migration | EO Engineer (Migration) | Not Started
Testing | Performance Testing | 15 days | [START_DATE+70] | [START_DATE+85] | Wave 1 Migration | EO Engineer (Migration) | Not Started
Testing | Security Testing | 10 days | [START_DATE+80] | [START_DATE+90] | Security Implementation | EO Engineer (Migration) | Not Started
Testing | Disaster Recovery Testing | 7 days | [START_DATE+90] | [START_DATE+97] | Wave 3 Migration | EO Engineer (Migration) | Not Started
Testing | User Acceptance Testing | 15 days | [START_DATE+95] | [START_DATE+110] | Wave 3 Migration | EO Sales Engineer | Not Started
Optimization | Cloud Cost Optimization | 10 days | [START_DATE+110] | [START_DATE+120] | Wave 3 Migration | EO Engineer (Migration) | Not Started
Optimization | Performance Optimization | 10 days | [START_DATE+115] | [START_DATE+125] | Performance Testing | EO Engineer (Migration) | Not Started
Handover | Cloud Operations Training | 15 days | [START_DATE+100] | [START_DATE+115] | Wave 3 Migration | EO Engineer (Migration) | Not Started
Handover | End User Training | 10 days | [START_DATE+110] | [START_DATE+120] | UAT Complete | EO Sales Engineer | Not Started
Handover | Documentation and Runbooks | 15 days | [START_DATE+115] | [START_DATE+130] | Operations Training | EO Engineer (Migration) | Not Started
Closure | On-Premise Decommissioning | 15 days | [START_DATE+125] | [START_DATE+140] | Cost Optimization | EO Engineer (Migration) | Not Started
Closure | Cloud Operations Handover | 7 days | [START_DATE+130] | [START_DATE+137] | Documentation Complete | EO Engineer (Migration) | Not Started
Closure | Hypercare Support | 30 days | [START_DATE+137] | [START_DATE+167] | Operations Handover | EO Engineer (Migration) | Not Started
Closure | Benefits Realization Assessment | 10 days | [START_DATE+150] | [START_DATE+160] | Decommissioning Complete | EO Sales Engineer | Not Started
Closure | Project Closure | 3 days | [START_DATE+167] | [START_DATE+170] | Hypercare Complete | EO Project Manager | Not Started

## Milestones
Milestones
Milestone ID | Milestone Name | Target Date | Success Criteria | Owner | Status
M1 | Assessment Complete | [START_DATE+27] | Application discovery and migration wave planning approved by stakeholders | EO Quarterback | Not Started
M2 | Landing Zone Ready | [START_DATE+45] | AWS multi-account environment operational with security baselines deployed | EO Engineer (Migration) | Not Started
M3 | Network Connected | [START_DATE+47] | Hybrid connectivity established between on-premise and AWS with validated throughput | EO Engineer (Migration) | Not Started
M4 | Pilot Complete | [START_DATE+60] | Wave 0 pilot migration successful with validated migration patterns and runbooks | EO Engineer (Migration) | Not Started
M5 | Wave 1 Complete | [START_DATE+80] | Wave 1 production applications migrated and validated in AWS environment | EO Engineer (Migration) | Not Started
M6 | Wave 2 Complete | [START_DATE+100] | Wave 2 business-critical applications migrated with zero data loss | EO Engineer (Migration) | Not Started
M7 | Wave 3 Complete | [START_DATE+120] | All in-scope applications migrated to AWS with performance targets achieved | EO Engineer (Migration) | Not Started
M8 | UAT Complete | [START_DATE+110] | User acceptance testing passed with business sign-off for all applications | EO Sales Engineer | Not Started
M9 | Training Complete | [START_DATE+120] | Operations team trained and ready to manage AWS environment independently | EO Engineer (Migration) | Not Started
M10 | Go-Live | [START_DATE+137] | Cloud operations handover complete with 24/7 support established | EO Project Manager | Not Started
M11 | Decommissioning Complete | [START_DATE+140] | On-premise infrastructure safely decommissioned with data destruction verified | EO Engineer (Migration) | Not Started
M12 | Project Closure | [START_DATE+170] | Project formally closed with lessons learned documented and benefits validated | EO Project Manager | Not Started

## RACI Matrix
RACI Matrix
Task/Deliverable | PM | QB | Sales | Mig Eng | Client IT | Sponsor | Ops | SME
Project Kickoff and Charter | A | C | C | C | C | R | I | I
Infrastructure Discovery | C | A | C | R | R | I | C | C
Application Portfolio Analysis | C | A | R | C | C | I | I | C
Dependency Mapping | C | C | A | R | C | I | I | C
Security and Compliance Review | C | A | C | R | C | I | C | I
AWS Landing Zone Design | C | A | C | R | C | I | I | I
Migration Wave Planning | C | C | C | A | C | I | C | C
Cost Optimization Strategy | C | C | A | C | C | I | I | I
Migration Factory Setup | C | C | I | A | C | I | I | I
AWS Environment Setup | C | C | I | A | C | I | C | I
Network Connectivity | C | C | I | A | R | I | C | I
Security Baseline Implementation | C | R | I | A | C | I | I | I
Pilot Migration Execution | A | C | I | R | C | I | C | I
Wave 1-3 Migration Execution | A | C | I | R | C | I | C | C
Database Migration | A | C | I | R | C | I | C | I
Performance Testing | A | C | I | R | C | I | C | I
Security Testing | A | R | I | R | C | I | I | I
User Acceptance Testing | A | C | R | C | C | C | C | R
Cloud Operations Training | A | C | R | R | C | I | R | I
Documentation and Runbooks | A | R | C | R | C | I | C | I
On-Premise Decommissioning | A | C | I | R | R | C | C | I
Cloud Operations Handover | A | C | C | R | R | I | R | I
Hypercare Support | A | C | I | R | C | I | C | I
Benefits Realization | A | C | R | C | C | C | I | I
Project Closure | A | C | C | I | C | I | I | I
Legend:
R | A A A A A A: Responsible - Does the work
A | A A A A A A: Accountable - Ultimate ownership
C | A A A A A A: Consulted - Provides input
I | A A A A A A: Informed - Kept updated

## Communications Plan
Communications Plan
Meeting Type | Frequency | Participants | Purpose | Owner | Day/Time
Project Kickoff | Once | All stakeholders | Launch migration project and align on objectives and success criteria | EO Project Manager | Day 1
Steering Committee | Bi-weekly | Executive sponsors and PMO | Strategic direction and issue resolution for migration program | EO Project Manager | Alternate Tuesdays
Status Meeting | Weekly | Core project team | Review migration progress against plan and address blockers | EO Project Manager | Mondays 10:00
Technical Review | Weekly | Technical leads and architects | AWS architecture decisions and migration technical issues | EO Quarterback | Wednesdays 14:00
Migration Planning | Weekly | Migration team | Plan upcoming migration waves and coordinate cutover activities | EO Engineer (Migration) | Thursdays 11:00
Wave Readiness | Pre-Wave | Wave stakeholders and ops team | Confirm readiness for upcoming migration wave with go/no-go decision | EO Project Manager | Friday before Wave
Cutover War Room | During Cutover | Migration and operations team | Real-time coordination during application cutover weekend | EO Engineer (Migration) | Cutover Weekend
Training Sessions | As Scheduled | IT operations and business users | Knowledge transfer on AWS operations and application changes | EO Sales Engineer | Per Training Plan